## IMS
OBS | WBS | OpenPlan ID | IMS ID | Jira Key | Control Acct Name | Work Package | SIP | Summary | 1LMX Plan SP | 1LMX Done SP | Remaining SP | % Complete | Baseline Start | Baseline End | 1LMX Actual Start | 1LMX Actual End | Planned Start Date | Planned End Date
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-5 | AES-5874 | ONELMX_MBE_SSC | MBE23LOE | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | 1Spc MBE: 1LMX LOE 23.2 - Exp - Lab/NL | 19.5 | 19.5 | 0 | 0% | 2023-04-02 | 2023-06-23 | 2023-04-02 | 2023-06-23 | 2023-03-27 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232C.0006 | SPACE-30 | AES-5898 | ONELMX_MBE_SSC | MBEDTI23CP | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Impl. DTw Platform and SBV Proto - Cap Lab/NL | 378.2 | 378.2 | 0 | 0% | 2023-04-02 | 2023-06-23 | 2023-04-02 | 2023-06-23 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0009 | SPACE-298 | AES-6166 | ONELMX_MBE_SSC | MBEDTI23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Req. and Release DTw Platform and SBV Proto - Exp Lab/NL | 89.5 | 89.5 | 0 | 0% | 2023-04-02 | 2023-06-23 | 2023-04-02 | 2023-06-23 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0003 | SPACE-401 | AES-6268 | ONELMX_MBE_SSC | MBECCA23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Architecture Rqmt, Modeling and Evaluation - Exp Lab/NL | 216.5 | 216.5 | 0 | 0% | 2023-04-02 | 2023-06-26 | 2023-04-02 | 2023-06-26 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232C.0004 | SPACE-545 | AES-6412 | ONELMX_MBE_SSC | MBECCA23CP | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Future Architecture Design Work - Cap Lab/NL | 130 | 113 | 17 | 0% | 2023-04-02 | 2023-06-27 | 2023-04-02 |  | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-612 | AES-6478 | ONELMX_MBE_SSC | MBE23LOE | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: ENABL LOE 23.2 - Exp - Lab/NL | 70.5 | 70.5 | 0 | 0% | 2023-04-02 | 2023-06-21 | 2023-04-02 | 2023-06-22 | 2023-03-27 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0004 | SPACE-682 | AES-6547 | ONELMX_MBE_SSC | MBEDPP23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Deployment 23.2 Quarterly Release - Exp Lab/NL | 13.9 | 13.9 | 0 | 0% | 2023-04-02 | 2023-06-19 | 2023-04-02 | 2023-06-19 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232C.0003 | SPACE-705 | AES-6571 | ONELMX_MBE_SSC | MBEDPP23CP | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Deployment 23.2 Quarterly Release - Cap Lab/NL | 462.1 | 462.1 | 0 | 0% | 2023-04-02 | 2023-06-26 | 2023-04-02 | 2023-06-26 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232C.0005 | SPACE-1051 | AES-6916 | ONELMX_MBE_SSC | MBEDTU23CP | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Impl. Design Automation And Tool Updates - Cap Lab/NL | 96.75 | 96.75 | 0 | 8.3% | 2023-01-29 | 2023-06-26 | 2023-01-29 | 2023-06-26 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0008 | SPACE-1143 | AES-7008 | ONELMX_MBE_SSC | MBEDTU23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Req. and Rel. Design Auto. and Tool Updates - EXP Lab/NL | 305.25 | 297.25 | 8 | 0% | 2023-04-02 | 2023-06-25 | 2023-04-02 |  | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0007 | SPACE-1388 | AES-7252 | ONELMX_MBE_SSC | MBEMBC23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Req. and Release MBC and Ops Efficiency - Exp Lab/NL | 201 | 201 | 0 | 0% | 2023-04-02 | 2023-06-28 | 2023-04-02 | 2023-06-28 | 2023-03-03 | 2023-05-23
1.5 | 1.3.1.5 | 4.2.05.231E.0047 | SPACE-1563 | AES-7427 | ONELMX_MBE_SSC | MBEMBC23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Space MBC Ops Eff Polyworks Expanded Deployment - Expense | 9.5 | 9.5 | 0 | 0% | 2023-01-01 | 2023-02-27 | 2023-01-01 | 2023-02-27 | 2023-01-03 | 2023-06-25
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-1575 | AES-7438 | ONELMX_MBE_SSC | MBE23LOE | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: PMO LOE 23.2 - Exp - Lab/NL | 129 | 129 | 0 | 10% | 2023-04-02 | 2023-06-26 | 2023-04-02 | 2023-06-25 | 2023-03-27 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0005 | SPACE-1776 | AES-7638 | ONELMX_MBE_SSC | MBESTK23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: PrgAd 23.2 Starter Kit Quarterly Release - Exp Labor/NL | 143.5 | 143.5 | 0 | 0% | 2023-04-02 | 2023-06-25 | 2023-04-01 | 2023-06-25 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-2009 | AES-7871 | ONELMX_MBE_SSC | MBE23LOE | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: PRGAD LOE 23.2 - Exp - Lab/NL | 299.8 | 299.8 | 0 | 0% | 2023-02-12 | 2023-06-28 | 2023-02-12 | 2023-06-28 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-2368 | AES-8229 | ONELMX_MBE_SSC | MBE23LOE | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: SCATS LOE 23.2 - Exp - Lab/NL | 386 | 386 | 0 | 0% | 2023-03-12 | 2023-06-26 | 2023-03-12 | 2023-06-26 | 2023-03-27 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232C.0008 | SPACE-2774 | AES-8634 | ONELMX_MBE_SSC | MBETEE23CP | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Impl. TSM 4.0, Thin Thread 1.0 - Cap Lab/NL | 359.5 | 359.5 | 0 | 0% | 2023-01-14 | 2023-06-26 | 2023-01-15 | 2023-06-26 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-3099 | AES-8959 | ONELMX_MBE_SSC | MBE23LOE | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: SCEE LOE 23.2 - Exp - Lab/NL | 26 | 26 | 0 | 100% | 2023-04-02 | 2023-06-25 | 2023-04-02 | 2023-06-26 | 2023-03-27 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0006 | SPACE-3136 | AES-8996 | ONELMX_MBE_SSC | MBETEE23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Req. - Release TSM 4.0, Thin Thread 1.0 - Exp Lab | 24 | 23 | 0 | 0% | 2023-03-12 | 2023-06-22 | 2023-03-12 | 2023-06-22 | 2023-04-03 | 2023-06-23
1.5 | 1.3.1.5 | 4.2.05.232E.0006 | SPACE-10000 | AES-NA | ONELMX_MBE_SSC | MBETEE23 | [{"self": "https://ebstools-jira.us.lmco.com/rest/api/2/customFieldOption/10602", "value": "Unrestricted", "id": "10602", "disabled": false}] | Spc MBE: Req. - NOT IN JIRA | 359.5 | 359.5 | 0 | 100% | 2023-01-15 | 2023-06-26 | 2023-01-15 | 2023-06-26 | 2023-04-03 | 2023-06-23
[5 empty] | JUNK |  |  | This is a notes field that shouldn't be in the compare

## SMBE 2023 Progress Measure (+)
OBS | WBS | OpenPlan ID | IMS ID | Jira Key | Control Acct Name | Work Package | Summary | 1LMX Plan SP | 1LMX Done SP | Remaining SP | % Complete | 1LMX Actual Start | 1LMX Actual End | Planned Start Date | Planned End Date | Level
[7 empty] | Capabilities & Enablers | 9891.75 | 6503.95 | 3387.8 | 65.75%
[7 empty] | 23.2 | 3359.5 | 3334.5 | 25 | 99.26%
|  |  | SPACE-4 |  |  |  | SLMX_MBE_1LMX | 19.5 | 19.5 | 0 | 100% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-5 | AES-5874 | ONELMX_MBE_SSC | MBE23LOE | Spc MBE: 1LMX LOE 23.2 - Exp - Lab/NL | 19.5 | 19.5 | 0 | 100% | 2023-04-02 | 2023-06-23 | 2023-03-27 | 2023-06-23 | 1
|  |  | SPACE-6 | AES-5875 |  |  | 23.2 SMBE Alignment to MBE Projects, DRBs, and Workshops (LOE) | 19.5 | 19.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-7 | AES-5876 |  |  | ROMB |  | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-8 | AES-5877 |  |  | ROMB | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-9 | AES-5878 |  |  | ROMB | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
|  |  | SPACE-10 | AES-5879 |  |  | Ensure Space representation on workshops, DRBs, and Key Decisions in April | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-11 | AES-5880 |  |  | Ensure Space representation on workshops, DRBs, and Key Decisions in May | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-12 | AES-5881 |  |  | Ensure Space representation on workshops, DRBs, and Key Decisions in June | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-13 | AES-5882 |  |  | PI 3 Increment Planning Run Ahead Work Iteration 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-14 | AES-5883 |  |  | PI 3 Increment Planning Run Ahead Work Iteration 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-15 | AES-5884 |  |  | Onboard PO | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-16 | AES-5885 |  |  | PO Training | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-17 | AES-5886 |  |  | Come up with plan for touch point for Space reps across the projects | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
|  |  | SPACE-18 | AES-5887 |  |  | PI Planning outbrief to POs/SMs – focus on impact to SMBE | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-19 | AES-5888 |  |  | Execute first touch point for Space reps across the projects | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-20 | AES-5889 |  |  | Participate in Enterprise E&T Peer Review command media tiger team | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-21 | AES-5890 |  |  | Interview POs | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-22 | AES-5891 |  |  | ROMB | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-23 | AES-5892 |  |  | Establish plan for future touch points for Space reps across the projects | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-24 | AES-5893 |  |  | Answer E&T IOR action: Space E&T director alignment to 1LMX roadmaps | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-25 | AES-5894 |  |  | Agile for Teams training: PO | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-26 | AES-5895 |  |  | SMBE CRB | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-27 | AES-5896 |  |  | Begin implementation of Space 1LMX reps connection plan | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-28 | AES-5897 |  |  | 1LMX Connections Month End May | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-29 |  |  |  | SLMX_MBE_DIGTW | 467.7 | 467.7 | 0 | 100% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232C.0006 | SPACE-30 | AES-5898 | ONELMX_MBE_SSC | MBEDTI23CP | Spc MBE: Impl. DTw Platform and SBV Proto - Cap Lab/NL | 378.2 | 378.2 | 0 | 100% | 2023-04-02 | 2023-06-23 | 2023-04-03 | 2023-06-23 | 1
| 1.3.1.5 |  | SPACE-31 | AES-5899 |  |  | [MBE-DTW] CAP: Automation Framework DTw Thread Integration | 1 | 1 | 0 | 100% |  |  | 2023-04-29 | 2023-06-29 | 2
|  |  | SPACE-32 | AES-5900 |  |  | [MBE-DTW] Automation Framework API Integration to UI | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-33 | AES-5901 |  |  | Automation Framework: AF integration discussion | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
| 1.3.1.5 |  | SPACE-34 | AES-5902 |  |  | [MBE-DTW] Two-way Cameo & Sim Prototype - Horizon SBV (CAP) | 24.5 | 24.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-35 | AES-5903 |  |  | (Horizon SBV) ELK Logstash Configuration | 4 | 4 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-36 | AES-5904 |  |  | Horizon SBV: ELK Connection for Horizon Logs | 4 | 4 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-37 | AES-5905 |  |  | Horizon SBV FLT Demo | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-18 |  |  | 3
|  |  | SPACE-38 | AES-5906 |  |  | Test Scalability of Full-Cycle | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-39 | AES-5907 |  |  | Test Full thread for Horizon SBV | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-40 | AES-5908 |  |  | Test Horizon Logging Updates with ELK | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-41 | AES-5909 |  |  | ELK Analytics with Cameo Requirement Conditions | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-42 | AES-5910 |  |  | Prep for Full thread Test Case Run | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-43 | AES-5911 |  |  | [MBE-DTW] 23.2 FE/BE - MBE UAT & E2E Testing/Bug fixes | 7 | 7 | 0 | 100% |  |  | 2023-04-17 | 2023-05-14 | 2
|  |  | SPACE-44 | AES-5912 |  |  | DEF: Search Provides Results Without Search Term | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-45 | AES-5913 |  |  | DEF: Display Tab Changes Following Expansion or Contraction | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-46 | AES-5914 |  |  | Move UAT Deployment to New Cluster | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-47 | AES-5915 |  |  | Update UAT Project with Additional Resources | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-48 | AES-5916 |  |  | DEF: Data Validation Windows Not Sized for Parent Window | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-49 | AES-5917 |  |  | [MBE-DTW] 23.2 FE/BE - MBE Security | 20 | 20 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-50 | AES-5918 |  |  | Security Checkpoint | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-51 | AES-5919 |  |  | Fix Pytorch Pt2 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-52 | AES-5920 |  |  | Run SCA scan with new Yarn Workspaces | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-53 | AES-5921 |  |  | Go-Back for Upgrading Vulnerabilities Not Approved by Cyber | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-54 | AES-5922 |  |  | Implement SyftBom pipeline step | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-55 | AES-5923 |  |  | Harbor Registry Image creation | 5 | 5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-56 | AES-5924 |  |  | Token to pick up Deadbolt token and pass along to API BE | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-57 | AES-5925 |  |  | Security Placeholder | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
|  |  | SPACE-58 | AES-5926 |  |  | Security Placeholder | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
| 1.3.1.5 |  | SPACE-59 | AES-5927 |  |  | [MBE-DTW] CAP: Two-way Cameo and DT sim connection Prototype | 21 | 21 | 0 | 100% |  |  | 2023-04-02 | 2023-05-28 | 2
|  |  | SPACE-60 | AES-5928 |  |  | Update DIS Adapter Iamge for OpenShift Deploymen | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-61 | AES-5929 |  |  | Wrap up Makefile to Python Conversion | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-62 | AES-5930 |  |  | Makefile for Adapters DevContainer Repo | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-63 | AES-5931 |  |  | Gain Access to Rancher for Sim Provisioner Deployment | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-64 | AES-5932 |  |  | Create eQube Adapter for SBV effort | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-65 | AES-5933 |  |  | Integration Testing SC/Sim P on Rancher | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-66 | AES-5934 |  |  | Implement EntityState Changes in DIS Adapter/Scenario Constructor | 4 | 4 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-67 | AES-5935 |  |  | Create the generic run spec for Sim Provisioner | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
| 1.3.1.5 |  | SPACE-68 | AES-5936 |  |  | [MBE-DTW] CAP: E2E Thread Space Local Cameo Plugin Complete | 3 | 3 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-69 | AES-5937 |  |  | Update dis_broker.py for Nodeport Layout | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-17 |  |  | 3
|  |  | SPACE-70 | AES-5938 |  |  | Correct Adapters dev container to build wheel | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-71 | AES-5939 |  |  | [MBE-DTW] 23.1 Model Update - Top-Level Digital Twin Portfolio Diagrams Baselined (CAP) | 46 | 46 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-72 | AES-5940 |  |  | Update Top-Level Strategic Taxonomy Diagram | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-73 | AES-5941 |  |  | Update Top-Level Strategic Taxonomy Diagram | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-74 | AES-5942 |  |  | Continued Webify Setup | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-75 | AES-5943 |  |  | Webify Process Documentation | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-76 | AES-5944 |  |  | Incorporate Feedback & New Models (As-requested) to Webify | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-77 | AES-5945 |  |  | Update Top-Level Operational Connectivity Diagrams | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-78 | AES-5946 |  |  | Update Top-Level Operational Connectivity Diagrams | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-79 | AES-5947 |  |  | Update Top-Level Operational Connectivity Diagrams | 0.4 | 0.4 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-80 | AES-5948 |  |  | Update Top-Level Diagrams as Required | 0.4 | 0.4 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-81 | AES-5949 |  |  | Update Top-Level Diagrams as Required | 0.4 | 0.4 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-82 | AES-5950 |  |  | Update Top-Level Operational Connectivity Diagrams | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-83 | AES-5951 |  |  | Update Top-Level Conceptual Data Model Diagram | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-84 | AES-5952 |  |  | Update Top-Level Conceptual Data Model Diagram | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-85 | AES-5953 |  |  | Update Top-Level Diagrams As Required | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-86 | AES-5954 |  |  | Update Top-Level Diagrams As Required | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-87 | AES-5955 |  |  | Update Top-Level Diagrams As Required | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-88 | AES-5956 |  |  | Webify Input Updates | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-89 | AES-5957 |  |  | Update Top-Level Physical Data Model Diagram | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-90 | AES-5958 |  |  | Update Top-Level Physical Data Model Diagram | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-91 | AES-5959 |  |  | Continued Webify Setup | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-92 | AES-5960 |  |  | Share Webify with Arch Team for Feedback | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-93 | AES-5961 |  |  | Update Top-Level Personnel Structure Diagram | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-94 | AES-5962 |  |  | Update Top-Level Use-Case Diagram | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-95 | AES-5963 |  |  | Update Top-Level Diagrams as Required | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-96 | AES-5964 |  |  | Update Top-Level Use-Case Diagram | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-97 | AES-5965 |  |  | Update Top-Level Use-Case Diagram | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-98 | AES-5966 |  |  | Update Top-Level Use-Case Diagram | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-99 | AES-5967 |  |  | Update Top-Level Operational Structure Diagram & Personnel Structure | 0.4 | 0.4 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-100 | AES-5968 |  |  | Update Top-Level Operational & Personnel Structure Diagram | 0.4 | 0.4 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-101 | AES-5969 |  |  | Update Top-Level Use-Case Diagram | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-102 | AES-5970 |  |  | Update Top-Level Operational Structure Diagram | 1.5 | 1.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-103 | AES-5971 |  |  | Kickoff Setup for Webify Instance Based on Instructions Available | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-104 | AES-5972 |  |  | Familiarization with Operational Process Diagrams | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-105 | AES-5973 |  |  | Familiarization with Operational Process Diagrams | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-106 | AES-5974 |  |  | Familiarization with Operational Process Diagrams | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-107 | AES-5975 |  |  | Create draft of first two operational process diagrams | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-108 | AES-5976 |  |  | Create draft of first two operational process diagrams | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-109 | AES-5977 |  |  | Create draft of two operational process diagrams | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-110 | AES-5978 |  |  | Review draft operational process diagrams against solution-level diagrams in heritage location | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-111 | AES-5979 |  |  | Operational Processes Activity Diagram Work | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-112 | AES-5980 |  |  | Create top-level operational process diagram draft for primary 2023 SBV use-case | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-113 | AES-5981 |  |  | Create top-level operational process diagram draft for primary 2023 SBV use-case | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-114 | AES-5982 |  |  | Review/updates to top-level operational process diagrams related to SBV | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-115 | AES-5983 |  |  | Review/updates to top-level operational process diagrams related to SBV | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-116 | AES-5984 |  |  | Process Draft for Modularization to Achieve Goals | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-117 | AES-5985 |  |  | Review 23.3 Planning for Modularization Planning | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-118 | AES-5986 |  |  | Placeholder - Luke | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-119 | AES-5987 |  |  | Troubleshooting Support for Webify Gitlab Pipeline | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-120 | AES-5988 |  |  | Operational Processes Activity Diagram Work | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-121 | AES-5989 |  |  | Support vCPE requirements for product test | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-122 | AES-5990 |  |  | Operational Processes Diagram - New Diagrams | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-123 | AES-5991 |  |  | Definition of process for modularization approach (continuation) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-124 | AES-5992 |  |  | [MBE-DTW] 23.1 Model Update - Kickoff Solution-Level Diagrams (CAP) | 22.5 | 22.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-125 | AES-5993 |  |  | Update operational structure for Descriptive Digital Twin | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-126 | AES-5994 |  |  | Define & Request Missing Data Information for Future Descriptive Digital Twin Use-Cases | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-127 | AES-5995 |  |  | Operational Processes Diagram Work - Continued | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-128 | AES-5996 |  |  | Finish aligning strategic taxonomy to 1LMX value streams | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-129 | AES-5997 |  |  | Use-Case Organization Work with Allie for GSFA/NGI Overlap | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-130 | AES-5998 |  |  | Continued Operational Processes Diagram Work | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-131 | AES-5999 |  |  | Review SEMP and Provide Feedback | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-132 | AES-6000 |  |  | Define Missing Data Information for 2023 Descriptive Digital Twin Use-Cases | 1.5 | 1.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-133 | AES-6001 |  |  | Continued Operational Processes Diagram Work | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-134 | AES-6002 |  |  | Incorporate definitions for Strategic Taxonomy (DRAFT) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-135 | AES-6003 |  |  | Request Missing Data Information for 2023 Descriptive Use-Cases from Product Owners | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-136 | AES-6004 |  |  | Group related diagrams in heritage Digital Twin model locations | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-137 | AES-6005 |  |  | SBV Operational Process Diagrams | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-138 | AES-6006 |  |  | Support SBV Operational Process Diagram Definition & Requirements | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-139 | AES-6007 |  |  | Operational Process Diagram Work (New Diagrams) | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-140 | AES-6008 |  |  | Operational Process Diagram Work (New Diagrams) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-141 | AES-6009 |  |  | Begin solution-level diagrams for DTSE | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-142 | AES-6010 |  |  | Begin solution-level diagrams for DTSE | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-143 | AES-6011 |  |  | Update Strategic Taxonomy to Reflect All Capabilities from PowerPoint | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-144 | AES-6012 |  |  | Map relationships between existing DTs diagrams | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-145 | AES-6013 |  |  | SBV Requirements Definition | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-146 | AES-6014 |  |  | [MBE-DTW] 23.1 Model Update - Architecture Alignment Implementation (CAP) | 2 | 2 | 0 | 100% |  |  | 2023-05-01 | 2023-06-22 | 2
|  |  | SPACE-147 | AES-6015 |  |  | Obtain buy-off on top-level DTw diagrams from stakeholders | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-148 | AES-6016 |  |  | Begin implementation of how to show "one DTw product" + deployable configurations | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-149 | AES-6017 |  |  | [MBE-DTW] 23.1 Model Update - Requirements Baseline for Digital Twin Products Documented (CAP) | 11.7 | 11.7 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-150 | AES-6018 |  |  | Setup requirements template in Cameo | 0.3 | 0.3 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-151 | AES-6019 |  |  | Update L1 Requirements Based on Review with Stakeholders | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-152 | AES-6020 |  |  | Update L2 & L3 Requirements Based on Review with Stakeholders | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-153 | AES-6021 |  |  | Finalize & Socialize Requirements Structure Defined | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-154 | AES-6022 |  |  | Review L0 Requirements with Stakeholders | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-155 | AES-6023 |  |  | Update L0 Requirements Based on Review with Stakeholders | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-156 | AES-6024 |  |  | Review L1 Requirements with Stakeholders | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-157 | AES-6025 |  |  | Requirements update work | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-158 | AES-6026 |  |  | Build specification tree in Cameo to visualize requirements breakout | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-159 | AES-6027 |  |  | Compile and Review L2 Requirements | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-160 | AES-6028 |  |  | Review requirements for the purpose of informing future flows/diagrams | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-161 | AES-6029 |  |  | Requirements Update Work | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-162 | AES-6030 |  |  | Review requirements for the purpose of informing future flows/diagrams | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-163 | AES-6031 |  |  | Support requirements discussion for cost insights capability | 0.4 | 0.4 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-164 | AES-6032 |  |  | Work L2 Requirements with Teams | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-165 | AES-6033 |  |  | Apply L2/L3 Structure to Requirements | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-166 | AES-6034 |  |  | [MBE-DTW] 23.2 vCPE: DevSecOps Enhancements | 21 | 21 | 0 | 100% |  |  | 2023-04-04 | 2023-06-30 | 2
|  |  | SPACE-167 | AES-6035 |  |  | vCPE - ArgoCD Hackathon | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-168 | AES-6036 |  |  | vCPE - Release Process Hackathon | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-169 | AES-6037 |  |  | vCPE - Create PRD deployments | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-170 | AES-6038 |  |  | Siftaur - ArgoCD Pilot to DEV deployment | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-171 | AES-6039 |  |  | Siftaur - CICD logical flow update with release gate to uat/prd branches | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-172 | AES-6040 |  |  | Siftaur - ArgoCD UAT/PRD deployments | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-173 | AES-6041 |  |  | Siftaur - Vault Secret Management with Gitlab CI POC | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-174 | AES-6042 |  |  | Siftaur - Compare Results of Syft to Current SBOM scan | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-175 | AES-6043 |  |  | DT Diagnostics - Grafana Dashboard | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-06-08 |  |  | 3
|  |  | SPACE-176 | AES-6044 |  |  | DT Diagnostics - Create Simulated Mach-5 Data Set | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-177 | AES-6045 |  |  | DT Diagnositcs - Draft Release Process | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-178 | AES-6046 |  |  | DT Diagnositcs - Release Process Specific Information Gather | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-179 | AES-6047 |  |  | [MBE-DTW] Tested Factory/Apex Integrated Product | 10 | 10 | 0 | 100% | 2023-04-30 | 2023-07-18 | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-180 | AES-6048 |  |  | Test Case Coordination | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-181 | AES-6049 |  |  | Test Case Coordination Placeholder | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-182 | AES-6050 |  |  | CoreDev: APEX - Color missile array based on a selected legend component | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-183 | AES-6051 |  |  | CoreDev: APEX - Missile sections | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-184 | AES-6052 |  |  | [DTw:UI] - Dependency Updates, Code Cleanup, Documentation | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-13 |  |  | 3
|  |  | SPACE-185 | AES-6053 |  |  | [MBE-DTW] Single TIBCO Project for DTw Platform | 0 | 0 | 0 | 0% | 2023-04-16 | 2023-06-12 | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-186 | AES-6054 |  |  | [MBE-DTW] Implement Metrics & Monitoring of Services | 5 | 5 | 0 | 100% | 2023-04-16 | 2023-06-12 | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-187 | AES-6055 |  |  | Research Prometheus Cluster Monitoring on Openshift | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-188 | AES-6056 |  |  | CoreDev:Services - Research TSM and database backup service | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-189 | AES-6057 |  |  | CoreDev:Service - Splunk power user training | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-190 | AES-6058 |  |  | CoreDev:Service - Set up Splunk dashboard for CoreDev apps | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-191 | AES-6059 |  |  | [MBE-DTW] Platform Security Vulnerability Mitigation & Cyber Compliance Advancement | 15 | 15 | 0 | 100% | 2023-04-16 | 2023-07-18 | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-192 | AES-6060 |  |  | Cyber security checklist discussion | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-193 | AES-6061 |  |  | Develop branch look into aqua scans | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-194 | AES-6062 |  |  | vCPE branch look into aqua scans | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-195 | AES-6063 |  |  | Cyber security checklist discussion 2 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-196 | AES-6064 |  |  | Cyber Coordination for DTw Platform | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-197 | AES-6065 |  |  | Cyber Coordination for DTw Platform | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-198 | AES-6066 |  |  | Updates to ITP/CyRIS Entries for Space Digital Twin | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-199 | AES-6067 |  |  | CoreDev:Service - Update ITP/SCF/CyRIS records | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-22 |  |  | 3
|  |  | SPACE-200 | AES-6068 |  |  | CoreDev:Services - Add syft scan to DTw UI | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
|  |  | SPACE-201 | AES-6069 |  |  | CoreDev:Services - Add syft scan to CTA | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-202 | AES-6070 |  |  | Review security documentation | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-203 | AES-6071 |  |  | [MBE-DTW] Bug Reporting Issue Collector Implementation | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-06-12 | 2023-05-01 | 2023-06-22 | 2
|  |  | SPACE-204 | AES-6072 |  |  | Software defect report discussion | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-205 | AES-6073 |  |  | [MBE-DTW] Two-way Cameo & Sim Prototype - LM400 SBV (CAP) | 28 | 28 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-206 | AES-6074 |  |  | LM400 SBV: LM400 Telemetry in ELK Familiarization | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-207 | AES-6075 |  |  | LM400 SBV: Familiarization with ELK | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-208 | AES-6076 |  |  | (LM400 SBV) LM400 Telemetry in ELK & Cameo Import | 4 | 4 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-209 | AES-6077 |  |  | Develop Cameo Import & Verification scripts for LM400 | 4 | 4 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-210 | AES-6078 |  |  | Test Import & Requirements Verification Scripts with ELK Data | 5 | 5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-211 | AES-6079 |  |  | Test Verification with live data from LM400 | 4 | 4 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-212 | AES-6080 |  |  | Test Cameo Scripts with data from LM400 | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-213 | AES-6081 |  |  | (LM400 SBV) Define Logging Interface for Telemetry | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-21 |  |  | 3
|  |  | SPACE-214 | AES-6082 |  |  | Test LM400 GovCloud Deployment with Scenario Builder | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-215 | AES-6083 |  |  | Test LM400 GovCloud Deployment - Pt. 2 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-216 | AES-6084 |  |  | Test LM400 GovCloud Deployment with Scenario Builder | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-15 |  |  | 3
|  |  | SPACE-217 | AES-6085 |  |  | 23.2 SECATS Support for DTw Platform and SBV Proto - CAP | 41 | 41 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-218 | AES-6086 |  |  | Cyber: DTv - Vulnerability Remediation Support | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-12 |  |  | 3
|  |  | SPACE-219 | AES-6087 |  |  | Cyber: DTw Validate Encryption in Transit & At Rest | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-220 | AES-6088 |  |  | Cyber: DTw DTw Logging and Monitoring | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-221 | AES-6089 |  |  | Cyber: vCPE - Inquire & Validate Openshift Project access | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-05 |  |  | 3
|  |  | SPACE-222 | AES-6090 |  |  | Cyber: DTw - Inquire & Validate Openshift Project access | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-223 | AES-6091 |  |  | Cyber: vCPE - Base Image Validation & Approval | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-17 |  |  | 3
|  |  | SPACE-224 | AES-6092 |  |  | Cyber: DTw - Base Image Validation & Approval | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-17 |  |  | 3
|  |  | SPACE-225 | AES-6093 |  |  | Cyber: vCPE- Vulnerability Mitigation Support | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-226 | AES-6094 |  |  | Test: Introduction to Pedigree | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-227 | AES-6095 |  |  | Test: Introduction to vCPE - 1 | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-228 | AES-6096 |  |  | Test: Pedigree Exploratory Testing | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-24 |  |  | 3
|  |  | SPACE-229 | AES-6097 |  |  | Test: vCPE Exploratory Testing - 2 | 3 | 3 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-230 | AES-6098 |  |  | Test; Establish Testing Platform for LM300 data | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-231 | AES-6099 |  |  | Test: Develop Test Case for the vCPE Models Tab | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-232 | AES-6100 |  |  | Test: Playwright/Zephyr Connector Development | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-24 |  |  | 3
|  |  | SPACE-233 | AES-6101 |  |  | Test: vCPE Test Case Development - 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-234 | AES-6102 |  |  | Test: Determine Workaround to Recording Issue - 1 | 3 | 3 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-235 | AES-6103 |  |  | Test: Determine Workaround to Recording Issue - 1 | 3 | 3 | 0 | 100% | 2023-04-03 | 2023-04-12 |  |  | 3
|  |  | SPACE-236 | AES-6104 |  |  | Test: Develop vCPE Performance Test Scripts - 2 | 3 | 3 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-237 | AES-6105 |  |  | Test: Develop vCPE Performance Test Scripts - 2 | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-238 | AES-6106 |  |  | Test: Mature vCPE Performance Test Scripts - 3 | 3 | 3 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-239 | AES-6107 |  |  | Test: Develop vCPE Performance Test Scripts - 3 | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-240 | AES-6108 |  |  | Cyber: DTv - Cyber Checklist Preview | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-12 |  |  | 3
|  |  | SPACE-241 | AES-6109 |  |  | Cyber: DTw - MVSP Documentation | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-242 | AES-6110 |  |  | Cyber: DTv - MVSP Documentation | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-12 |  |  | 3
|  |  | SPACE-243 | AES-6111 |  |  | Test: Introduction to Pedigree | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-244 | AES-6112 |  |  | Test: Introduction to vCPE - 1 | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-245 | AES-6113 |  |  | Test: Pedigree Exploratory Testing | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-24 |  |  | 3
|  |  | SPACE-246 | AES-6114 |  |  | Test: vCPE Exploratory Testing - 2 | 3 | 3 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-247 | AES-6115 |  |  | Test: Develop Test Case for the vCPE Data Tab | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-18 |  |  | 3
|  |  | SPACE-248 | AES-6116 |  |  | Test: Explore Automated Test Tools for vCPE Testing | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-249 | AES-6117 |  |  | Test: Simple Automated Test Demonstration | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-250 | AES-6118 |  |  | Cyber: DTw - Vulnerability Scan Analysis | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-17 |  |  | 3
|  |  | SPACE-251 | AES-6119 |  |  | [MBE-DTW] DTv: Cyber Production Readiness | 9 | 9 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-252 | AES-6120 |  |  | Finish Cyris Assessment | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-253 | AES-6121 |  |  | Finish ITP for DTv | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-254 | AES-6122 |  |  | Deploy tools to Auto Generate SBOMs and Perform Security Scans to DTv Repo | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-255 | AES-6123 |  |  | Get Cyber Security up to Speed With DTv Architecture | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-256 | AES-6124 |  |  | Deploy Fortify Locally to Scan C# Files | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-16 |  |  | 3
|  |  | SPACE-257 | AES-6125 |  |  | Deploy Fortify to beefy CHIL machine to Scan C# Files | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-258 | AES-6126 |  |  | Generate AD Group and Connection Documentation | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-259 | AES-6127 |  |  | Support Cyber Appstream Approval | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-260 | AES-6128 |  |  | [MBE-DTW] Research CI/CD ArgoCD Deployment | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-06-12 |  |  | 2
|  |  | SPACE-261 | AES-6129 |  |  | Research ArgoCD | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-262 | AES-6130 |  |  | Sim Provisioner Development for TBS | 57 | 57 | 0 | 100% |  |  | 2023-04-03 | 2023-06-24 | 2
|  |  | SPACE-263 | AES-6131 |  |  | add ability to release and rollback specific version of SimProvisioner | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-264 | AES-6132 |  |  | Support of Asset Types - K8sManifest - ultimate override for worst case scenario | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-265 | AES-6133 |  |  | Create asset for Eqube | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-266 | AES-6134 |  |  | Proof: FVT Sidecar componet | 4 | 4 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-267 | AES-6135 |  |  | UML diagram for SimProvisioner composable components | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-268 | AES-6136 |  |  | Chain components - Components of a deployments are made of other components | 4 | 4 | 0 | 100% | 2023-04-02 | 2023-05-11 |  |  | 3
|  |  | SPACE-269 | AES-6137 |  |  | Support of Asset Types - ConfigurationFile | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-270 | AES-6138 |  |  | Support of Asset Types - RunEnvironmentVar - Allow a sim to be configured with environment variables | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-271 | AES-6139 |  |  | Follow Up: FVT Container hackathon changes | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-272 | AES-6140 |  |  | Update unittests to ensure the behavior of SimProvisioner core | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-273 | AES-6141 |  |  | Correct the GNC innit config maps, add Time element | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-274 | AES-6142 |  |  | Add FVT Asset | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-275 | AES-6143 |  |  | Deploy V0 of SimProvisioner to 21cwf for TbS testing | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-276 | AES-6144 |  |  | update make.py to reflect 'make release' and 'make rollback' | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-277 | AES-6145 |  |  | Allow user to SimProvisioner to upload assets and apply to TbsProgramComponent | 4 | 4 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-278 | AES-6146 |  |  | refactor helm out of workflow in favor of kustomize | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-279 | AES-6147 |  |  | Move SimProvisioner to tbs/external gitlab repo | 4 | 4 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-280 | AES-6148 |  |  | Authorize routes in simprovisioner with token | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-281 | AES-6149 |  |  | Make InitContainer a "component" in runspec | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-282 | AES-6150 |  |  | Pull together SBV External Data Source's | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-283 | AES-6151 |  |  | SimProvisioner requirement discussion with TbS Stakeholders | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-284 | AES-6152 |  |  | research spike: Why TCP traffic does not flow into 21cwf | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-285 | AES-6153 |  |  | Development: Commanding SV Via Horizon Scripting | 8 | 8 | 0 | 100% |  |  | 2023-04-03 | 2023-06-24 | 2
|  |  | SPACE-286 | AES-6154 |  |  | Spike: Become familiar with Horizon | 8 | 8 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-287 | AES-6155 |  |  | Sim Provisioner: Horizon connection with Deployed Sim Q2 | 4 | 4 | 0 | 100% |  |  | 2023-05-08 | 2023-06-25 | 2
|  |  | SPACE-288 | AES-6156 |  |  | Verify the Lm400 Horizon DockerCompose works as intended | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-289 | AES-6157 |  |  | Research Spike: Groundhog | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-290 | AES-6158 |  |  | Distributed Sim Log Aggregation | 17.5 | 17.5 | 0 | 100% |  |  | 2023-05-15 | 2023-06-25 | 2
|  |  | SPACE-291 | AES-6159 |  |  | Talk with horizon about how to send data to their elasticsearch instance | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-292 | AES-6160 |  |  | Attach fluent bit to horizon elasticsearch | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-293 | AES-6161 |  |  | SPIKE: Read existing MRs to learn about fluent bit | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-294 | AES-6162 |  |  | Tag up to discuss the feature | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-16 |  |  | 3
|  |  | SPACE-295 | AES-6163 |  |  | create minimal example | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-296 | AES-6164 |  |  | Modify fluent bit to send to elastisearch | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-297 | AES-6165 |  |  | Research FluentBit for a way to tag logs from different files | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.232E.0009 | SPACE-298 | AES-6166 | ONELMX_MBE_SSC | MBEDTI23 | Spc MBE: Req. and Release DTw Platform and SBV Proto - Exp Lab/NL | 89.5 | 89.5 | 0 | 100% | 2023-04-02 | 2023-06-23 | 2023-04-03 | 2023-06-23 | 1
| 1.3.1.5 |  | SPACE-299 | AES-6167 |  |  | [MBE-DTW] E2E Thread Space Local Cameo Plugin - Automate LM400 DTw Start-Up (EXP) | 2 | 2 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-300 | AES-6168 |  |  | (Spike) SBV: DTS Start-Up Process Familiarization | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-301 | AES-6169 |  |  | LM400 SBV (Spike): Define Example for Satellite Start-Up and Logging | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-302 | AES-6170 |  |  | Message Broker for Cameo | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-303 | AES-6171 |  |  | Determine Automation Opportunities for LM400 Start-up | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-304 | AES-6172 |  |  | Test Start-up Process | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-305 | AES-6173 |  |  | LM400 SBV Requirements Allocation | 0 | 0 | 0 | 0% |  |  |  |  | 3
| 1.3.1.5 |  | SPACE-306 | AES-6174 |  |  | [MBE-DTW] EXP: DTw Platform Baseline 23.2 "Lab/NL" | 0 | 0 | 0 | 0% |  |  | 2023-05-15 | 2023-06-22 | 2
| 1.3.1.5 |  | SPACE-307 | AES-6175 |  |  | [MBE-DTW] Two-way Cameo & Sim Prototype - DTw Tools Integration Design (EXP) | 3.5 | 3.5 | 0 | 100% |  |  | 2023-05-15 | 2023-06-22 | 2
|  |  | SPACE-308 | AES-6176 |  |  | Investigate Interface from Cameo to ELK | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-309 | AES-6177 |  |  | Investigate Integration of SBV Data with DTw Tools | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
| 1.3.1.5 |  | SPACE-310 | AES-6178 |  |  | [MBE-DTW] EXP: Baseline Defined for Quality Artifact Thread Integration | 4.5 | 4.5 | 0 | 100% |  |  | 2023-03-30 | 2023-06-15 | 2
|  |  | SPACE-311 | AES-6179 |  |  | Make cocktail napkin mockup for Quality Artifacts page in Insights | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-05-01 |  |  | 3
|  |  | SPACE-312 | AES-6180 |  |  | Define requirements for Quality use-cases in Digital Twin from SIA | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-313 | AES-6181 |  |  | Update Overall EIDP data schema model after SIA event | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-314 | AES-6182 |  |  | Create consolidated process flows - Qnotes/Inspections - Part1 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-315 | AES-6183 |  |  | Execute virtual fDT Quality SIA and burndown Get-to-Excellence plan | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-316 | AES-6184 |  |  | Identify CDRL that covers Qnotes | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-317 | AES-6185 |  |  | [MBE-DTW] 23.2 FE - MBE Overhead Training | 2 | 2 | 0 | 100% |  |  | 2023-05-01 | 2023-06-11 | 2
|  |  | SPACE-318 | AES-6186 |  |  | Check in Meeting with MBE training Team | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-03 |  |  | 3
|  |  | SPACE-319 | AES-6187 |  |  | Check in Meeting with MBE training Team | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
| 1.3.1.5 |  | SPACE-320 | AES-6188 |  |  | [MBE-DTW] EXP: E2E Thread Space Local Cameo Plugin Complete | 4 | 4 | 0 | 100% |  |  | 2023-04-07 | 2023-06-17 | 2
|  |  | SPACE-321 | AES-6189 |  |  | Research: Meet w/ SynEnv to Discuss Deployment Strategies for Horizon and ELK | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-322 | AES-6190 |  |  | Research Spike: Learning SBV DTS Goals | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-323 | AES-6191 |  |  | [MBE-DTW] 23.1 Model Update - Architecture Alignment Planning (EXP) | 43 | 43 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-324 | AES-6192 |  |  | Review top-level models with Space EA | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-325 | AES-6193 |  |  | Identify DTw diagrams to push to Space EA Top-Level | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-326 | AES-6194 |  |  | Brainstorm approach to capture stakeholder needs | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-327 | AES-6195 |  |  | Determine how to best capture HW/SW lists for DTw | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-02 |  |  | 3
|  |  | SPACE-328 | AES-6196 |  |  | Create examples for Operational Processes Diagrams | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-329 | AES-6197 |  |  | UI/UX Alignment Planning Follow-on | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-330 | AES-6198 |  |  | Architecture Discussions Re: Woodchuck/CTA Integration | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-331 | AES-6199 |  |  | Provide MBE SCEE existing TIBCO connector information (GIVER) | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-332 | AES-6200 |  |  | MBE Architecture Alignment | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-333 | AES-6201 |  |  | Meetings with Team to Plan/Review Architecture Diagrams | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-05 |  |  | 3
|  |  | SPACE-334 | AES-6202 |  |  | MBE Architecture Alignment | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-335 | AES-6203 |  |  | MBE Architecture Alignment | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-336 | AES-6204 |  |  | Pick a pilot case for modularization of the code with Luke | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-337 | AES-6205 |  |  | MBE Architecture Alignment | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-338 | AES-6206 |  |  | MBE Architecture Alignment | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-339 | AES-6207 |  |  | MBE Architecture Alignment | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-340 | AES-6208 |  |  | Meetings with Team to Plan/Review Architecture Diagrams | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-341 | AES-6209 |  |  | Meetings with Team to Plan/Review Architecture Diagrams | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-342 | AES-6210 |  |  | Meetings with Team to Plan/Review Architecture Diagrams | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-343 | AES-6211 |  |  | Meetings with Team to Plan/Review Architecture Diagrams | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-344 | AES-6212 |  |  | Meetings with Team to Plan/Review Architecture Diagrams | 1.5 | 1.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-345 | AES-6213 |  |  | Vision Planning to Aid Q3 Planning | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-346 | AES-6214 |  |  | Placeholder - Salena | 1 | 1 | 0 | 100% |  |  |  |  | 3
|  |  | SPACE-347 | AES-6215 |  |  | MBE Roadmap Update Meetings for Q3 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-348 | AES-6216 |  |  | Support Arch Discussions re: Woodchuck & CTA Integration | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-349 | AES-6217 |  |  | Early Planning for Q3 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-350 | AES-6218 |  |  | Q3 Planning Runahead (DTw & SMBE) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-351 | AES-6219 |  |  | Planning for Q3 | 2.5 | 2.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-352 | AES-6220 |  |  | Architecture Model Review | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-353 | AES-6221 |  |  | Architecture Model Review | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-354 | AES-6222 |  |  | Architecture Model Review | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-355 | AES-6223 |  |  | Architecture Model Review | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-356 | AES-6224 |  |  | Operational Processes Vision & Example Work | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-357 | AES-6225 |  |  | Architecture Model Review | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-358 | AES-6226 |  |  | Create a mapping of when governance applies | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-359 | AES-6227 |  |  | Determine how we transition current products to future state capabilities within model | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-360 | AES-6228 |  |  | Jira Planning and Roadmap Work | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-361 | AES-6229 |  |  | Plan modularization approach with Luke | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-362 | AES-6230 |  |  | Plan modularization approach with Salena | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-363 | AES-6231 |  |  | Pick a pilot case for modularization of the code with Salena | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-364 | AES-6232 |  |  | Familiarization and onboarding with Luke | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-365 | AES-6233 |  |  | Familiarization and onboarding with Salena | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-366 | AES-6234 |  |  | Determine requirements structure for L2/L3 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-367 | AES-6235 |  |  | Brainstorm: How do we show the single DTw product and all modules/deployable configurations in the model? | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-368 | AES-6236 |  |  | Determine requirements structure for L2/L3 with Salena | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-369 | AES-6237 |  |  | Pick a pilot case for modularization of the code with Luke (Continued) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-370 | AES-6238 |  |  | Data Architect Onboarding & Planning | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-371 | AES-6239 |  |  | Modularization of Code Pilot Case - Continuation | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-372 | AES-6240 |  |  | [MBE-DTW] 23.1 Model Update - Systems Engineering Process & Documentation Updates (EXP) | 15.5 | 15.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-373 | AES-6241 |  |  | Cleanup Architecture Pages on Confluence | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-374 | AES-6242 |  |  | Identify Approach for Webify Instance | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-375 | AES-6243 |  |  | Refine process for Cyber Security Engagement on Digital Twin | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-376 | AES-6244 |  |  | Draft "New Integration" Process | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-377 | AES-6245 |  |  | Provide feedback re: Webify tool and use | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-378 | AES-6246 |  |  | Creation of Guidelines for Digital Twin API Standardization | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-379 | AES-6247 |  |  | Socialization of Guidelines for Digital Twin API Standardization | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-380 | AES-6248 |  |  | Review / Compile Governance References | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-381 | AES-6249 |  |  | SEMP Review & Feedback | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-382 | AES-6250 |  |  | Kickoff Creation of Guidelines for Digital Twin API Standardization | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-03 |  |  | 3
|  |  | SPACE-383 | AES-6251 |  |  | Prelim. Use-Case Prioritization Approach | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-384 | AES-6252 |  |  | Create draft process for systems engineering-driven DTw development | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-385 | AES-6253 |  |  | Review & group additional use-cases (NGI, GSFA, etc.) | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-386 | AES-6254 |  |  | Provide feedback/updates for Space Digital Twin tailored SEMP | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-387 | AES-6255 |  |  | Use-Case Prioritization Approach | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-388 | AES-6256 |  |  | Provide feedback to tailored Space Digital Twin SEMP | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-389 | AES-6257 |  |  | Data Architecture Onboarding | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-390 | AES-6258 |  |  | [MBE-DTW] Unified UI/UX Planning (EXP) | 1.5 | 1.5 | 0 | 100% | 2023-04-02 |  | 2023-04-03 | 2023-05-25 | 2
|  |  | SPACE-391 | AES-6259 |  |  | Napkin mockup - Insights platform total revamp of entire framework | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-05-01 |  |  | 3
|  |  | SPACE-392 | AES-6260 |  |  | Execute UI/UX Summit | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-393 | AES-6261 |  |  | Research: Inject Initialization Command product into LM400 Q2 | 3 | 3 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-394 | AES-6262 |  |  | Research Spike: Sync Sim to Spacecraft Time | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-395 | AES-6263 |  |  | Research: Sim Provisioner Development for TBS | 10.5 | 10.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-396 | AES-6264 |  |  | Research Spike: how to connect and use with TBS Spooler | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-397 | AES-6265 |  |  | Sim Provisisoner Knowledge Share | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-398 | AES-6266 |  |  | Get up to speed on Sim Provisioner - Kjel | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-399 | AES-6267 |  |  | Get up to speed on Sim Provisioner - Austin | 5 | 5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-400 |  |  |  | SLMX_MBE_DSARC | 346.5 | 329.5 | 17 | 95.09% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232E.0003 | SPACE-401 | AES-6268 | ONELMX_MBE_SSC | MBECCA23 | Spc MBE: Architecture Rqmt, Modeling and Evaluation - Exp Lab/NL | 216.5 | 216.5 | 0 | 100% | 2023-04-02 | 2023-06-26 | 2023-04-03 | 2023-06-23 | 1
| 1.3.1.5 |  | SPACE-402 | AES-6269 |  |  | EXP: Continue to work on PLM Integration Architecture | 48.5 | 48.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-403 | AES-6270 |  |  | Identify opportunities for PLM interface capabilities pt1 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-404 | AES-6271 |  |  | Research how Intelligent Assembly works with Integration Layer | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-405 | AES-6272 |  |  | Create Resource Internal Connectivity Diagram for Intelligent Assembly | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-406 | AES-6273 |  |  | Create resource internal connectivity diagram for Creo Toolkit in UAF | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-407 | AES-6274 |  |  | Create resource structure diagram for Creo Toolkit in UAF | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-408 | AES-6275 |  |  | Create resource process diagram for Creo Toolkit in UAF | 5 | 5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-409 | AES-6276 |  |  | Gather information for Zuken E3 use cases | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-410 | AES-6277 |  |  | Create Zuken E3 use cases | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-411 | AES-6278 |  |  | Create Zuken E3 requirements in UAF | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-412 | AES-6279 |  |  | Gather information for Zuken E3 use cases Pt 2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-413 | AES-6280 |  |  | Create Resource Structure diagram for Intelligent Assembly | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-414 | AES-6281 |  |  | Create Operational Use Case Diagram for Zuken Integration | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-415 | AES-6282 |  |  | Create Resource Process Diagram for Intelligent Assembly | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-416 | AES-6283 |  |  | Identify opportunities for PLM interface capabilities pt2 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
|  |  | SPACE-417 | AES-6284 |  |  | Identify opportunities for PLM interface capabilities pt3 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-418 | AES-6285 |  |  | Run the Zuken E3 Forum to gather use cases and further requirements pt1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-19 |  |  | 3
|  |  | SPACE-419 | AES-6286 |  |  | Run the Zuken E3 Forum to gather use cases and further requirements pt2 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-420 | AES-6287 |  |  | Run the Zuken E3 Forum to gather use cases and further requirements pt3 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-421 | AES-6288 |  |  | Run the Creo Toolkit Forum to gather use cases and further requirements pt3 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-422 | AES-6289 |  |  | Run the Creo Toolkit Forum to gather use cases and further requirements pt2 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-423 | AES-6290 |  |  | Run the Creo Toolkit Forum to gather use cases and further requirements pt1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-19 |  |  | 3
|  |  | SPACE-424 | AES-6291 |  |  | Review and update LM Scripts Resource Structure (RS-TX) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-425 | AES-6292 |  |  | Creo Toolkit Review | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-426 | AES-6293 |  |  | Finalize Zuken E3 use cases and requirements | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
| 1.3.1.5 |  | SPACE-427 | AES-6294 |  |  | EXP: Define Space implications of Part Registry | 3 | 3 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-428 | AES-6295 |  |  | Month End Summary | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-429 | AES-6296 |  |  | Month End Summary | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-06-08 |  |  | 3
|  |  | SPACE-430 | AES-6297 |  |  | Month End Summary | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
| 1.3.1.5 |  | SPACE-431 | AES-6298 |  |  | EXP: Gather PLM Architecture Modelling Requirements | 17 | 17 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-432 | AES-6299 |  |  | Operational / Functional Objectives of PLM - Part 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-433 | AES-6300 |  |  | Review All information | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-434 | AES-6301 |  |  | Research Information Exchanges Necessary for PLM Implementation - Part 1 | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-435 | AES-6302 |  |  | Identify and Create PLM Top Level Operational Objectives | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-436 | AES-6303 |  |  | Define High Level Use Cases for PLM | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-437 | AES-6304 |  |  | Define PLM Stakeholders | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-438 | AES-6305 |  |  | Operational / Functional Objectives of PLM - Part 2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
| 1.3.1.5 |  | SPACE-439 | AES-6306 |  |  | EXP: Complete the current state of Space Interface | 8.5 | 8.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-440 | AES-6307 |  |  | Apply Rapid-Need standard to current state Pt1 | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-441 | AES-6308 |  |  | Cameo Familiarization | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-442 | AES-6309 |  |  | Get Cameo Access | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-443 | AES-6310 |  |  | Document Integration Layer Services | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-444 | AES-6311 |  |  | Integration Layer Deep-Dive Session - Part 3 | 0 | 0 | 0 | 0% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-445 | AES-6312 |  |  | Insight Platform Deep-Dive Session | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-446 | AES-6313 |  |  | Conduct PDR Interviews - Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-447 | AES-6314 |  |  | Conduct PDR Interviews - Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-448 | AES-6315 |  |  | Evaluate TSM Capability Demonstration with DTS/DTV Pt 1 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
| 1.3.1.5 |  | SPACE-449 | AES-6316 |  |  | EXP: Build a draft version of Space PLM Roadmap | 14.5 | 14.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-450 | AES-6317 |  |  | Design Roadmap Confluence Page | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-451 | AES-6318 |  |  | Document EO 1LMX PLM Strategy Decisions S1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-452 | AES-6319 |  |  | Document Ongoing Space PLM Activities S3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-453 | AES-6320 |  |  | Document Planned Space PLM Activities and timeline | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-454 | AES-6321 |  |  | Document External Dependencies pt1 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-455 | AES-6322 |  |  | Document EO 1LMX PLM Strategy Decisions S2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-456 | AES-6323 |  |  | Document EO 1LMX PLM Strategy Decisions S3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-457 | AES-6324 |  |  | Document EO 1LMX PLM Strategy Decisions S4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-458 | AES-6325 |  |  | Document EO 1LMX PLM Strategy Decisions S5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-459 | AES-6326 |  |  | Conduct Monthly Roadmap Review - April | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-460 | AES-6327 |  |  | Conduct Monthly Roadmap Review - May | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-461 | AES-6328 |  |  | Conduct Monthly Roadmap Review - June | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-462 | AES-6329 |  |  | Document Ongoing Space PLM Activities S5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-463 | AES-6330 |  |  | Document External Dependencies pt2 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-464 | AES-6331 |  |  | Disposition Initiatives Identified in Assessment | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
| 1.3.1.5 |  | SPACE-465 | AES-6332 |  |  | EXP: Continue MBE High Level Architecture – build a bridge between UAF and MBE-A legacy models | 40.5 | 40.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-466 | AES-6333 |  |  | Research the data elements required for Resources Information for SMBE | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-26 |  |  | 3
|  |  | SPACE-467 | AES-6334 |  |  | Define initial set of data elements needed for Resources Information for SMBE | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-468 | AES-6335 |  |  | UAF: (IAT) Resource Structure Diagrams | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-469 | AES-6336 |  |  | MBE Resource Structure Alignment [Place Holder] | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-470 | AES-6337 |  |  | UAF: (TSM) Resource Structure Diagrams | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-471 | AES-6338 |  |  | MBE High Level - SMBE Integration Layer | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-472 | AES-6339 |  |  | MBE High Level - PLM Environment | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
|  |  | SPACE-473 | AES-6340 |  |  | MBE Resource Structure Alignment - Engineering Efficiency support - ZukenE3 and Harness Builder | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-474 | AES-6341 |  |  | MBE Modeling approach for the physical architecture for UAF and SysML | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-475 | AES-6342 |  |  | Work with Sena and Marlena (or delegate) for MBE-A Legacy Model Knowledge Transfer | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-476 | AES-6343 |  |  | UAF: (TSM) Resource Internal Connectivity Diagram | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-477 | AES-6344 |  |  | Align SMBE Resource Data Elements with 1LMX data updates | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
|  |  | SPACE-478 | AES-6345 |  |  | UAF: (IAT) Resources Internal Connectivity Diagram | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-479 | AES-6346 |  |  | UAF: (TSM) Research TSM | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-480 | AES-6347 |  |  | UAF: (TSM) Integration Layer | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-481 | AES-6348 |  |  | UAF: (IAT) Research | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-482 | AES-6349 |  |  | UAF: (IAT) Data Resource Information Elements | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-483 | AES-6350 |  |  | Engage with Corey for Legacy Model Data Elements | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-484 | AES-6351 |  |  | Cyber: GFSA - UAF Modeling support | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-14 |  |  | 3
|  |  | SPACE-485 | AES-6352 |  |  | UAF: Define and document the standards of Use Cases in UAF | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-15 |  |  | 3
|  |  | SPACE-486 | AES-6353 |  |  | Work with Sena and Marlena (or delegate) for MBE-A Legacy Model Knowledge Transfer pt2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-17 |  |  | 3
|  |  | SPACE-487 | AES-6354 |  |  | UAF: (TSM) Resource Internal Connectivity Diagram - Round 2 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-488 | AES-6355 |  |  | MBE Resource Structure Alignment for Creo/IA Context | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-489 | AES-6356 |  |  | Review UAF/TSM Resource Internal Connectivity Diagram | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-490 | AES-6357 |  |  | Review Resource Structure Approach with 1LMX | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
| 1.3.1.5 |  | SPACE-491 | AES-6358 |  |  | EXP: Evaluate ThingWorx Navigate | 4 | 4 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-492 | AES-6359 |  |  | Need ThingWorx Access | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-493 | AES-6360 |  |  | Document ThingWorx Navigation View Evaluation Plan | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-494 | AES-6361 |  |  | ThingWorx Evaluation Placeholder | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-495 | AES-6362 |  |  | Understand ThingWorx License Cost | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-496 | AES-6363 |  |  | Create MBE Physical Architecture Diagram - focus on Simulation, Test and Verification | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
| 1.3.1.5 |  | SPACE-497 | AES-6364 |  |  | EXP: MPMLink | 3 | 3 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-498 | AES-6365 |  |  | DSARC-Conduct IT Task Review and Assignments | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
| 1.3.1.5 |  | SPACE-499 | AES-6366 |  |  | EXP: Document Space Master Data for EPDM and PMPDB | 14 | 14 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-500 | AES-6367 |  |  | Kickoff EPDM and PMP Master Data Scope | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-501 | AES-6368 |  |  | EPDM and PMP Master Data Inputs | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-502 | AES-6369 |  |  | EPDM and PMP Master Data Inputs | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-503 | AES-6370 |  |  | EPDM and PMP Master Data Inputs | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-504 | AES-6371 |  |  | EPDM and PMP Master Data Inputs | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-505 | AES-6372 |  |  | EPDM and PMP Master Data Inputs | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-506 | AES-6373 |  |  | Collab with Master Data Management team | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
| 1.3.1.5 |  | SPACE-507 | AES-6374 |  |  | EXP: Define the MBE architecture documentation standards | 7.5 | 7.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-508 | AES-6375 |  |  | Create problem definition to describe this enabler | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-509 | AES-6376 |  |  | Working meeting to discuss solutions to the "Rapid-need" Systems engineering architecture capture artifacts.. | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-510 | AES-6377 |  |  | Produce Standards for documenting "Rapid-need" SE Arch artifacts | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-511 | AES-6378 |  |  | Work with Cyber on IAT models | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-11 |  |  | 3
| 1.3.1.5 |  | SPACE-512 | AES-6379 |  |  | EXP: Support EIS Design Thread Use Case Development | 5 | 5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-513 | AES-6380 |  |  | Document the status of EIS Design Thread progress pt1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-514 | AES-6381 |  |  | Document the status of EIS progress pt2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-515 | AES-6382 |  |  | Document the status of EIS progress pt4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-31 |  |  | 3
|  |  | SPACE-516 | AES-6383 |  |  | Document the status of EIS progress pt5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-517 | AES-6384 |  |  | Document the status of EIS progress pt6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
| 1.3.1.5 |  | SPACE-518 | AES-6385 |  |  | EXP: SME Support to document Space Master Data for Non-Core Systems for MBE | 31 | 31 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-519 | AES-6386 |  |  | Understand the scope of non core master data management work | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-520 | AES-6387 |  |  | SME Support placeholder pt1 | 5 | 5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-521 | AES-6388 |  |  | SME Support placeholder pt2 | 5 | 5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-522 | AES-6389 |  |  | SME Support placeholder pt3 | 5 | 5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-523 | AES-6390 |  |  | SME Support placeholder pt4 | 5 | 5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-524 | AES-6391 |  |  | SME Support placeholder pt5 | 5 | 5 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-525 | AES-6392 |  |  | SME Support placeholder pt6 | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-526 | AES-6393 |  |  | EXP: DSARC LOE | 20 | 20 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-527 | AES-6394 |  |  | Run-Ahead | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-528 | AES-6395 |  |  | Run-Ahead | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-529 | AES-6396 |  |  | Run-Ahead | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-530 | AES-6397 |  |  | ROMB Prep | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-531 | AES-6398 |  |  | ERB/CCB Review | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-532 | AES-6399 |  |  | ERB/CCB Review | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-533 | AES-6400 |  |  | ROMB Prep | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-534 | AES-6401 |  |  | ROMB Prep | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-535 | AES-6402 |  |  | ROMB Prep | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-536 | AES-6403 |  |  | ROMB Prep | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-537 | AES-6404 |  |  | ROMB Prep | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-538 | AES-6405 |  |  | ERB/CCB Review | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-539 | AES-6406 |  |  | ERB/CCB Review | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-540 | AES-6407 |  |  | ERB/CCB Review | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-541 | AES-6408 |  |  | ERB/CCB Review | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-542 | AES-6409 |  |  | Data Standards and Architecture Month End May | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-543 | AES-6410 |  |  | Data Standards and Architecture Month End April | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-544 | AES-6411 |  |  | Run-Ahead Planning | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.232C.0004 | SPACE-545 | AES-6412 | ONELMX_MBE_SSC | MBECCA23CP | Spc MBE: Future Architecture Design Work - Cap Lab/NL | 130 | 113 | 17 | 86.92% | 2023-04-02 |  | 2023-04-03 | 2023-06-23 | 1
| 1.3.1.5 |  | SPACE-546 | AES-6413 |  |  | CAP: Draft PLM Whitepaper | 18 | 18 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-547 | AES-6414 |  |  | Create PLM Whitepaper Outline | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-548 | AES-6415 |  |  | Complete 1LMX Vision Section of PLM Whitepaper | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-549 | AES-6416 |  |  | Complete Abstract and Problem Statement Section of PLM Whitepaper | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-550 | AES-6417 |  |  | Complete PLM Scope and Strategy Sections of PLM Whitepaper | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-551 | AES-6418 |  |  | Complete Impact and Space Strategy Sections of PLM Whitepaper | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-552 | AES-6419 |  |  | Finalize First Draft of PLM Whitepaper | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
| 1.3.1.5 |  | SPACE-553 | AES-6420 |  |  | CAP: Design the future state of Space Interface | 25 | 25 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-554 | AES-6421 |  |  | Convert the future state of Space Interface diagrams into UAF | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-555 | AES-6422 |  |  | Complete SVB Capability Diagram | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-556 | AES-6423 |  |  | Collect Detailed SBV Development Goals | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-557 | AES-6424 |  |  | Apply Rapid-Need Standards to SBV Capability | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
|  |  | SPACE-558 | AES-6425 |  |  | Work top level logical reference architecture pt 3 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-559 | AES-6426 |  |  | Integration Layer Deep-Dive Session - Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-08 |  |  | 3
|  |  | SPACE-560 | AES-6427 |  |  | Integration Layer Deep-Dive Session - Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-561 | AES-6428 |  |  | Integration Layer PDR Use Case Questions | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-11 |  |  | 3
|  |  | SPACE-562 | AES-6429 |  |  | Work top level logical reference architecture pt 1 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-563 | AES-6430 |  |  | Work top level logical reference architecture pt 2 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-564 | AES-6431 |  |  | Evaluate TSM Capability Demonstration with DTS/DTV Pt 2 | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-565 | AES-6432 |  |  | Collect information on current state for modeling effort next quarter <look-ahead> pt1 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-566 | AES-6433 |  |  | Collect information on Future state for modeling effort next quarter <look-ahead> pt1 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-567 | AES-6434 |  |  | Collect information on Future state for modeling effort next quarter <look-ahead> pt2 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-568 | AES-6435 |  |  | Create Future State Diagram for DTv Demo | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-569 | AES-6436 |  |  | Create Future State Diagram for Analysis Sync Capability | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-570 | AES-6437 |  |  | Collect information on Value Streams and Enterprise Arch (ERP,MES) for modeling effort next quarter <look-ahead> pt2 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-571 | AES-6438 |  |  | Compile PDR Use Cases | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-572 | AES-6439 |  |  | SBV Capability Integration | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-573 | AES-6440 |  |  | CAP: MPMLink - Develop Process for Synthetic Materials | 6 | 6 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-574 | AES-6441 |  |  | DSARC-Review Requirements for Sync of Common and Orion Synthetics | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-15 |  |  | 3
|  |  | SPACE-575 | AES-6442 |  |  | DSARC-Document EPDM Synthetic Part Requirements | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-576 | AES-6443 |  |  | DSARC-Create Synthetic Part soft type in EPDM | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-577 | AES-6444 |  |  | CAP: MPMLink - Effectivity Requirements | 20 | 20 | 0 | 100% |  |  | 2023-04-02 | 2023-06-23 | 2
|  |  | SPACE-578 | AES-6445 |  |  | DSARC-Effectivity Demo - Kickoff and Planning | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-579 | AES-6446 |  |  | DSARC-Effectivity Demo - Coordination and Prep | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-580 | AES-6447 |  |  | DSARC-Evaluate Effectivity Process Harmonization options | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-581 | AES-6448 |  |  | DSARC-Effectivity Demo - Team Preparation | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-582 | AES-6449 |  |  | DSARC-Effectivity Demo - Team Preparation | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-583 | AES-6450 |  |  | DSARC-Effectivity Demo - Session 2 | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-584 | AES-6451 |  |  | DSARC-Effectivity Demo - Session 1 | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-585 | AES-6452 |  |  | DSARC-Document Effectivity Demo Summary Observations (EPDM and SAP) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-586 | AES-6453 |  |  | CAP: MPMLink - Modify EPDM and SAP Interface | 24 | 21 | 3 | 87.5% |  |  | 2023-06-26 | 2023-09-24 | 2
|  |  | SPACE-587 | AES-6454 |  |  | DSARC-Document EPDM to ERP Transaction Requirements | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-588 | AES-6455 |  |  | DSARC-Create new transaction 203M in EPDM to handle creation of MBOM - Part 1 | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-589 | AES-6456 |  |  | DSARC-Modify 101 transaction on EPDM side to allow synthetic/inv code part types | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-590 | AES-6457 |  |  | DSARC-Investigate EPDM to ERP Interface Transactions | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-591 | AES-6458 |  |  | DSARC-Create new transaction 203M in EPDM to handle creation of MBOM - Part 3 | 3 | 0 | 3 | 0% | 2023-07-16 |  |  |  | 3
|  |  | SPACE-592 | AES-6459 |  |  | DSARC-Create new transaction 203M in EPDM to handle creation of MBOM - Part 2 | 5 | 5 | 0 | 100% | 2023-06-25 | 2023-07-13 |  |  | 3
|  |  | SPACE-593 | AES-6460 |  |  | CAP: MPMLink - Develop Process for Inventory Codes | 21 | 15 | 6 | 71.43% |  |  | 2023-04-02 | 2023-09-22 | 2
|  |  | SPACE-594 | AES-6461 |  |  | DSARC-Document EPDM Inventory Code Requirements | 5 | 5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-595 | AES-6462 |  |  | DSARC-Review Inventory Code federation objectives | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-596 | AES-6463 |  |  | DSARC-EPDM Inventory Code Soft Type Creation | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-597 | AES-6464 |  |  | DSARC-Configure EPDM for Inventory Codes (container/access) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-598 | AES-6465 |  |  | DSARC-Develop PMP Federation for Inventory Codes - Part 1 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-599 | AES-6466 |  |  | DSARC-Complete Data Mapping for Inventory Code Migration | 5 | 5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-600 | AES-6467 |  |  | DSARC-Complete Staging for Inventory Code Migration | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-601 | AES-6468 |  |  | DSARC-Execute data migration of inventory codes | 1 | 0 | 1 | 0% |  |  |  |  | 3
|  |  | SPACE-602 | AES-6469 |  |  | DSARC-Develop PMP Inventory Code Synchronization Functionality | 5 | 0 | 5 | 0% |  |  |  |  | 3
|  |  | SPACE-603 | AES-6470 |  |  | CAP: MPMLink - Develop MBOM Release Process | 16 | 8 | 8 | 50% |  |  | 2023-04-02 | 2023-09-22 | 2
|  |  | SPACE-604 | AES-6471 |  |  | DSARC-Review MBOM Release Process with ME Team | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-605 | AES-6472 |  |  | DSARC-Document MBOM Usage Attribute Requirements | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-606 | AES-6473 |  |  | DSARC-Create MBOM Usage Attributes | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-607 | AES-6474 |  |  | DSARC-Document MBOM Release Process Requirements | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-608 | AES-6475 |  |  | DSARC-Configure Plant Specific MBOMs/Views in EPDM | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-609 | AES-6476 |  |  | DSARC-Develop Action to Send MBOM to ERP - Part 1 | 5 | 0 | 5 | 0% |  |  |  |  | 3
|  |  | SPACE-610 | AES-6477 |  |  | DSARC-Develop Action to Send MBOM to ERP - Part 2 | 3 | 0 | 3 | 0% |  |  |  |  | 3
|  |  | SPACE-611 |  |  |  | SLMX_MBE_ENABL | 546.5 | 546.5 | 0 | 100% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-612 | AES-6478 | ONELMX_MBE_SSC | MBE23LOE | Spc MBE: ENABL LOE 23.2 - Exp - Lab/NL | 70.5 | 70.5 | 0 | 100% | 2023-04-02 | 2023-06-22 | 2023-03-27 | 2023-06-23 | 1
|  |  | SPACE-613 | AES-6479 |  |  | Enablers Generic Tasks 2023.2 | 70.5 | 70.5 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-614 | AES-6480 |  |  | Enablers SM Support 2023.2.1 | 6 | 6 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-615 | AES-6481 |  |  | Enablers Generic Tasks 2023.2.1 | 1.5 | 1.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-616 | AES-6482 |  |  | Run Ahead Planning 2023.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-617 | AES-6483 |  |  | Run Ahead Planning 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-618 | AES-6484 |  |  | Run Ahead Planning 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-619 | AES-6485 |  |  | Enablers ROMB 2023.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-620 | AES-6486 |  |  | External Dependency Remediation 2023.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-621 | AES-6487 |  |  | Enablers SM Support 2023.2.2 | 4 | 4 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-622 | AES-6488 |  |  | Enablers SM Support 2023.2.3 | 6 | 6 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-623 | AES-6489 |  |  | Enablers SM Support 2023.2.4 | 5 | 5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-624 | AES-6490 |  |  | Enablers SM Support 2023.2.5 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-625 | AES-6491 |  |  | Enablers SM Support 2023.2.6 | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-626 | AES-6492 |  |  | Enablers Generic Tasks 2023.2.2 | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-627 | AES-6493 |  |  | Enablers Generic Tasks 2023.2.3 | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-628 | AES-6494 |  |  | Enablers Generic Tasks 2023.2.4 | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-629 | AES-6495 |  |  | Enablers Generic Tasks 2023.2.5 | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-630 | AES-6496 |  |  | Enablers Generic Tasks 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-631 | AES-6497 |  |  | Enablers ROMB 2023.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-632 | AES-6498 |  |  | Enablers ROMB 2023.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-633 | AES-6499 |  |  | Enablers ROMB 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-634 | AES-6500 |  |  | Enablers ROMB 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-635 | AES-6501 |  |  | Enablers ROMB 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-636 | AES-6502 |  |  | External Dependency Remediation 2023.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-637 | AES-6503 |  |  | External Dependency Remediation 2023.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-638 | AES-6504 |  |  | External Dependency Remediation 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-639 | AES-6505 |  |  | External Dependency Remediation 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-640 | AES-6506 |  |  | External Dependency Remediation 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-641 | AES-6507 |  |  | Run Ahead Planning 2023.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-642 | AES-6508 |  |  | Run Ahead Planning 2023.2.6 | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-643 | AES-6509 |  |  | Run Ahead Planning 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-644 | AES-6510 |  |  | Run Ahead Planning 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-645 | AES-6511 |  |  | Run Ahead Planning 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-646 | AES-6512 |  |  | Run Ahead Planning 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-647 | AES-6513 |  |  | Enablers Generic Tasks 2023.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-648 | AES-6514 |  |  | Enablers Generic Tasks 2023.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-649 | AES-6515 |  |  | Enablers Generic Tasks 2023.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-650 | AES-6516 |  |  | Enablers Generic Tasks 2023.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-651 | AES-6517 |  |  | Enablers Generic Tasks 2023.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-652 | AES-6518 |  |  | Enablers Generic Tasks 2023.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-653 | AES-6519 |  |  | Enablers ERB/CCB 2023.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-654 | AES-6520 |  |  | Enablers ERB/CCB 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-655 | AES-6521 |  |  | Enablers ERB/CCB 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-656 | AES-6522 |  |  | Enablers ERB/CCB 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-657 | AES-6523 |  |  | Enablers ERB/CCB 2023.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-658 | AES-6524 |  |  | Enablers ERB/CCB 2023.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-659 | AES-6525 |  |  | Innovation: Azure - research adoption on classified versus AWS, experiment with a deployment to? | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-660 | AES-6526 |  |  | Innovation: Investigate moving all containers and automation to harbor.global | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-661 | AES-6527 |  |  | Innovation: ArgoCD - investigate benefits | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-662 | AES-6528 |  |  | Innovation: Investigate moving SMBE to AWS Openshift clusters - data types | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-663 | AES-6529 |  |  | Innovation: Investigate Tanzu openshift dedicated clusters | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-664 | AES-6530 |  |  | Innovation: Volta-player on cloud and containerized | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-665 | AES-6531 |  |  | Conduct NGI Blameless Post-Mortem | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-666 | AES-6532 |  |  | Increment Demo Prep | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-667 | AES-6533 |  |  | F2F Attendance - Rick | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-668 | AES-6534 |  |  | F2F Attendance - Erin | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-18 |  |  | 3
|  |  | SPACE-669 | AES-6535 |  |  | F2F Attendance - Dave | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-670 | AES-6536 |  |  | F2F Attendance - Diane | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-671 | AES-6537 |  |  | F2F Attendance - Zac | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-672 | AES-6538 |  |  | F2F Attendance - Daniel | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-673 | AES-6539 |  |  | F2F Attendance - Daryn | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-18 |  |  | 3
|  |  | SPACE-674 | AES-6540 |  |  | F2F Attendance - Calvin | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-17 |  |  | 3
|  |  | SPACE-675 | AES-6541 |  |  | SPIKE: Issue resolve - Mission Ready Openshift not allowing new Harbor.Global | 0 | 0 | 0 | 0% | 2023-04-30 | 2023-05-03 |  |  | 3
|  |  | SPACE-676 | AES-6542 |  |  | Enablers Month End May | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-677 | AES-6543 |  |  | Enablers Month End April | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-678 | AES-6544 |  |  | Recruit for Deputy Chief Arch Req 636786BR | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-679 | AES-6545 |  |  | Innovation Follow-On: SOW Review Mtg on Volta-player on cloud & containerized | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-680 | AES-6546 |  |  | Innovation Follow-On: ArgoCD - SCEE Coordination | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-681 | AES-6547 |  |  | Post SIA and NGI Post Mortem Follow Through | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.232E.0004 | SPACE-682 | AES-6548 | ONELMX_MBE_SSC | MBEDPP23 | Spc MBE: Deployment 23.2 Quarterly Release - Exp Lab/NL | 13.9 | 13.9 | 0 | 100% | 2023-04-02 | 2023-06-19 | 2023-04-03 | 2023-06-23 | 1
|  |  | SPACE-683 | AES-6549 |  |  | Deployment Packaging Requirements 2023.2 | 0.5 | 0.5 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-684 | AES-6550 |  |  | Define Requirements for Deployment Updates 2023.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-685 | AES-6551 |  |  | Production Operations Requirements 2023.2 | 0.9 | 0.9 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-686 | AES-6552 |  |  | Define Requirements for ITIL 2023.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-687 | AES-6553 |  |  | Define Requirements for ITIL 2023.2.6 | 0.4 | 0.4 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-688 | AES-6554 |  |  | SWF Pipeline/Deployment Release Requirements 2023.2 | 7 | 7 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-689 | AES-6555 |  |  | TO DO List | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-690 | AES-6556 |  |  | Efoss Intake 2023.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-691 | AES-6557 |  |  | Prepr Pipeline Requirements Task 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-692 | AES-6558 |  |  | Hoppr Intake | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-693 | AES-6559 |  |  | Hoppr Intake | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-694 | AES-6560 |  |  | Solicit eFOSS Hot List for MBE/NGI Submissions/Approvals | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-695 | AES-6561 |  |  | Hoppr Intake Part 2 2023.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-696 | AES-6562 |  |  | Solicit DD intent | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-697 | AES-6563 |  |  | Generic Requirements Task 2023.2.4 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-698 | AES-6564 |  |  | Prepr Pipeline Requirements Task 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-699 | AES-6565 |  |  | Prepr Pipeline Requirements Task 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-700 | AES-6566 |  |  | Additional Program Deployment Planning/Requirements 2023.2 | 5.5 | 5.5 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-701 | AES-6567 |  |  | Additional Program Deployment Planning 2023.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-702 | AES-6568 |  |  | GSFA Program Deployment Planning 2023.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-703 | AES-6569 |  |  | GSFA Program Deployment Planning 2023.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-704 | AES-6570 |  |  | GSFA Program Deployment Planning - SIA - 2023.2.3 | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.232C.0003 | SPACE-705 | AES-6571 | ONELMX_MBE_SSC | MBEDPP23CP | Spc MBE: Deployment 23.2 Quarterly Release - Cap Lab/NL | 462.1 | 462.1 | 0 | 100% | 2023-04-02 | 2023-06-26 | 2023-04-03 | 2023-06-23 | 1
|  |  | SPACE-706 | AES-6572 |  |  | Service Level Agreement Refinement 2023.2 | 1 | 1 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-707 | AES-6573 |  |  | Update SLA documents 2023.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-708 | AES-6574 |  |  | Update SLA documents 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-709 | AES-6575 |  |  | Enablers - SCEE Outreach 2023.2 | 4 | 4 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-710 | AES-6576 |  |  | SCEE Outreach 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-711 | AES-6577 |  |  | SCEE Outreach 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-712 | AES-6578 |  |  | SCEE Outreach 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-713 | AES-6579 |  |  | SCEE Outreach 2023.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-714 | AES-6580 |  |  | SCEE Outreach 2023.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-715 | AES-6581 |  |  | SCEE Outreach 2023.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-716 | AES-6582 |  |  | Reach out to SCEE about Hoppr | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-717 | AES-6583 |  |  | Reach out to SCEE about Hoppr/Prepr | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-718 | AES-6584 |  |  | Enablers - Digital Twin Outreach 2023.2 | 12.5 | 12.5 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-719 | AES-6585 |  |  | Digital Twin Outreach 2023.2.1 - Jordan | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-720 | AES-6586 |  |  | Digital Twin Outreach 2023.2.1 - Phill | 0 | 0 | 0 | 0% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-721 | AES-6587 |  |  | Digital Twin Outreach 2023.2.1 - Dave | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-722 | AES-6588 |  |  | Digital Twin Outreach 2023.2.6 - Dave | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-723 | AES-6589 |  |  | Digital Twin Outreach 2023.2.5 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-724 | AES-6590 |  |  | Digital Twin Outreach 2023.2.4 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-725 | AES-6591 |  |  | Digital Twin Outreach 2023.2.3 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-726 | AES-6592 |  |  | Digital Twin Outreach 2023.2.2 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-727 | AES-6593 |  |  | Digital Twin Outreach 2023.2.6 - Phill | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-728 | AES-6594 |  |  | Digital Twin Outreach 2023.2.5 - Phill | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-729 | AES-6595 |  |  | Digital Twin Outreach 2023.2.4 - Phill | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-730 | AES-6596 |  |  | Digital Twin Outreach 2023.2.6 - Jordan | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-731 | AES-6597 |  |  | Digital Twin Outreach 2023.2.5 - Jordan | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-732 | AES-6598 |  |  | Digital Twin Outreach 2023.2.4 - Jordan | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-733 | AES-6599 |  |  | Digital Twin Outreach 2023.2.3 - Jordan | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-734 | AES-6600 |  |  | Digital Twin Outreach 2023.2.2 - Jordan | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-735 | AES-6601 |  |  | SWF Align Enabler Pipelines/Deployment Release 2023.2 | 178.5 | 178.5 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-736 | AES-6602 |  |  | SBOM Release Alternative 2023.2 | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-737 | AES-6603 |  |  | Kafka SBOM add docker purl automatically 2023.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-738 | AES-6604 |  |  | Generic Pipeline Task 2023.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-739 | AES-6605 |  |  | Generic Pipeline Task 2023.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-740 | AES-6606 |  |  | Generic Pipeline Task 2023.2.5 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-741 | AES-6607 |  |  | Generic Pipeline Task 2023.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-742 | AES-6608 |  |  | Correct Semantic Release Dry Run and add to Kafka 2023.2 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-743 | AES-6609 |  |  | Syndeia create an SBOM for the repo 2023.2 | 1.5 | 1.5 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-744 | AES-6610 |  |  | Semantic Release VS NGI (Erick) committer module | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-745 | AES-6611 |  |  | Adjudicate Tyler's developer desktop | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-746 | AES-6612 |  |  | Extract Erick's process into it's own repo. | 7 | 7 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-747 | AES-6613 |  |  | Submit semantic release dry run fix to pipeline catalog | 5 | 5 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-748 | AES-6614 |  |  | Implement Sbom-Modify-Components | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-749 | AES-6615 |  |  | Extract Data from py-foss modules | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-750 | AES-6616 |  |  | Generic Pipeline Task | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-751 | AES-6617 |  |  | ARGO CD changes | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-752 | AES-6618 |  |  | Add Semantic Release to all Syndeia supporting Repos | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-753 | AES-6619 |  |  | Handle Automated failed submissions, Identify how to handle | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-754 | AES-6620 |  |  | Add "transfer" CI/CD job 2023.2 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-755 | AES-6621 |  |  | Bring Semantic Release to ngi-transfer-utils | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-756 | AES-6622 |  |  | Extract "sbom-exclude" to ngi-transfer-utils | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-757 | AES-6623 |  |  | Manual NGI Low-High Steps | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-758 | AES-6624 |  |  | Submit semantic release dry run fix to pipeline catalog | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-759 | AES-6625 |  |  | Implement Sbom-Modify-Properties | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-760 | AES-6626 |  |  | Generic Pipeline Task 2023.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-761 | AES-6627 |  |  | Kafka SBOM add docker purl automatically 2023.2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-762 | AES-6628 |  |  | Extract "efoss_request" to ngi-transfer-utils | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-763 | AES-6629 |  |  | Use Semantic Release to tag BOM | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-764 | AES-6630 |  |  | Codify Erick's NGI code 2023.2 - TBD | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-765 | AES-6631 |  |  | Submit semantic release dry run (& publish) fix to pipeline catalog | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-766 | AES-6632 |  |  | Align KAFKA repository to use semantic release - TBD | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-767 | AES-6633 |  |  | NGI/Erick Process Capture | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-768 | AES-6634 |  |  | Align ngi-transfer-utils to Erick's format | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-769 | AES-6635 |  |  | Make “test” transfer/approved CL | 1.5 | 1.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-770 | AES-6636 |  |  | Extract job SBOM TRANSFER to (ngi-)transfer-utils - cl | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-771 | AES-6637 |  |  | Extract job SBOM Modify Component to ngi-transfer-utils | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-772 | AES-6638 |  |  | Write instruction on how to use Semantic Release to tag BOM | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-773 | AES-6639 |  |  | Prepr Committer 2023.2.3 Clone | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-774 | AES-6640 |  |  | Add Semantic Release to Zookeeper Repo | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-02 |  |  | 3
|  |  | SPACE-775 | AES-6641 |  |  | Add internal test to ngi-transfer-utils repo | 0.5 | 0.5 | 0 | 100% |  |  |  |  | 3
|  |  | SPACE-776 | AES-6642 |  |  | Add Abstract Jobs to NGI-Transfer-Utils 2023.2.3 - cl | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-777 | AES-6643 |  |  | CL -eFOSS Approvals for NGI/MBE | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-778 | AES-6644 |  |  | NGI/Erick Process Capture | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-779 | AES-6645 |  |  | Contribute to Pipeline Catalog (PC); Erick's NGI code 2023.2 | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-780 | AES-6646 |  |  | KAFKA repository Corrections with semantic release | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-781 | AES-6647 |  |  | Manual NGI Low-High Steps.. first go kafka | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-782 | AES-6648 |  |  | Sbom-Quality-Assessment (for Erick) - SMCL | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-783 | AES-6649 |  |  | PURL Solution in NGI-Transfer-Utils | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-784 | AES-6650 |  |  | CL - Purl Option 2: Use Erick's Purl solution 2023.2 - TBD | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-785 | AES-6651 |  |  | Add Podman/Kaniko to ngi-transfer-utils cl | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-786 | AES-6652 |  |  | Add Hadolint to ngi-transfer-utils | 1.5 | 1.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-787 | AES-6653 |  |  | CL Update build image transfer-prepr job not push to harbor Kafka | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-788 | AES-6654 |  |  | Extract job SBOM Modify Property to ngi-transfer-utils | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-789 | AES-6655 |  |  | Argo CD/Vendor Images - Run Syndeia (anything) in OpenShift | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-790 | AES-6656 |  |  | Test Out Vendor Image in our OC (Like Kafka) | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-791 | AES-6657 |  |  | Fix Branches in Nodes and Edges Clone | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-792 | AES-6658 |  |  | Add Renovate to ngi-transfer-utils repo -cl | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-793 | AES-6659 |  |  | Demo Feedback 4/27- Add version metadata to kafka image name and sbom name | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-794 | AES-6660 |  |  | Demo Feedback 4/27 -Parameterize Kafka version in Dockerfile | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-795 | AES-6661 |  |  | Get kafka branch to make an MR in ngi-transfer/approved | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-796 | AES-6662 |  |  | Demo follow on (potentially create DD image for SCEE) -SMCL | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-797 | AES-6663 |  |  | Zookeeper - Horizonal Implementation of transfer-utils for Syndeia | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-798 | AES-6664 |  |  | Clean up Kafka and the Swamp cl | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-799 | AES-6665 |  |  | Prepr, Pipeline Catalog Alternative 2023.2 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-800 | AES-6666 |  |  | Solicit eFOSS Hot List for MBE/NGI Submissions/Approvals | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-801 | AES-6667 |  |  | Argo CD/Vendor Images - Run Syndeia (anything) in SWF OpenShift | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-802 | AES-6668 |  |  | Clean up Kafka to use only tranfer-prepr | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-803 | AES-6669 |  |  | Abstract Improvements to Transfer-Prepr | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-804 | AES-6670 |  |  | Show SBOM TRANSFER job working in transfer-prepr | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-805 | AES-6671 |  |  | CL Complete Podman transfer-prepr | 3.5 | 3.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-806 | AES-6672 |  |  | Add Renovate to transfer-prepr repo | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-807 | AES-6673 |  |  | Venahab -Horizonal Implementation of transfer-prepr for Syndeia | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-808 | AES-6674 |  |  | Casandra -Horizonal Implementation of transfer-prepr for Syndeia | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-809 | AES-6675 |  |  | Run Bitnami Kafka image in SWF Syndeia build | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-810 | AES-6676 |  |  | Fix transfer-utils pipeline to work with Kafka | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-811 | AES-6677 |  |  | Merge approved/kafka MR and verify bundle works | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-812 | AES-6678 |  |  | OC deployment documentation | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-813 | AES-6679 |  |  | CL Demo Feedback - Spike: fix cyclonedx scanner pipeline catalogue script | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-814 | AES-6680 |  |  | 5/30 Developer Desktop Demo Prep | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-05-30 |  |  | 3
|  |  | SPACE-815 | AES-6681 |  |  | Make CI/CD Purl Solution to use Erick's Component Add | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-816 | AES-6682 |  |  | Scout rules - Venahab | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-817 | AES-6683 |  |  | Merge in Podman transfer-prepr -clone | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-818 | AES-6684 |  |  | Demo Feedback - Spike: fix cyclonedx scanner pipeline catalogue script | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-819 | AES-6685 |  |  | Close MR on Zookeeper | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-820 | AES-6686 |  |  | eFOSS Approvals for NGI/MBE | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-821 | AES-6687 |  |  | Close - Merge approved/kafka MR and verify bundle works | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-822 | AES-6688 |  |  | Update build image transfer-prepr job not push to harbor Kafka | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-823 | AES-6689 |  |  | Point our prepr to Erick's prepr - clone | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-824 | AES-6690 |  |  | SCEE Access for prepr - SMCL | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-825 | AES-6691 |  |  | Document SBOM additions/removals process | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-826 | AES-6692 |  |  | Make CI/CD Efoss job Manual/different - clone | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-827 | AES-6693 |  |  | Make sbom-combine use erick's pipeline instead of copy pasting the code - Clone Exclude | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-828 | AES-6694 |  |  | Make ngi-transfer/approved generic - clone | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-829 | AES-6695 |  |  | Prepr Phrasing; Use at your own risk - SMCL | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-830 | AES-6696 |  |  | Merge in Podman transfer-prepr | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-13 |  |  | 3
|  |  | SPACE-831 | AES-6697 |  |  | Make MBE prepr use erick's single prepr instead of copy pasting | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-832 | AES-6698 |  |  | Demo Feedback - Make CI/CD Efoss job Manual/different | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-833 | AES-6699 |  |  | eFOSS Approvals for NGI/MBE CL | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-834 | AES-6700 |  |  | Merge - Make CI/CD Purl Solution to use Erick's Component Add | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-835 | AES-6701 |  |  | Demo Feedback - Sbom-Quality-Assessment | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-836 | AES-6702 |  |  | Demo follow on (potentially create DD image for SCEE) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-837 | AES-6703 |  |  | Allow Prepr to skip eFOSS for NSPR/COTS repos | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-838 | AES-6704 |  |  | Make sure that all Syndeia repos needed by NGI have Prepr | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-839 | AES-6705 |  |  | Make sbom-exclude use erick's pipeline instead of copy pasting the code | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-840 | AES-6706 |  |  | Make ngi-transfer/approved generic CL | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-841 | AES-6707 |  |  | Is add/remove is the same as say in a tar file | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-842 | AES-6708 |  |  | Investigate Lintr in prepr Clone | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-843 | AES-6709 |  |  | Spike on verify source of a SBOM with dockerfile layers | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-844 | AES-6710 |  |  | Update MBE O&M Plan 2023.2 | 3 | 3 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-845 | AES-6711 |  |  | Update MBE O&M Plan 2023.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-846 | AES-6712 |  |  | Update MBE O&M Plan 2023.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-847 | AES-6713 |  |  | Update MBE O&M Plan 2023.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-848 | AES-6714 |  |  | Update MBE O&M Plan 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-849 | AES-6715 |  |  | Update MBE O&M Plan 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-850 | AES-6716 |  |  | Update MBE O&M Plan 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-851 | AES-6717 |  |  | Vault Outreach 2023.2 | 43 | 43 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-852 | AES-6718 |  |  | Vault Outreach 2023.2.1 - Diane | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-853 | AES-6719 |  |  | Vault Outreach 2023.2.6 - Diane | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-854 | AES-6720 |  |  | Vault Outreach 2023.2.5 - Diane | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-855 | AES-6721 |  |  | Vault Outreach 2023.2.4 - Diane | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-856 | AES-6722 |  |  | Vault Outreach 2023.2.3 - Diane | 2.5 | 2.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-857 | AES-6723 |  |  | Vault Outreach 2023.2.2 - Diane | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-858 | AES-6724 |  |  | Vault Outreach 2023.2.1 - Bao | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-859 | AES-6725 |  |  | Vault Outreach 2023.2.6 - Bao | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-860 | AES-6726 |  |  | Vault Outreach 2023.2.5 - Bao | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-861 | AES-6727 |  |  | Vault Outreach 2023.2.4 - Bao | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-862 | AES-6728 |  |  | Vault Outreach 2023.2.3 - Bao | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-863 | AES-6729 |  |  | Vault Outreach 2023.2.2 - Bao | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-864 | AES-6730 |  |  | Vault-plugin openshift 2023.2.1 -- Diane | 2.5 | 2.5 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-865 | AES-6731 |  |  | Vault-plugin openshift 2023.2.1 -- Bao | 2.5 | 2.5 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-866 | AES-6732 |  |  | Vault-plugin openshift 2023.2.2 -- Diane | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-867 | AES-6733 |  |  | Vault-plugin openshift 2023.2.2 -- Bao | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-868 | AES-6734 |  |  | Vault-plugin openshift 2023.2.3 -- Bao | 2.5 | 2.5 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-869 | AES-6735 |  |  | Vault-plugin openshift 2023.2.4 -- Bao | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-870 | AES-6736 |  |  | Vault-plugin openshift 2023.2.5 -- Bao | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-871 | AES-6737 |  |  | Vault-plugin openshift 2023.2.6 -- Bao | 2.5 | 2.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-872 | AES-6738 |  |  | Vault-plugin Openshift 2023.2.3 -- Diane | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-873 | AES-6739 |  |  | Vault-plugin Openshift 2023.2.4 -- Diane | 4.5 | 4.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-874 | AES-6740 |  |  | Vault-plugin Openshift 2023.2.5 -- Diane | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-875 | AES-6741 |  |  | Vault-plugin Openshift 2023.2.6 -- Diane | 3.5 | 3.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-876 | AES-6742 |  |  | Enablers - Engineering Efficiency Outreach 2023.2 | 24 | 24 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-877 | AES-6743 |  |  | Enablers Eng Eff Outreach 2023.2.1 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-878 | AES-6744 |  |  | Enablers Eng Eff Outreach 2023.2.6 - Dave | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-879 | AES-6745 |  |  | Enablers Eng Eff Outreach 2023.2.5 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-880 | AES-6746 |  |  | Enablers Eng Eff Outreach 2023.2.4 - Dave | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-881 | AES-6747 |  |  | Enablers Eng Eff Outreach 2023.2.3 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-882 | AES-6748 |  |  | Enablers Eng Eff Outreach 2023.2.2 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-883 | AES-6749 |  |  | Enablers Eng Eff Outreach 2023.2.1 - Jordan | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-884 | AES-6750 |  |  | Enablers Eng Eff Outreach 2023.2.6 - Jordan | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-885 | AES-6751 |  |  | Enablers Eng Eff Outreach 2023.2.5 - Jordan | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-886 | AES-6752 |  |  | Enablers Eng Eff Outreach 2023.2.4 - Jordan | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-887 | AES-6753 |  |  | Enablers Eng Eff Outreach 2023.2.3 - Jordan | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-888 | AES-6754 |  |  | Enablers Eng Eff Outreach 2023.2.2 - Jordan | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-889 | AES-6755 |  |  | Enablers Eng Eff Outreach 2023.2.1 - Phill | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-890 | AES-6756 |  |  | Enablers Eng Eff Outreach 2023.2.6 - Phill | 3.5 | 3.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-891 | AES-6757 |  |  | Enablers Eng Eff Outreach 2023.2.5 - Phill | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-892 | AES-6758 |  |  | Enablers Eng Eff Outreach 2023.2.4 - Phill | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-893 | AES-6759 |  |  | Enablers Tag Up Sprint 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-894 | AES-6760 |  |  | Enablers Tag Up Sprint 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-895 | AES-6761 |  |  | Enablers Tag Up Sprint 3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-01 |  |  | 3
|  |  | SPACE-896 | AES-6762 |  |  | Enablers Tag Up Sprint 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-897 | AES-6763 |  |  | Enablers Tag Up Sprint 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-898 | AES-6764 |  |  | Enablers Tag Up Sprint 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-899 | AES-6765 |  |  | Enablers - NGI Program Deployment 2023.2 | 24.5 | 24.5 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-900 | AES-6766 |  |  | NGI TSM Deployment 2023.2.1 - Dave | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-901 | AES-6767 |  |  | NGI TSM Deployment 2023.2.1 - Michael | 3.5 | 3.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-902 | AES-6768 |  |  | NGI TSM Deployment 2023.2.1 - Daniel | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-903 | AES-6769 |  |  | NGI TSM Deployment 2023.2.1 - David | 2.5 | 2.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-904 | AES-6770 |  |  | NGI TSM Deployment 2023.2.1 - Kevin | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-905 | AES-6771 |  |  | NGI TSM Deployment 2023.2.2 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-906 | AES-6772 |  |  | NGI TSM Deployment 2023.2.2 - Michael | 5 | 5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-907 | AES-6773 |  |  | NGI TSM Deployment 2023.2.2 - Daniel | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-908 | AES-6774 |  |  | NGI TSM Deployment 2023.2.2 - David | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-18 |  |  | 3
|  |  | SPACE-909 | AES-6775 |  |  | NGI TSM Deployment 2023.2.2 - Kevin | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-910 | AES-6776 |  |  | NGI Vulnerability Update - 3.5SP1, RLM14 License Server, IL Release 7a | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-911 | AES-6777 |  |  | Efoss Reviews NGI/MBE | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-912 | AES-6778 |  |  | Volta IAT - Volta Player on HPC 2023.2 | 2.4 | 2.4 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-913 | AES-6779 |  |  | VoltaPlayer 2023.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-914 | AES-6780 |  |  | VoltaPlayer 2023.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-915 | AES-6781 |  |  | VoltaPlayer 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-916 | AES-6782 |  |  | VoltaPlayer 2023.2.5 | 0.4 | 0.4 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-917 | AES-6783 |  |  | VoltaPlayer 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-918 | AES-6784 |  |  | Demand Management 2023.2 | 0.1 | 0.1 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-919 | AES-6785 |  |  | Demand Management 2023.2.6 | 0.1 | 0.1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-920 | AES-6786 |  |  | Incident Management 2023.2 | 0.1 | 0.1 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-921 | AES-6787 |  |  | Incident Management 2023.2.6 | 0.1 | 0.1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-922 | AES-6788 |  |  | Change Management 2023.2 | 0.1 | 0.1 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-923 | AES-6789 |  |  | Change Management 2023.2.6 | 0.1 | 0.1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-924 | AES-6790 |  |  | Problem Management 2023.2 | 0.1 | 0.1 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-925 | AES-6791 |  |  | Problem Management 2023.2.6 | 0.1 | 0.1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-926 | AES-6792 |  |  | Performance & Capacity Management 2023.2 | 1.5 | 1.5 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-927 | AES-6793 |  |  | Performance & Capacity Management 2023.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-928 | AES-6794 |  |  | Performance & Capacity Management 2023.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-929 | AES-6795 |  |  | Pager Duty Refinement 2023.2 | 0.1 | 0.1 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-930 | AES-6796 |  |  | Pager Duty Onboarding 2023.2.6 | 0.1 | 0.1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-931 | AES-6797 |  |  | NOC Refinement 2023.2 | 0.1 | 0.1 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-932 | AES-6798 |  |  | NOC Refinement 2023.2.6 | 0.1 | 0.1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-933 | AES-6799 |  |  | ADP - Pipeline Refactoring 2023.2 | 53.8 | 53.8 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-934 | AES-6800 |  |  | ADP Pipeline Refactoring 2023.2.1 - Dave | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-935 | AES-6801 |  |  | ADP Pipeline Refactoring 2023.2.1 - Michael | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-936 | AES-6802 |  |  | ADP Pipeline Refactoring 2023.2.1 - Kevin | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-937 | AES-6803 |  |  | ADP Pipeline Refactoring 2023.2.1 - Daniel | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-938 | AES-6804 |  |  | ADP Pipeline Refactoring 2023.2.1 - David | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-939 | AES-6805 |  |  | ADP Pipeline Refactoring 2023.2.1 - Jordan | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-940 | AES-6806 |  |  | ADP Pipeline Refactoring 2023.2.1 - Phill | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-941 | AES-6807 |  |  | ADP Pipeline Refactoring 2023.2.6 - Phill | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-942 | AES-6808 |  |  | ADP Pipeline Refactoring 2023.2.5 - Phill | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-943 | AES-6809 |  |  | ADP Pipeline Refactoring 2023.2.4 - Phill | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-944 | AES-6810 |  |  | ADP Pipeline Refactoring 2023.2.6 - Daniel | 3.5 | 3.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-945 | AES-6811 |  |  | ADP Pipeline Refactoring 2023.2.5 - Daniel | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-946 | AES-6812 |  |  | ADP Pipeline Refactoring 2023.2.4 - Cristian | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-947 | AES-6813 |  |  | ADP Pipeline Refactoring 2023.2.3 - Daniel | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-948 | AES-6814 |  |  | ADP Pipeline Refactoring 2023.2.2 - Daniel | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-949 | AES-6815 |  |  | ADP Pipeline Refactoring 2023.2.6 - Dave | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-950 | AES-6816 |  |  | ADP Pipeline Refactoring 2023.2.5 - Dave | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-951 | AES-6817 |  |  | ADP Pipeline Refactoring 2023.2.4 - Dave | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-952 | AES-6818 |  |  | ADP Pipeline Refactoring 2023.2.3 - Dave | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-953 | AES-6819 |  |  | ADP Pipeline Refactoring 2023.2.2 - Dave | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-954 | AES-6820 |  |  | ADP Pipeline Refactoring 2023.2.6 - David | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-955 | AES-6821 |  |  | ADP Pipeline Refactoring 2023.2.5 - David | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-956 | AES-6822 |  |  | ADP Pipeline Refactoring 2023.2.4 - David | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-957 | AES-6823 |  |  | ADP Pipeline Refactoring 2023.2.3 - David | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-958 | AES-6824 |  |  | ADP Pipeline Refactoring 2023.2.2 - David | 0.3 | 0.3 | 0 | 100% | 2023-04-16 | 2023-04-18 |  |  | 3
|  |  | SPACE-959 | AES-6825 |  |  | ADP Pipeline Refactoring 2023.2.6 - Kevin | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-960 | AES-6826 |  |  | ADP Pipeline Refactoring 2023.2.5 - Kevin | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-961 | AES-6827 |  |  | ADP Pipeline Refactoring 2023.2.4 - Kevin | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-962 | AES-6828 |  |  | ADP Pipeline Refactoring 2023.2.3 - Kevin | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-963 | AES-6829 |  |  | ADP Pipeline Refactoring 2023.2.2 - Kevin | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-964 | AES-6830 |  |  | ADP Pipeline Refactoring 2023.2.6 - Michael | 5.5 | 5.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-965 | AES-6831 |  |  | ADP Pipeline Refactoring 2023.2.5 - Michael | 4.5 | 4.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-966 | AES-6832 |  |  | ADP Pipeline Refactoring 2023.2.4 - Michael | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-967 | AES-6833 |  |  | ADP Pipeline Refactoring 2023.2.3 - Michael | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-968 | AES-6834 |  |  | ADP Pipeline Refactoring 2023.2.2 - Michael | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-969 | AES-6835 |  |  | ADP Pipeline Refactoring 2023.2.6 - Jordan | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-970 | AES-6836 |  |  | ADP Pipeline Refactoring 2023.2.5 - Jordan | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-971 | AES-6837 |  |  | ADP Pipeline Refactoring 2023.2.4 - Jordan | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-972 | AES-6838 |  |  | ADP Pipeline Refactoring 2023.2.3 - Jordan | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-973 | AES-6839 |  |  | ADP Pipeline Refactoring 2023.2.2 - Jordan | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-974 | AES-6840 |  |  | ADP Pipeline Refactoring 2023.2.4 - Zac | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-975 | AES-6841 |  |  | ADP Pipeline Refactoring 2023.2.6 - Cristian | 1.5 | 1.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-976 | AES-6842 |  |  | ADP - Playbook Updates 2023.2 | 19 | 19 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-977 | AES-6843 |  |  | ADP Playbook Updates 2023.2.1 - Dave | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-978 | AES-6844 |  |  | ADP Playbook Updates 2023.2.1 - David | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-979 | AES-6845 |  |  | ADP Playbook Updates 2023.2.1 - Daniel | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-980 | AES-6846 |  |  | ADP Playbook Updates 2023.2.1 - Kevin | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-981 | AES-6847 |  |  | ADP Playbook Updates 2023.2.1 - Michael | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-982 | AES-6848 |  |  | ADP Playbook Updates 2023.2.1 - Shaun | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-983 | AES-6849 |  |  | ADP Playbook Updates 2023.2.1 - Calvin | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-984 | AES-6850 |  |  | ADP Playbook Updates 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-985 | AES-6851 |  |  | ADP Playbook Updates 2023.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-986 | AES-6852 |  |  | ADP Playbook Updates 2023.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-987 | AES-6853 |  |  | ADP Playbook Updates 2023.2.3 | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-988 | AES-6854 |  |  | ADP Playbook Updates 2023.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-989 | AES-6855 |  |  | ADP Playbook Updates 2023.2.1 - Bao | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-990 | AES-6856 |  |  | ADP Playbook Updates 2023.2.1 - Diane | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-991 | AES-6857 |  |  | ADP Playbook Updates 2023.2.2 - Bao | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-992 | AES-6858 |  |  | ADP Playbook Updates 2023.2.3 - Bao | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-993 | AES-6859 |  |  | ADP Playbook Updates 2023.2.4 - Bao | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-994 | AES-6860 |  |  | ADP Playbook Updates 2023.2.5 - Bao | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-995 | AES-6861 |  |  | ADP Playbook Updates 2023.2.6 - Bao | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-996 | AES-6862 |  |  | ADP Playbook Updates 2023.2.2 - Diane | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-997 | AES-6863 |  |  | ADP Playbook Updates 2023.2.3 - Diane | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-998 | AES-6864 |  |  | ADP Playbook Updates 2023.2.4 - Diane | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-999 | AES-6865 |  |  | ADP Playbook Updates 2023.2.5 - Diane | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1000 | AES-6866 |  |  | ADP Playbook Updates 2023.2.6 - Diane | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1001 | AES-6867 |  |  | Enablers - GSFA Program Deployment 2023.2 | 32.3 | 32.3 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-1002 | AES-6868 |  |  | CoWan (GSFA) Support/Consultation 2023.2.1 | 1.9 | 1.9 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1003 | AES-6869 |  |  | CoWan (GSFA) Support/Consultation 2023.2.2 | 2.5 | 2.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1004 | AES-6870 |  |  | CoWan (GSFA) Support/Consultation 2023.2.3 | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1005 | AES-6871 |  |  | CoWan (GSFA) Support/Consultation 2023.2.4 | 5 | 5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1006 | AES-6872 |  |  | CoWan (GSFA) Support/Consultation 2023.2.5 | 4.6 | 4.6 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1007 | AES-6873 |  |  | CoWan (GSFA) Support/Consultation 2023.2.6 | 2.3 | 2.3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1008 | AES-6874 |  |  | Cyber: GSFA IAT on VMWare - Carb Readiness after-action | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1009 | AES-6875 |  |  | Cyber: GSFA IAT on VMWare - Review Prod Ready Unclassified LMI Env | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-1010 | AES-6876 |  |  | Cyber: GSFA IAT unclassified controls Identification | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-11 |  |  | 3
|  |  | SPACE-1011 | AES-6877 |  |  | CoWan (GSFA) Support/Consultation 2023.2.6 - Zac | 6 | 6 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1012 | AES-6878 |  |  | CoWan (GSFA) Support/Consultation 2023.2.6 - Calvin | 4 | 4 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1013 | AES-6879 |  |  | Deployment Packaging 2023.2 | 53 | 53 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-1014 | AES-6880 |  |  | Deployment Packaging 2023.2.3 (Day 2 Deployment) | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1015 | AES-6881 |  |  | Deployment Packaging 2023.2.4 (Day 2 Deployment) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1016 | AES-6882 |  |  | Deployment Packaging 2023.2.5 (Day 2 Deployment) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1017 | AES-6883 |  |  | Deployment Packaging 2023.2.6 (Day 2 Deployment) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1018 | AES-6884 |  |  | Deployment Packaging 2023.2.3 (Day 2 Deployment) | 4 | 4 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1019 | AES-6885 |  |  | Deployment Packaging 2023.2.3 (Day 2 Deployment) | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1020 | AES-6886 |  |  | Deployment Packaging 2023.2.3 (Day 2 Deployment) | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1021 | AES-6887 |  |  | Deployment Packaging 2023.2.3 (Day 2 Deployment) | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1022 | AES-6888 |  |  | Deployment Packaging 2023.2.4 (Day 2 Deployment) | 4.5 | 4.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1023 | AES-6889 |  |  | Deployment Packaging 2023.2.4 (Day 2 Deployment) | 2.5 | 2.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1024 | AES-6890 |  |  | Deployment Packaging 2023.2.4 (Day 2 Deployment) | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1025 | AES-6891 |  |  | Deployment Packaging 2023.2.4 (Day 2 Deployment) | 4 | 4 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1026 | AES-6892 |  |  | Deployment Packaging 2023.2.5 (Day 2 Deployment) | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1027 | AES-6893 |  |  | Deployment Packaging 2023.2.5 (Day 2 Deployment) | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1028 | AES-6894 |  |  | Deployment Packaging 2023.2.5 (Day 2 Deployment) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1029 | AES-6895 |  |  | Deployment Packaging 2023.2.5 (Day 2 Deployment) | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-1030 | AES-6896 |  |  | Deployment Packaging 2023.2.6 (Day 2 Deployment) | 4 | 4 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1031 | AES-6897 |  |  | Deployment Packaging 2023.2.6 (Day 2 Deployment) | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1032 | AES-6898 |  |  | Deployment Packaging 2023.2.6 (Day 2 Deployment) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-1033 | AES-6899 |  |  | Deployment Packaging 2023.2.6 (Day 2 Deployment) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1034 | AES-6900 |  |  | Janus Graph -Horizonal Implementation of transfer-prepr for Syndeia | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1035 | AES-6901 |  |  | Deployment Packaging 2023.2.4 (Harbor Migration) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1036 | AES-6902 |  |  | Deployment Packaging 2023.2.4 (Harbor Migration) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1037 | AES-6903 |  |  | Deployment Packaging 2023.2.6 (Day 2 Deployment) - Cristian | 1.5 | 1.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1038 | AES-6904 |  |  | Enablers - NGI Program Post Deployment 2023.2 | 9 | 9 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-1039 | AES-6905 |  |  | Enablers - NGI Program Post Deployment 2023.2.3 - Dave | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1040 | AES-6906 |  |  | Enablers - NGI Program Post Deployment 2023.2.3 - David | 0 | 0 | 0 | 0% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1041 | AES-6907 |  |  | Enablers - NGI Program Post Deployment 2023.2.3 - Michael | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1042 | AES-6908 |  |  | Enablers - NGI Program Post Deployment 2023.2.3 - Daniel | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1043 | AES-6909 |  |  | Enablers - NGI Program Post Deployment 2023.2.3 - Kevin | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1044 | AES-6910 |  |  | Enablers - NGI Program Post Deployment 2023.2.4 - Dave | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-1045 | AES-6911 |  |  | Enablers - NGI Program Post Deployment 2023.2.5 - Dave | 0 | 0 | 0 | 0% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1046 | AES-6912 |  |  | Enablers - NGI Program Post Deployment 2023.2.4 - David | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1047 | AES-6913 |  |  | Enablers - NGI Program Post Deployment 2023.2.4 - Michael | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1048 | AES-6914 |  |  | Enablers - NGI Program Post Deployment 2023.2.4 - Daniel | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1049 | AES-6915 |  |  | Enablers - NGI Program Post Deployment 2023.2.4 - Kevin | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1050 |  |  |  | SLMX_MBE_ENGEF | 402 | 394 | 8 | 98.01% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232C.0005 | SPACE-1051 | AES-6916 | ONELMX_MBE_SSC | MBEDTU23CP | Spc MBE: Impl. Design Automation And Tool Updates - Cap Lab/NL | 96.75 | 96.75 | 0 | 100% | 2023-01-29 | 2023-06-26 | 2023-04-03 | 2023-06-23 | 1
|  |  | SPACE-1052 | AES-6917 |  |  | CAP: Tom Sawyer Perspectives | 7 | 7 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1053 | AES-6918 |  |  | [TSP General Release] Update TWC/TSP application | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1054 | AES-6919 |  |  | [General TSP Version Release] Debug the TSM Nodes and Edges with License server | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1055 | AES-6920 |  |  | [General TSP Release] Download TSP 10.2.1 and evaluate changes | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1056 | AES-6921 |  |  | [General TSP Release] Extra Time for debugging TWC/TSP | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1057 | AES-6922 |  |  | [General TSP Release] Extra Time for debugging Nodes and Edges | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1058 | AES-6923 |  |  | Test: Update TSP Performance Scripts | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-1059 | AES-6924 |  |  | Test: Run TSP Performance Tests | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-06-22 |  |  | 3
| 1.3.1.5 |  | SPACE-1060 | AES-6925 |  |  | CAP: Design Automation: Metrics Module PoC | 27 | 27 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1061 | AES-6926 |  |  | [MM] Create end user reports | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1062 | AES-6927 |  |  | [MM] Add Metrics capabilities to additional apps/functions pt.2 | 5 | 5 | 0 | 100% | 2023-05-14 | 2023-05-29 |  |  | 3
|  |  | SPACE-1063 | AES-6928 |  |  | [MM] Add Metrix to 3 more LMScripts applications | 5 | 5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1064 | AES-6929 |  |  | [MM] Add Metrics capabilities to additional apps/functions pt.1 | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-1065 | AES-6930 |  |  | [MM] Research database access between BAs (part 1) | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1066 | AES-6931 |  |  | [MM] Research database access between BAs (part 2) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1067 | AES-6932 |  |  | [MM] Add User ID to Metrix data | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1068 | AES-6933 |  |  | [MM] Add From and To dates on reports | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1069 | AES-6934 |  |  | [MM] Verification video | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-1070 | AES-6935 |  |  | [MM] Update/refresh LM Scripts repository | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-1071 | AES-6936 |  |  | [MM] Create Demo video for MM reporting | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
| 1.3.1.5 |  | SPACE-1072 | AES-6937 |  |  | CAP: Design Automation: Intelligent Assembly. App MVP Q2 | 49 | 49 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1073 | AES-6938 |  |  | [IA] Match hole UI - Intersecting parts table | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1074 | AES-6939 |  |  | [IA] User feedback incorporation 1 | 3.5 | 3.5 | 0 | 100% | 2023-04-02 | 2023-04-15 |  |  | 3
|  |  | SPACE-1075 | AES-6940 |  |  | [IA] Match hole - Created hole data structure | 5 | 5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1076 | AES-6941 |  |  | [IA] Match hole - location tracking pt. 1 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1077 | AES-6942 |  |  | [IA] Insert placement - UI development | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1078 | AES-6943 |  |  | [IA] Insert placement - hole data | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1079 | AES-6944 |  |  | [IA] Discussion on Maintenance | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1080 | AES-6945 |  |  | [IA] Develop new functionality based on user feedback | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1081 | AES-6946 |  |  | [IA] Deploy IA metrics to beta | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-1082 | AES-6947 |  |  | [IA] Initial Metrics capture | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-1083 | AES-6948 |  |  | Test: Develop Test Cases for Intelligent Assembly - 3 | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-1084 | AES-6949 |  |  | Test: Perform Intelligent Assembly Test Campaign | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1085 | AES-6950 |  |  | [IA] Match hole - location tracking pt. 2 | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1086 | AES-6951 |  |  | [IA] Matched hole location update | 5 | 5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1087 | AES-6952 |  |  | [Design Automation] Bug fix and comments | 1 | 1 | 0 | 100% | 2023-01-29 | 2023-05-15 |  |  | 3
|  |  | SPACE-1088 | AES-6953 |  |  | Test: Sikuli/Robot Exploratory Testing | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-1089 | AES-6954 |  |  | [IA] Testing, tweaking and release | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-1090 | AES-6955 |  |  | [IA] Cameo Model: V&V Reserve and General Clean UP | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1091 | AES-6956 |  |  | Importing Flag Notes - Confirmation Message | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1092 | AES-6957 |  |  | Should there be functionality to remove items under “Available Flag Notes” (like the flag note I was able to import in bug 9 above)? | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1093 | AES-6958 |  |  | Importing Flag Notes - Invalid JSON Entry | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1094 | AES-6959 |  |  | Importing Flag Notes - Closing IA Instructions Window | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1095 | AES-6960 |  |  | Removing Interface Definition - Multiple Component Selection | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1096 | AES-6961 |  |  | Confluence Article Linking in IA Windows | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1097 | AES-6962 |  |  | Add Interface Definition - Incorrect Labeling | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1098 | AES-6963 |  |  | Assembly Group Editing - Intermittent Incorrect Role Selection | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1099 | AES-6964 |  |  | Assembly Group Editing - Editing Placing Role to Undefined | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1100 | AES-6965 |  |  | Assembly Group Editing - Edit Placing Roles | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1101 | AES-6966 |  |  | [IA] Insert Placement - Assembly | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-1102 | AES-6967 |  |  | Assembly Group Editing - Editing Receiving Part | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
| 1.3.1.5 |  | SPACE-1103 | AES-6968 |  |  | CAP: Design Automation: Zuken E3 Script Updates Q2 | 7 | 7 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1104 | AES-6969 |  |  | Develop and Deploy Urgent Script Needs | 2.5 | 2.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1105 | AES-6970 |  |  | New Script Export and Deployment | 2.5 | 2.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1106 | AES-6971 |  |  | GitLab Implementation of Generate Wirelist Script | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
| 1.3.1.5 |  | SPACE-1107 | AES-6972 |  |  | CAP: Design Automation: LM Scripts Codebase Updates Q2 | 0 | 0 | 0 | 0% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1108 | AES-6973 |  |  | [LMScripts] ZonePairs feedback incoropration | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1109 | AES-6974 |  |  | CAP: SDM Adoption | 1.75 | 1.75 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-1110 | AES-6975 |  |  | Confirm Zemax ZDA file added as launch object type bug fix with new Zemax SME | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-1111 | AES-6976 |  |  | [SDM Adoption] Prework Steps | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1112 | AES-6977 |  |  | [SDM] ERB/CCB | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-1113 | AES-6978 |  |  | Wedge | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1114 | AES-6979 |  |  | Wedge | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1115 | AES-6980 |  |  | [SDM Adoption] Coordinate required App Licensing | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1116 | AES-6981 |  |  | [SDM Adoption] Locate Software | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1117 | AES-6982 |  |  | [SDM Adoption] RF Tool SDM CAE Manager integration | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1118 | AES-6983 |  |  | [SDM Adoption] Schema Design | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1119 | AES-6984 |  |  | [SDM Adoption] Branch the SDM schema off of Dev | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1120 | AES-6985 |  |  | [SDM Adoption] Modify Github files | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1121 | AES-6986 |  |  | Deployment to Dev | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1122 | AES-6987 |  |  | Install needed software (RF Tool) to the Dev Environment | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1123 | AES-6988 |  |  | Install the github package to Dev | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1124 | AES-6989 |  |  | Debug and modify schema for found bugs | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1125 | AES-6990 |  |  | Merge branch into Dev | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1126 | AES-6991 |  |  | Deployment to QAS | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1127 | AES-6992 |  |  | Install needed software to the QAS client pointing environment | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1128 | AES-6993 |  |  | Install the github package to QAS | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1129 | AES-6994 |  |  | Run UAT. Collect found bugs / change requests | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1130 | AES-6995 |  |  | Update schema and cycle through Dev back to QAS. | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1131 | AES-6996 |  |  | Deployment to Production | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1132 | AES-6997 |  |  | Install needed software to the Production Environment | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1133 | AES-6998 |  |  | Install the github package to Production | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1134 | AES-6999 |  |  | On acceptance of ORR begin merge of branch into Prod via approval process | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1135 | AES-7000 |  |  | Update client information to include needed tools | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1136 | AES-7001 |  |  | Prep for UAT | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1137 | AES-7002 |  |  | Prep for ORR | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1138 | AES-7003 |  |  | [SDM Adoption] Reserve Donna House for UAT Efforts | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1139 | AES-7004 |  |  | [SDM Adoption] SME Collects samples and use cases : One card per tool! | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1140 | AES-7005 |  |  | [SDM Adoption] Meetings with SME for system design | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1141 | AES-7006 |  |  | CAP: Engineering Efficiency 23.2 Generic Tasks | 5 | 5 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1142 | AES-7007 |  |  | Wedge for Innovation Week | 5 | 5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.232E.0008 | SPACE-1143 | AES-7008 | ONELMX_MBE_SSC | MBEDTU23 | Spc MBE: Req. and Rel. Design Auto. and Tool Updates - EXP Lab/NL | 305.25 | 297.25 | 8 | 97.38% | 2023-04-02 |  | 2023-04-03 | 2023-06-23 | 1
|  |  | SPACE-1144 | AES-7009 |  |  | EXP: Tom Sawyer Perspectives | 50.5 | 42.5 | 8 | 84.16% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1145 | AES-7010 |  |  | [General TSP Version Release] Confer with Cyber/Mini Cyber Cycle | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-1146 | AES-7011 |  |  | [General TSP Version Release] Test Execution | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-07-17 |  |  | 3
|  |  | SPACE-1147 | AES-7012 |  |  | [General TSP Version Release] Get up to speed on status of current SEIT | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-1148 | AES-7013 |  |  | [General TSP Version Release] Peer review V&V artifacts | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1149 | AES-7014 |  |  | [General TSP Version Release] Publish Webify Updates (if applicable) | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1150 | AES-7015 |  |  | [General TSP Version Release] Verification/Validation artifacts (in Zephyr) | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1151 | AES-7016 |  |  | [General TSP Version Release] V&V Activities | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1152 | AES-7017 |  |  | [General TSP Version Release] Start Test Execution | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1153 | AES-7018 |  |  | [General TSP Release] Documentation updates | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-17 |  |  | 3
|  |  | SPACE-1154 | AES-7019 |  |  | [General TSP Perspectives Release] Notify Stakeholders about new release | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-17 |  |  | 3
|  |  | SPACE-1155 | AES-7020 |  |  | [General TSP Release] Blocker placeholder for Documentation Updates | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1156 | AES-7021 |  |  | [General TSP Update] Cyber Blockers | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1157 | AES-7022 |  |  | [General TSP Update] License Server Blocker Placeholder | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-06-08 |  |  | 3
|  |  | SPACE-1158 | AES-7023 |  |  | [General TSP Release] Ticket Communication with TSP | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1159 | AES-7024 |  |  | [General TSP Release] Help Complete cyber checklist requirements | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1160 | AES-7025 |  |  | [General TSP Version Release] Gather security updates from TSP team for February release | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-15 |  |  | 3
|  |  | SPACE-1161 | AES-7026 |  |  | [General TSP Version Release] Cyber Scan Reviews | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-11 |  |  | 3
|  |  | SPACE-1162 | AES-7027 |  |  | Cyber: TSP - Investigate Dynamic asynchronous and periodic Password management | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-1163 | AES-7028 |  |  | Cyber: TSP TWC 10.2.1 (Pipeline, Vulns, POAM’s, Deployment, Threat Model Review, Checklist Update) | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-1164 | AES-7029 |  |  | Cyber: TSP Nodes/Edges 10.2.1 (Pipeline, Vulns, POAM’s, Deployment, Threat Model Review, Checklist Update) | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-1165 | AES-7030 |  |  | Cyber: TSP Standalone Client (Pipeline, Vulns, POAM’s, Deployment, Threat Model Review, Checklist Update) | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-1166 | AES-7031 |  |  | Cyber: TSP License Server - Cyber review of Deployment to Openstack (VM running Docker) | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-22 |  |  | 3
|  |  | SPACE-1167 | AES-7032 |  |  | [General TSP Release] Provide Packaging Information to Tools Team | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1168 | AES-7033 |  |  | [TSP General Release] Update TWC/TSP application Part 2 | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-1169 | AES-7034 |  |  | [General TSP Release] Provide Packaging Information to Tools Team Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1170 | AES-7035 |  |  | Cyber: TSP Burpsuite targeted sec testing | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-17 |  |  | 3
|  |  | SPACE-1171 | AES-7036 |  |  | [General TSP Release] Provide Packaging Information to Tools Team Part 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1172 | AES-7037 |  |  | [General Version TSP Release] Aid Cyrus in making TSP TWC deployed in QAS/PROD | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1173 | AES-7038 |  |  | [General TSP Update] Credit for work on Nodes and Edges and TWC/TSP app | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1174 | AES-7039 |  |  | Cyber: TSP Nodes/Edges 10.2.1 (Pipeline, Vulns, POAM’s, Deployment, Threat Model Review, Checklist Update) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1175 | AES-7040 |  |  | [General TSP Version Release] Nodes and Edges Upgrade Debugging (part 2) | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-1176 | AES-7041 |  |  | [Graph Generation something] Placeholder for Tools research of Creo and Zuken | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1177 | AES-7042 |  |  | [General TSP Version Release] Find path forward with Cyber team on TSP/TWC vulnerabilities | 4 | 4 | 0 | 100% | 2023-06-25 | 2023-07-17 |  |  | 3
|  |  | SPACE-1178 | AES-7043 |  |  | [General TSP Version Release] Update Documentation following ORR completed | 0.5 | 0.5 | 0 | 100% | 2023-06-25 | 2023-07-24 |  |  | 3
|  |  | SPACE-1179 | AES-7044 |  |  | [TSP] Re-run scans on 11.0 tsp/twc | 1.5 | 1.5 | 0 | 100% | 2023-06-25 | 2023-07-06 |  |  | 3
|  |  | SPACE-1180 | AES-7045 |  |  | [TSP General Release] Support customers with problems/isntallation | 1 | 1 | 0 | 100% | 2023-06-25 | 2023-07-17 |  |  | 3
|  |  | SPACE-1181 | AES-7046 |  |  | Cyber: Path forward on TSP/TWC vulnerabilities | 2 | 0 | 2 | 0% | 2023-07-17 |  |  |  | 3
|  |  | SPACE-1182 | AES-7047 |  |  | Cyber: TSP updated documentation cyber review and support | 2 | 0 | 2 | 0% |  |  |  |  | 3
|  |  | SPACE-1183 | AES-7048 |  |  | Cyber: TSP TWC and TSP Node & Edges 11.0 Vulnerabilities (Pipelines) | 1 | 1 | 0 | 100% | 2023-06-25 | 2023-07-13 |  |  | 3
|  |  | SPACE-1184 | AES-7049 |  |  | [General TSP Version Release] Test Execution Part 2 | 1 | 0 | 1 | 0% | 2023-07-16 |  |  |  | 3
|  |  | SPACE-1185 | AES-7050 |  |  | [General TSP Version Release] Find path forward with Cyber team on TSP/TWC vulnerabilities Part 2 | 2 | 0 | 2 | 0% | 2023-07-16 |  |  |  | 3
|  |  | SPACE-1186 | AES-7051 |  |  | [TSP General Release] Support customers with problems/isntallation Part 2 | 1 | 0 | 1 | 0% | 2023-07-16 |  |  |  | 3
| 1.3.1.5 |  | SPACE-1187 | AES-7052 |  |  | EXP: QIF File Publishing | 11 | 11 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1188 | AES-7053 |  |  | Learn more about other QIF solutions under development. | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1189 | AES-7054 |  |  | Verify if LMScripts licensing scheme is viable for server-side QIF | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-18 |  |  | 3
|  |  | SPACE-1190 | AES-7055 |  |  | Summarize and document current findings for integrated QIF | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1191 | AES-7056 |  |  | QIF local installation and evaluation. | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-25 |  |  | 3
|  |  | SPACE-1192 | AES-7057 |  |  | QIF local installation and evaluation Part 2 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1193 | AES-7058 |  |  | QIF local installation and evaluation Part 3 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-29 |  |  | 3
| 1.3.1.5 |  | SPACE-1194 | AES-7059 |  |  | EXP: ECAD-MCAD: Zuken E3 Harness Library Q2 | 19 | 19 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1195 | AES-7060 |  |  | Overbraid Library Automation Script | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-1196 | AES-7061 |  |  | Establish Cost Savings Documentation for Library Part Creation | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1197 | AES-7062 |  |  | Bring Library Cost Savings Data to ROMB board | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-1198 | AES-7063 |  |  | Format D Size Sheet 1- 2023 | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-05-03 |  |  | 3
|  |  | SPACE-1199 | AES-7064 |  |  | Update D3999 Connectors with correct polarization- Per Creo Library | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-1200 | AES-7065 |  |  | Update D38999 For Polarization Pt. 2 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1201 | AES-7066 |  |  | Format Sheet E Continuation - 2023 | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
|  |  | SPACE-1202 | AES-7067 |  |  | Symbol Verification task Continued | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1203 | AES-7068 |  |  | Format Sheet D Continuation- 2023 | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1204 | AES-7069 |  |  | Hide outdated cables - Cable Component Task 5 | 1.5 | 1.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-1205 | AES-7070 |  |  | Symbol Verification Task Pt. 2 | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1206 | AES-7071 |  |  | Symbol Verification Task Pt. 3 | 1.5 | 1.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-1207 | AES-7072 |  |  | Format Template Sheet E Sheet 1 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
| 1.3.1.5 |  | SPACE-1208 | AES-7073 |  |  | EXP: Design Automation: Metrics Module PoC | 53.5 | 53.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1209 | AES-7074 |  |  | [MM] Cameo Model: Operational Processes (Logical Use Case) | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1210 | AES-7075 |  |  | [MM] Cameo Model: Finalize Operational Process /Req/Verification Diagrams | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-1211 | AES-7076 |  |  | [MM] Cameo Model: Peer Review Use Cases and Requirements | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1212 | AES-7077 |  |  | [MM] Cameo Model: Peer Review and Update Logical Diagrams | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1213 | AES-7078 |  |  | [MM] Cameo Model: Continue V&V Activities | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1214 | AES-7079 |  |  | [MM] Cameo Model: Peer Review and Update V&V Diagrams | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-1215 | AES-7080 |  |  | [MM] Cameo Model: V&V Activities | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-1216 | AES-7081 |  |  | [MM] Cameo Model: Publish All Updates to Webify | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-05-31 |  |  | 3
|  |  | SPACE-1217 | AES-7082 |  |  | Use Cases for Metrics Module | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1218 | AES-7083 |  |  | [MM] Learn about Metrics Module | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1219 | AES-7084 |  |  | [MM] Cameo Model: Logical | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1220 | AES-7085 |  |  | [MM] Cameo Model: V&V Reserve and General Clean Up | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-1221 | AES-7086 |  |  | [MM] Cameo Model: Peer Review Any Outstanding or Updated Artifacts | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1222 | AES-7087 |  |  | [MM] Understand MM capability and features for SEIT work | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-1223 | AES-7088 |  |  | [MM] BETA release | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-1224 | AES-7089 |  |  | [MM] Create data flow documentation for Metrix/logging | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-1225 | AES-7090 |  |  | [MM] Create object model documentation for Metrix/Logging | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-1226 | AES-7091 |  |  | [MM] Create Metrix data documentation | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1227 | AES-7092 |  |  | [MM] Review results of BETA rollout | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1228 | AES-7093 |  |  | [MM] Cameo Model: Requirements and Verification View | 4 | 4 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1229 | AES-7094 |  |  | [MM] Develop / Modify Verification Success Criteria | 2.5 | 2.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1230 | AES-7095 |  |  | [MM] Cameo Model: Actual Resources (Deployment) | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1231 | AES-7096 |  |  | [MM] Host ORR | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1232 | AES-7097 |  |  | [MM] Confer with Cyber | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-1233 | AES-7098 |  |  | [MM] Cameo Model: Physical | 4 | 4 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1234 | AES-7099 |  |  | [MM] Cameo Model: Peer Review and Update Physical Diagrams | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1235 | AES-7100 |  |  | [MM] Metrics Module Familiarity & SEIT Competency Development | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1236 | AES-7101 |  |  | Requirements Verification & Resource Diagram Review Support & SEIT Competency Development | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1237 | AES-7102 |  |  | [MM] Verify SEIT Tasks are Closed | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-1238 | AES-7103 |  |  | [MM] Verify SEIT Tasks are Closed | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
| 1.3.1.5 |  | SPACE-1239 | AES-7104 |  |  | EXP: Design Automation: Intelligent Assembly. App MVP Q2 | 32.5 | 32.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1240 | AES-7105 |  |  | [IA] Cameo Model: Operational Processes (Logical Use Case) | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1241 | AES-7106 |  |  | [IA] Cameo Model: Requirements and Verification View | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1242 | AES-7107 |  |  | [IA] Cameo Model: Finalize Operational Process /Req Diagrams | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1243 | AES-7108 |  |  | [IA] Cameo Modeling: Logical | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1244 | AES-7109 |  |  | [IA] Peer Review Use Cases and Requirements | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1245 | AES-7110 |  |  | [IA] Cameo Model: Begin V&V Modeling | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1246 | AES-7111 |  |  | [IA] Cameo Model: Physical | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1247 | AES-7112 |  |  | [IA] Cameo Model: Peer Review and Update Logical Diagrams | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1248 | AES-7113 |  |  | [IA] Cameo Model: Continue V&V Activities | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1249 | AES-7114 |  |  | [IA] Cameo Model: Peer Review and Update Physical Diagrams | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1250 | AES-7115 |  |  | [IA] Cameo Model: Peer Review and Update V&V Diagrams | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1251 | AES-7116 |  |  | [IA] Cameo Model: Finish V&V Activities | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1252 | AES-7117 |  |  | [IA] Cameo Model: Peer Review and Update V&V Artifacts | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1253 | AES-7118 |  |  | [IA] Cameo Model: Publish All Updates to Webify | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1254 | AES-7119 |  |  | [IA] Cameo Model: Peer Review Any Outstanding or Updated Artifacts | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1255 | AES-7120 |  |  | [IA] Cameo Model: Logical and Physical (Begin) | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1256 | AES-7121 |  |  | [IA] Confer with Cyber | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1257 | AES-7122 |  |  | [IA] Confer with Cyber | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1258 | AES-7123 |  |  | [IA] Get Sam up to speed on state of IA modeling in Cameo | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-1259 | AES-7124 |  |  | Test: Determine How To Test Intelligent Assembly - 1 | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-1260 | AES-7125 |  |  | Test: Explore tools for Automated Testing of Intelligent Assembly | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-1261 | AES-7126 |  |  | [IA] Investigate Unproduced Video Clip: First Experience | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
| 1.3.1.5 |  | SPACE-1262 | AES-7127 |  |  | EXP: Assembly MBD Standard Q2 | 0.5 | 0.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1263 | AES-7128 |  |  | Coordinate Future Need and Support Pt. 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-09 |  |  | 3
| 1.3.1.5 |  | SPACE-1264 | AES-7129 |  |  | EXP: Design Automation: Zuken E3 Script Updates Q2 | 29.5 | 29.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1265 | AES-7130 |  |  | [Zuken E3] Generate Wirelist Script Updates - Part 1 | 6.5 | 6.5 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-1266 | AES-7131 |  |  | [Zuken E3] Document GitLab Standards | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1267 | AES-7132 |  |  | Generate Wirelist Script Updates - Part 3 | 7 | 7 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-1268 | AES-7133 |  |  | Generate Wirelist Script Updates - Part 4 | 4 | 4 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-1269 | AES-7134 |  |  | Generate Wirelist Script Updates - Part 5 | 5 | 5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1270 | AES-7135 |  |  | Zuken E3 Custom Script Updates - Part 6 | 6 | 6 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
| 1.3.1.5 |  | SPACE-1271 | AES-7136 |  |  | EXP: Design Automation: LM Scripts Codebase Updates Q2 | 1 | 1 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1272 | AES-7137 |  |  | [Design Automation] Winchill REST api implementation plan | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
| 1.3.1.5 |  | SPACE-1273 | AES-7138 |  |  | EXP: HEP FLT Support Q2 | 6 | 6 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1274 | AES-7139 |  |  | [HEP FLT] Support Sprint 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1275 | AES-7140 |  |  | [HEP FLT] Support Sprint 2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1276 | AES-7141 |  |  | [HEP FLT] Support Sprint 3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1277 | AES-7142 |  |  | [HEP FLT] Support Sprint 4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1278 | AES-7143 |  |  | [HEP FLT] Support Sprint 5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1279 | AES-7144 |  |  | [HEP FLT] Support Sprint 6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1280 | AES-7145 |  |  | EXP: SDM Adoption | 6 | 6 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-1281 | AES-7146 |  |  | Sync with STAT/UQ Team for RF Workflow Development | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1282 | AES-7147 |  |  | Wedge | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1283 | AES-7148 |  |  | Deploy to Production | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1284 | AES-7149 |  |  | Wedge | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1285 | AES-7150 |  |  | [SDM Adoption] Identify SME | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1286 | AES-7151 |  |  | [SDM Adoption] Increment Demo Prep | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1287 | AES-7152 |  |  | EXP: IAT Continued Development | 15.25 | 15.25 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1288 | AES-7153 |  |  | Support IAT Workflow Development/Adoption Discussions 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1289 | AES-7154 |  |  | Support IAT Workflow Development/Adoption Discussions 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-1290 | AES-7155 |  |  | Support IAT Workflow Development/Adoption Discussions 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-1291 | AES-7156 |  |  | [IAT] Support IAT Workflow Development/Adoption Discussions 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1292 | AES-7157 |  |  | [IAT] Support IAT Workflow Development/Adoption Discussions 5 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1293 | AES-7158 |  |  | [IAT] Vendor Tag Up 1 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1294 | AES-7159 |  |  | [IAT] Vendor Tag Up 2 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1295 | AES-7160 |  |  | [IAT] Vendor Tag Up 3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
|  |  | SPACE-1296 | AES-7161 |  |  | [IAT] Vendor Tag Up 4 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1297 | AES-7162 |  |  | [IAT] Vendor Tag Up 5 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1298 | AES-7163 |  |  | [IAT] Vendor Tag Up 6 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1299 | AES-7164 |  |  | [Workflow Dev] STOP Workflow Development 1 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-1300 | AES-7165 |  |  | [Workflow Dev] STOP Workflow Development 2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1301 | AES-7166 |  |  | [Workflow Dev] STOP Workflow Development 3 | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1302 | AES-7167 |  |  | [Workflow Dev] STOP Workflow Development 4 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1303 | AES-7168 |  |  | [Workflow Dev] STOP Workflow Development 5 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1304 | AES-7169 |  |  | [Workflow Dev] STOP Workflow Development 6 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-27 |  |  | 3
|  |  | SPACE-1305 | AES-7170 |  |  | Cyber: Volta Player - Local Web Server Concerns | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-23 |  |  | 3
| 1.3.1.5 |  | SPACE-1306 | AES-7171 |  |  | EXP: Q2 Creo EEE library updates | 9 | 9 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1307 | AES-7172 |  |  | Creo EEE Library Sprint 1: Team Tag Up | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-05 |  |  | 3
|  |  | SPACE-1308 | AES-7173 |  |  | Creo EEE Library Sprint 1: MCAD Standard Parts Guidebook updates | 0.75 | 0.75 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1309 | AES-7174 |  |  | Creo EEE Library Sprint 1: CAD Family Table updates | 0.75 | 0.75 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1310 | AES-7175 |  |  | Creo EEE Library Sprint 2: Team Tag Up | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-1311 | AES-7176 |  |  | Creo EEE Library Sprint 2: MCAD Standard Parts Guidebook updates | 0.75 | 0.75 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1312 | AES-7177 |  |  | Creo EEE Library Sprint 3: CAD Family Table updates | 0.75 | 0.75 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1313 | AES-7178 |  |  | Creo EEE Library Sprint 3: Team Tag Up | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1314 | AES-7179 |  |  | Creo EEE Library Sprint 3: MCAD Standard Parts Guidebook updates | 0.75 | 0.75 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1315 | AES-7180 |  |  | Creo EEE Library Sprint 4: CAD Family Table updates | 0.75 | 0.75 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1316 | AES-7181 |  |  | Creo EEE Library Sprint 4: Team Tag Up | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-1317 | AES-7182 |  |  | Creo EEE Library Sprint 4: MCAD Standard Parts Guidebook updates | 0.75 | 0.75 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1318 | AES-7183 |  |  | Creo EEE Library Sprint 5: MCAD Standard Parts Guidebook updates | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-1319 | AES-7184 |  |  | Creo EEE Library Sprint 6: MCAD Standard Parts Guidebook updates | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1320 | AES-7185 |  |  | Creo EEE Library Sprint 2: CAD Family Table updates | 0.75 | 0.75 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1321 | AES-7186 |  |  | EXP: Engineering Efficiency 23.2 Generic Tasks | 59.5 | 59.5 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1322 | AES-7187 |  |  | [Generic] STAT/UQ Coordination 1/MM Review | 1.5 | 1.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1323 | AES-7188 |  |  | [Generic] STAT/UQ Coordination 2 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1324 | AES-7189 |  |  | [Generic] STAT/UQ Coordination 3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-1325 | AES-7190 |  |  | [Generic] STAT/UQ Coordination 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-1326 | AES-7191 |  |  | [Generic] STAT/UQ Coordination 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1327 | AES-7192 |  |  | [Generic] STAT/UQ Coordination 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1328 | AES-7193 |  |  | [Generic] Program Adoption Support 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-1329 | AES-7194 |  |  | [Generic] Program Adoption Support 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1330 | AES-7195 |  |  | [Generic] Program Adoption Support 3 | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-1331 | AES-7196 |  |  | [Generic] Program Adoption Support 4 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-1332 | AES-7197 |  |  | [Generic] Program Adoption Support 5 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1333 | AES-7198 |  |  | [Generic] Program Adoption Support 6 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1334 | AES-7199 |  |  | [SEIT] Review SEIT tasks/methodology from last PI w/ SEIT team | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1335 | AES-7200 |  |  | [Generic] RFME IBD-RF SME Interface Investigation | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-27 |  |  | 3
|  |  | SPACE-1336 | AES-7201 |  |  | [Generic] RFME IBD-IBD Development | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-27 |  |  | 3
|  |  | SPACE-1337 | AES-7202 |  |  | [Generic] RFME IBD-ME SME Interface Investigation | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-27 |  |  | 3
|  |  | SPACE-1338 | AES-7203 |  |  | [Generic] RFEE IBD-RF SME Interface Investigation | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1339 | AES-7204 |  |  | [Generic] RFEE IBD-EE SME Interface Investigation | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1340 | AES-7205 |  |  | [Generic] RFEE IBD-POC/Stakeholder Review | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-06-21 |  |  | 3
|  |  | SPACE-1341 | AES-7206 |  |  | [Generic] RFGNC IBD-GNC SME Interface Investigation | 0.3 | 0.3 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1342 | AES-7207 |  |  | [Generic] RFGNC IBD-RF SME Interface Investigation | 0.3 | 0.3 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1343 | AES-7208 |  |  | [Generic] RFGNC IBD-Identify GNC SMEs | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1344 | AES-7209 |  |  | [Generic] RFGNC IBD-IBD Development | 2.5 | 2.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1345 | AES-7210 |  |  | [Generic] RFGNC IBD-POC/Stakeholder Review | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1346 | AES-7211 |  |  | [Generic] RFOP IBD-Identify OP SMEs | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1347 | AES-7212 |  |  | [Generic] RFOP IBD-RF SME Interface Investigation | 0.2 | 0.2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1348 | AES-7213 |  |  | [Generic] RFOP IBD-OP SME Interface Investigation | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-1349 | AES-7214 |  |  | [Generic] RFOP IBD-IBD Development | 1.2 | 1.2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1350 | AES-7215 |  |  | [Generic] RFOP IBD-POC/Stakeholder Review | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1351 | AES-7216 |  |  | [Generic] RFSW IBD-Identify SW SMEs | 0.2 | 0.2 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1352 | AES-7217 |  |  | [Generic] RFME IBD-Interface Investigation | 1.75 | 1.75 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-1353 | AES-7218 |  |  | [Generic] RFME IBD-SME/Stakeholder Review | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-06-21 |  |  | 3
|  |  | SPACE-1354 | AES-7219 |  |  | [Generic] RFGNC IBD-Interface Investigation | 1.75 | 1.75 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-1355 | AES-7220 |  |  | [Generic] RFOP IBD-Interface Investigation | 1.5 | 1.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1356 | AES-7221 |  |  | [Generic] RFSW IBD-Interface Investigation | 0.8 | 0.8 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1357 | AES-7222 |  |  | [Generic] RFSW IBD-Meet with RF SME | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1358 | AES-7223 |  |  | [Generic] RFSW IBD-SW SME Interface Investigation | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1359 | AES-7224 |  |  | [Generic] RFSW IBD-IBD Development | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1360 | AES-7225 |  |  | [Generic] RFSW IBD-POC/Stakeholder Review | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1361 | AES-7226 |  |  | [Generic] MESW IBD-Interface Investigation | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1362 | AES-7227 |  |  | [Generic] Determine Path Forward for Production Ready Capabilities | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1363 | AES-7228 |  |  | SEIT Requirements Refactoring | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1364 | AES-7229 |  |  | [Webify] Webify Prioritization with MBSE Lead (April Luczywek) | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1365 | AES-7230 |  |  | [Webify] Webify Demo | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1366 | AES-7231 |  |  | CAM Work Sprint 1 | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1367 | AES-7232 |  |  | CAM Work Sprint 2 | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1368 | AES-7233 |  |  | [Generic] RFEE IBD-IBD Completion | 2.5 | 2.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1369 | AES-7234 |  |  | Increment Demo | 5 | 5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-1370 | AES-7235 |  |  | SEIT Webify Updates | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1371 | AES-7236 |  |  | [SEIT] Webify Metrics Table Updates | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1372 | AES-7237 |  |  | [SEIT] SEIT Webify Updates | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1373 | AES-7238 |  |  | Run-Ahead Work for Webify | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-1374 | AES-7239 |  |  | EXP: Cameo to Zuken Integration | 3.5 | 3.5 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1375 | AES-7240 |  |  | [C2Z] Support Request from Stakeholders | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1376 | AES-7241 |  |  | [C2Z] Documentation of Use Cases and Need | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1377 | AES-7242 |  |  | [C2Z] Follow up on Stakeholder Responses | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1378 | AES-7243 |  |  | EXP: MCAD Command Media Final Review | 0.5 | 0.5 | 0 | 100% |  |  | 2023-03-27 | 2023-04-13 | 2
|  |  | SPACE-1379 | AES-7244 |  |  | [MCAD] SPD00044 Savant Feedback Revisions Placeholder | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1380 | AES-7245 |  |  | [Webify] Coordination with MBSE | 2 | 2 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-1381 | AES-7246 |  |  | Webify Demo to MBSE Core Team | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1382 | AES-7247 |  |  | [Harness Builder] Determine Ops. Eff. Blocker and Resolution | 4 | 4 | 0 | 100% |  |  | 2023-04-03 | 2023-06-22 | 2
|  |  | SPACE-1383 | AES-7248 |  |  | [Harness Builder] Engage with Harness Design SMEs | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-1384 | AES-7249 |  |  | Harness Work | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1385 | AES-7250 |  |  | EXP: Teamcenter Enhancements Q2 | 2 | 2 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-1386 | AES-7251 |  |  | [SDM IOC] Prioritize the need and determine priorities for these efforts | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1387 |  |  |  | SLMX_MBE_OPSEF | 210.5 | 210.5 | 0 | 100% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232E.0007 | SPACE-1388 | AES-7252 | ONELMX_MBE_SSC | MBEMBC23 | Spc MBE: Req. and Release MBC and Ops Efficiency - Exp Lab/NL | 201 | 201 | 0 | 100% | 2023-04-02 | 2023-06-28 | 2023-04-03 | 2023-06-23 | 1
| 1.3.1.5 |  | SPACE-1389 | AES-7253 |  |  | EXP: PolyWorks Inspector/DataLoop Support 23.2 | 8 | 8 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1390 | AES-7254 |  |  | SEIT Use Case | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1391 | AES-7255 |  |  | SEIT Physical Review | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1392 | AES-7256 |  |  | SEIT Logical Review | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1393 | AES-7257 |  |  | SEIT Logical (Polyworks) | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1394 | AES-7258 |  |  | Request Update of SW Center Polyworks Version | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1395 | AES-7259 |  |  | PLM Connector SW Procurement | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
| 1.3.1.5 |  | SPACE-1396 | AES-7260 |  |  | EXP: Initial Rollout of VWI to Michoud | 1.5 | 1.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1397 | AES-7261 |  |  | Identify Users (Michoud) | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1398 | AES-7262 |  |  | Deploy SW/Training | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
| 1.3.1.5 |  | SPACE-1399 | AES-7263 |  |  | EXP: Creo Illustrate/VWI Support 23.2 | 34 | 34 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1400 | AES-7264 |  |  | Creo Illustrate/VWI Support I1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1401 | AES-7265 |  |  | Creo Illustrate/VWI Support I2 | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1402 | AES-7266 |  |  | Creo Illustrate/VWI Support I3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1403 | AES-7267 |  |  | Creo Illustrate/VWI Support I4 | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1404 | AES-7268 |  |  | Creo Illustrate/VWI Support I5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1405 | AES-7269 |  |  | Creo Illustrate/VWI Support I6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1406 | AES-7270 |  |  | SEIT Logical Diagrams Part 1 | 4 | 4 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1407 | AES-7271 |  |  | SEIT Logical Review | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-1408 | AES-7272 |  |  | SEIT Physical Diagrams Part 1 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1409 | AES-7273 |  |  | SEIT Physical Review | 4 | 4 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1410 | AES-7274 |  |  | SEIT Use Case | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1411 | AES-7275 |  |  | SEIT Logical Part 2 | 4 | 4 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-1412 | AES-7276 |  |  | SEIT Physical Part 2 | 6 | 6 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1413 | AES-7277 |  |  | Creo Illustrate Capability Catalog | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1414 | AES-7278 |  |  | SEIT Modify Logical Diagrams | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
|  |  | SPACE-1415 | AES-7279 |  |  | VWI Use Case(s) | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1416 | AES-7280 |  |  | Determine Level of User Adoption | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1417 | AES-7281 |  |  | Facilitate obtaining and tracking feedback on VWI | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
| 1.3.1.5 |  | SPACE-1418 | AES-7282 |  |  | EXP: Optimize EBOM -->MBOM Release 2 | 11 | 11 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-1419 | AES-7283 |  |  | Get Engineering Cost Upper Data Part 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-1420 | AES-7284 |  |  | Get Pros/Cons from Engineering | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1421 | AES-7285 |  |  | Edit Business Case Presentation | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1422 | AES-7286 |  |  | Placeholder | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1423 | AES-7287 |  |  | Placeholder | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1424 | AES-7288 |  |  | SEIT Investigation for BOM Conversion | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-1425 | AES-7289 |  |  | Spin-Up on EBOM/MBOM Conversion | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1426 | AES-7290 |  |  | EBOM/MBOM ROI investigation Part 1 | 4 | 4 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1427 | AES-7291 |  |  | eBOM to mBOM process investigation (Current State) | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1428 | AES-7292 |  |  | EXP: Process Plan and VWI MPMLink Evaluation Deep Dive | 27 | 27 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-1429 | AES-7293 |  |  | Develop Troubleshooting List | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1430 | AES-7294 |  |  | Follow Up on Opening CAD Visualization Ticket with PTC | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-05 |  |  | 3
|  |  | SPACE-1431 | AES-7295 |  |  | Prepare Outbrief for 23.1 Findings | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-18 |  |  | 3
|  |  | SPACE-1432 | AES-7296 |  |  | Demo Follow On Actions | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1433 | AES-7297 |  |  | WG Facilitation & Support Iteration 4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-1434 | AES-7298 |  |  | WG Facilitation & Support Iteration 5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1435 | AES-7299 |  |  | Troubleshooting List Execution | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1436 | AES-7300 |  |  | Troubleshooting List Execution | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-1437 | AES-7301 |  |  | Troubleshooting List Execution | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1438 | AES-7302 |  |  | CAD Visualization | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1439 | AES-7303 |  |  | Document VWI Limitations | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-1440 | AES-7304 |  |  | Completion of MPMLink Punch List Updates | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-18 |  |  | 3
|  |  | SPACE-1441 | AES-7305 |  |  | SEIT Use Cases | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1442 | AES-7306 |  |  | SEIT Logical | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1443 | AES-7307 |  |  | SEIT Logical Review | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1444 | AES-7308 |  |  | SEIT Physical | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-12 |  |  | 3
|  |  | SPACE-1445 | AES-7309 |  |  | SEIT Physical Review | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1446 | AES-7310 |  |  | Create VWI in MPMLink | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1447 | AES-7311 |  |  | Present Outbrief on 23.1 Findings | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-1448 | AES-7312 |  |  | EXP: Initial Rollout of VWI to MMC/Sunnyvale | 1.5 | 1.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-1449 | AES-7313 |  |  | Deploy SW/Training | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1450 | AES-7314 |  |  | Identify Users | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-1451 | AES-7315 |  |  | EXP: Polyworks Dataloop Computed Tomography Potential Integration | 1 | 1 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1452 | AES-7316 |  |  | Investigate Integration of Poly/Tomo | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1453 | AES-7317 |  |  | EXP: Harness Builder in Standardization | 5.5 | 5.5 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1454 | AES-7318 |  |  | HB Standard Install Placeholder 2 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1455 | AES-7319 |  |  | HB Standard Install Planning | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1456 | AES-7320 |  |  | Engage Engineering Tools Board | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-1457 | AES-7321 |  |  | Engineering Adoption 1 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-29 |  |  | 3
|  |  | SPACE-1458 | AES-7322 |  |  | Engineering Adoption | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1459 | AES-7323 |  |  | HB BDX Entry | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1460 | AES-7324 |  |  | HB Awareness Campaign | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-03 |  |  | 3
|  |  | SPACE-1461 | AES-7325 |  |  | EXP: Harness Builder Support 23.2 | 16.5 | 16.5 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1462 | AES-7326 |  |  | Skills&Eng Alliance Presentation | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-03 |  |  | 3
|  |  | SPACE-1463 | AES-7327 |  |  | Courtland Testing Investigation | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-1464 | AES-7328 |  |  | Denver Testing Investigation 2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-1465 | AES-7329 |  |  | SEIT Physical Diagram Creation | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1466 | AES-7330 |  |  | SEIT Physical Review (HB) | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1467 | AES-7331 |  |  | Denver Testing Investigation 3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1468 | AES-7332 |  |  | Build new HB Test Design 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-1469 | AES-7333 |  |  | Build New HB Test Design 2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1470 | AES-7334 |  |  | Test using New Design | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-06-12 |  |  | 3
|  |  | SPACE-1471 | AES-7335 |  |  | NETS testing DTMCO | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1472 | AES-7336 |  |  | Training Preparation for Courtland | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1473 | AES-7337 |  |  | Financial Impact Investigation Groundwork | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1474 | AES-7338 |  |  | Coordinate Training with Courtland | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1475 | AES-7339 |  |  | Engineering Impediment Support | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1476 | AES-7340 |  |  | Facilitate Nova Move to Courtland | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1477 | AES-7341 |  |  | Mastercam Adoption to LM Space Machine Shops | 26.5 | 26.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-1478 | AES-7342 |  |  | Valley Forge Gap Analysis Machinist Centric | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1479 | AES-7343 |  |  | Valley Forge Gap Analysis - CNC User-Centric | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1480 | AES-7344 |  |  | Request Mastercam Licenses | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1481 | AES-7345 |  |  | Return Legacy Mastercam Licenses | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1482 | AES-7346 |  |  | Mastercam Tools Board Investigation | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1483 | AES-7347 |  |  | Open BDX Entry for CDS | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1484 | AES-7348 |  |  | Provide Training to CDS | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1485 | AES-7349 |  |  | Valley Forge Engagment | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1486 | AES-7350 |  |  | Identify Users Valley Forge | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-1487 | AES-7351 |  |  | Open BDX Entry for Valley Forge | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1488 | AES-7352 |  |  | Provide Demo to Valley Forge | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-06-27 |  |  | 3
|  |  | SPACE-1489 | AES-7353 |  |  | Engage Leadership at Valley Forge | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1490 | AES-7354 |  |  | Open BDX Entry SVL | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1491 | AES-7355 |  |  | Identify all Mastercam users | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1492 | AES-7356 |  |  | Open BDX Entry for PDC | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1493 | AES-7357 |  |  | Submit BDX Package for Validation - CDS | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-05-30 |  |  | 3
|  |  | SPACE-1494 | AES-7358 |  |  | Submit BDX Package for Validation - PDC | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-05-30 |  |  | 3
|  |  | SPACE-1495 | AES-7359 |  |  | Confirm SWz installed SVL | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1496 | AES-7360 |  |  | Provide SWz Training to SVL | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-06-27 |  |  | 3
|  |  | SPACE-1497 | AES-7361 |  |  | Submit BDX Package for Validation - SVL | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-1498 | AES-7362 |  |  | Identify SWz Stakeholders at Stennis | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1499 | AES-7363 |  |  | Provide SWz Demo to Stennis | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1500 | AES-7364 |  |  | Open BDX Entry for Stennis | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-1501 | AES-7365 |  |  | Identify SWz Users at Stennis | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-1502 | AES-7366 |  |  | Confirm SWz installed Stennis | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1503 | AES-7367 |  |  | Provide SWz Training Stennis | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1504 | AES-7368 |  |  | Submit BDX Package for Validation - Stennis | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-28 |  |  | 3
|  |  | SPACE-1505 | AES-7369 |  |  | Valley Forge Gap Analysis Supervision-Centric | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1506 | AES-7370 |  |  | Engage SVL in Preparation for Training | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-05-30 |  |  | 3
|  |  | SPACE-1507 | AES-7371 |  |  | Determine if Valley Forge should adopt MasterCam | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1508 | AES-7372 |  |  | SVL and CDS Mastercam File Support | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1509 | AES-7373 |  |  | Agile Support | 14 | 14 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1510 | AES-7374 |  |  | Run Ahead Planning for 23.3 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1511 | AES-7375 |  |  | Run Ahead Planning for 23.3 (2) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1512 | AES-7376 |  |  | Run Ahead Planning for 23.3 (3) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1513 | AES-7377 |  |  | Run Ahead Planning for 23.3 (4) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1514 | AES-7378 |  |  | Run Ahead Planning for 23.3 (5) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1515 | AES-7379 |  |  | Run Ahead Planning for 23.3 (6) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1516 | AES-7380 |  |  | ROMB Support (1) | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1517 | AES-7381 |  |  | ROMB Support (2) | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1518 | AES-7382 |  |  | ROMB Support (3) | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1519 | AES-7383 |  |  | ROMB Support (4) | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1520 | AES-7384 |  |  | ROMB Support (5) | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1521 | AES-7385 |  |  | ROMB Support (6) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1522 | AES-7386 |  |  | Mastercam Startup Wizard Handoff tasks | 4 | 4 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1523 | AES-7387 |  |  | Flatten Reqs 2 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1524 | AES-7388 |  |  | Misc Support | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1525 | AES-7389 |  |  | SEIT Modeling | 14 | 14 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1526 | AES-7390 |  |  | Modeling Support 2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1527 | AES-7391 |  |  | Modeling Support 3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1528 | AES-7392 |  |  | Modeling Support 4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1529 | AES-7393 |  |  | Modeling Support 5 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-1530 | AES-7394 |  |  | Modeling Support 1 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1531 | AES-7395 |  |  | Flatten Reqs 1 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-1532 | AES-7396 |  |  | Determine Logical Modeling Strategy | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1533 | AES-7397 |  |  | OpsEf Process Model | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1534 | AES-7398 |  |  | OpsEf Process Model Complete | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1535 | AES-7399 |  |  | AR Develop Scenes | 3 | 3 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1536 | AES-7400 |  |  | SEC Box AR | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1537 | AES-7401 |  |  | AR Scene Development | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1538 | AES-7402 |  |  | AR Determine Alignment and D-Thread | 3 | 3 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1539 | AES-7403 |  |  | AR Requirements/Trades between Worklink and Vuforia | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1540 | AES-7404 |  |  | SEIT Strategy Investigation AR | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1541 | AES-7405 |  |  | DTECTX Deploy to Waterton | 22.5 | 22.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-1542 | AES-7406 |  |  | DTECTX SW Procurement Request | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1543 | AES-7407 |  |  | SEIT Strategy for DTECTX | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1544 | AES-7408 |  |  | SEIT Logical Diagrams DTECTX | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1545 | AES-7409 |  |  | SEIT Modeling Physical Diagrams for DTECTX | 6 | 6 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1546 | AES-7410 |  |  | DTECTX Deployed to Waterton | 4 | 4 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1547 | AES-7411 |  |  | DTECTX Stakeholder Engagement | 4 | 4 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1548 | AES-7412 |  |  | DTECTX SW Install | 4 | 4 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1549 | AES-7413 |  |  | DTECTX Adoption | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1550 | AES-7414 |  |  | DCT SPC to Waterton Support | 11 | 11 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1551 | AES-7415 |  |  | SEIT Strategy for DCT SPC | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1552 | AES-7416 |  |  | SPC Physical Diagrams | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1553 | AES-7417 |  |  | DCT SPC Hosting 1 | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1554 | AES-7418 |  |  | Determine SPC/1LMX Alignment | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1555 | AES-7419 |  |  | HW/SW PR Process Understanding | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1556 | AES-7420 |  |  | DCT SPC Architecture Documentation | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1557 | AES-7421 |  |  | DCT SPC: PR/PO process defined & understood | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1558 | AES-7422 |  |  | Determine path to move forward w/larger SPC trade study | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1559 | AES-7423 |  |  | SPC Requirements Discussion | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1560 | AES-7424 |  |  | Deliver MBT Standard Model | 1 | 1 | 0 | 100% |  |  | 2023-05-29 | 2023-06-25 | 2
|  |  | SPACE-1561 | AES-7425 |  |  | Deliver MBT Standard Model WEDGE 1 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1562 | AES-7426 |  |  | Deliver MBT Standard Model WEDGE 2 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.231E.0047 | SPACE-1563 | AES-7427 | ONELMX_MBE_SSC | MBEMBC23 | Space MBC Ops Eff Polyworks Expanded Deployment - Expense | 9.5 | 9.5 | 0 | 100% | 2023-01-01 | 2023-02-27 | 2023-01-03 | 2023-06-25 | 1
|  |  | SPACE-1564 | AES-7428 |  |  | MBC: Polyworks (Inspector/DataLoop) Expansion | 9.5 | 9.5 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-1565 | AES-7429 |  |  | Invite KSC into onsite Polyworks license pool | 1 | 1 | 0 | 100% | 2023-01-29 | 2023-02-13 |  |  | 3
|  |  | SPACE-1566 | AES-7430 |  |  | Create common Polyworks template for panels | 1 | 1 | 0 | 100% | 2023-01-29 | 2023-02-02 |  |  | 3
|  |  | SPACE-1567 | AES-7431 |  |  | Deploy common Polyworks template for panels | 1 | 1 | 0 | 100% | 2023-01-29 | 2023-02-13 |  |  | 3
|  |  | SPACE-1568 | AES-7432 |  |  | Deploy & Demonstrate Polyworks at SVL | 1 | 1 | 0 | 100% | 2023-01-01 | 2023-01-12 |  |  | 3
|  |  | SPACE-1569 | AES-7433 |  |  | Initial engagement with Courtland on Polyworks capability | 1 | 1 | 0 | 100% | 2023-01-29 | 2023-02-13 |  |  | 3
|  |  | SPACE-1570 | AES-7434 |  |  | Determine Modeling Approach | 2 | 2 | 0 | 100% | 2023-01-29 | 2023-02-08 |  |  | 3
|  |  | SPACE-1571 | AES-7435 |  |  | Investigate Polyworks ILT Training for KSC | 1 | 1 | 0 | 100% | 2023-01-29 | 2023-02-09 |  |  | 3
|  |  | SPACE-1572 | AES-7436 |  |  | Identify KSC Training POC | 0.5 | 0.5 | 0 | 100% | 2023-02-12 | 2023-02-20 |  |  | 3
|  |  | SPACE-1573 | AES-7437 |  |  | Engage KSC Training POC | 1 | 1 | 0 | 100% | 2023-02-12 | 2023-02-27 |  |  | 3
|  |  | SPACE-1574 |  |  |  | SLMX_MBE_PMO | 129 | 129 | 0 | 100% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-1575 | AES-7438 | ONELMX_MBE_SSC | MBE23LOE | Spc MBE: PMO LOE 23.2 - Exp - Lab/NL | 129 | 129 | 0 | 100% | 2023-04-02 | 2023-06-26 | 2023-03-27 | 2023-06-23 | 1
|  |  | SPACE-1576 | AES-7439 |  |  | 23.2 SMBE Engagements (LOE) | 26.5 | 26.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1577 | AES-7440 |  |  | Overview for E&T IOR April '23 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1578 | AES-7441 |  |  | Overview for E&T IOR - May '23 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-1579 | AES-7442 |  |  | Overview for E&T IOR - June '23 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1580 | AES-7443 |  |  | Start Initial Discovery into NGI and lack of SDM adoption | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1581 | AES-7444 |  |  | Conduct 23.1 Increment demos | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-1582 | AES-7445 |  |  | Logistics and Prep for SMBE 23.1 Increment demos | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-1583 | AES-7446 |  |  | MBE MFO/LOB Engagement | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1584 | AES-7447 |  |  | MBE MFO/LOB Engagement | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1585 | AES-7448 |  |  | MBE MFO/LOB Engagement | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1586 | AES-7449 |  |  | EO MBE Functional Roadmaps | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1587 | AES-7450 |  |  | EO MBE Roadmaps (Space Enablement) | 4 | 4 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1588 | AES-7451 |  |  | EO MBE Roadmaps (Functional and Space Adoption) | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1589 | AES-7452 |  |  | EO MBE Roadmaps (Functional and Space Adoption) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1590 | AES-7453 |  |  | EO MBE Roadmaps (Functional and Space Adoption) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-1591 | AES-7454 |  |  | MBE MFO/LOB Engagement | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1592 | AES-7455 |  |  | EO MBE Functional Roadmaps | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-1593 | AES-7456 |  |  | MBE MFO/LOB Engagement | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-1594 | AES-7457 |  |  | Support to Dan Heller Quarterly Marquee Best Practices meeting 2Q | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1595 | AES-7458 |  |  | Prepare content for 23.2 Increment Demos | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1596 | AES-7459 |  |  | Complete Initial Discovery into NGI and lack of SDM adoption | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1597 | AES-7460 |  |  | E&T VP: Space 1LMX Review request | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1598 | AES-7461 |  |  | MS Teams Sandbox for SMBE ⛱ | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1599 | AES-7462 |  |  | Recommendation for E&T Reorg for SMBE | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-1600 | AES-7463 |  |  | Summit #3 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-1601 | AES-7464 |  |  | Summit 3 Prep | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1602 | AES-7465 |  |  | Summit 3 Prep | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-1603 | AES-7466 |  |  | E&T All Hands - 1LMX | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1604 | AES-7467 |  |  | Solicit feedback from TBD potential pilot program for a given capability | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-1605 | AES-7468 |  |  | Gain agreement from one LOB program to be our SMBE pilot program | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-1606 | AES-7469 |  |  | 23.2 Subcontracts LOE | 2.5 | 2.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1607 | AES-7470 |  |  | Ensure April '23 Procurements are on Track | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1608 | AES-7471 |  |  | Determine where the PO is for the latest Intercax site license | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-1609 | AES-7472 |  |  | Ensure May '23 Procurements are on Track | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1610 | AES-7473 |  |  | Ensure June '23 Procurements are on Track | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1611 | AES-7474 |  |  | Ensure July '23 Procurements are on Track | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-1612 | AES-7475 |  |  | 23.2 Execution Enhancements and Experiments LOE | 17.5 | 17.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1613 | AES-7476 |  |  | Document how to read the various gadgets on the SMBE Performance Dashboards Part 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1614 | AES-7477 |  |  | Templatize Roadmap Milestone Descriptions to be more end-user facing | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-1615 | AES-7478 |  |  | Initial Draft of Updated TSM Graphic with Interoperable threads identified | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1616 | AES-7479 |  |  | Tempo - Work-Package Confirmation & set-point of good data | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1617 | AES-7480 |  |  | Determine which culture hacks we want to continue or initiate on SMBE | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1618 | AES-7481 |  |  | Identify & document Business Owner(s) for Teams' PI Objectives | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-05-01 |  |  | 3
|  |  | SPACE-1619 | AES-7482 |  |  | Initial Discovery for SEIT Dashboard Ideas | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1620 | AES-7483 |  |  | Initial Discovery for Cyber Dashboard Ideas | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1621 | AES-7484 |  |  | Structure – Improvements and Enhancements 🦾 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1622 | AES-7485 |  |  | End of PI Incomplete Scope Process | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1623 | AES-7486 |  |  | Jira Hive Automation | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1624 | AES-7487 |  |  | Initial Discovery for Test Dashboard Ideas | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1625 | AES-7488 |  |  | Start draft of formalization of Pilot Programs per Capability | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-27 |  |  | 3
|  |  | SPACE-1626 | AES-7489 |  |  | Initial thoughts on how to package up our program management approach | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-26 |  |  | 3
|  |  | SPACE-1627 | AES-7490 |  |  | Initial draft of packaged up program management concept | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-23 |  |  | 3
|  |  | SPACE-1628 | AES-7491 |  |  | Brainstorm ways a network linked schedule could add value to SMBE beyond just having a roadmap | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1629 | AES-7492 |  |  | Update Increment Demos template consistent with the rest of SMBE branding | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1630 | AES-7493 |  |  | Jira Hive Updates Investigation 🔎 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1631 | AES-7494 |  |  | Perform a retrospective of our program business rhythms 🥁 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1632 | AES-7495 |  |  | Define example scenarios for the even/over statements | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-1633 | AES-7496 |  |  | Complete initial draft of formalization of Pilot Programs per Capability | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1634 | AES-7497 |  |  | Solicit feedback from potential pilot program for a given capability | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1635 | AES-7498 |  |  | Initial Release of Updated TSM Graphic with Interoperable threads identified | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-21 |  |  | 3
|  |  | SPACE-1636 | AES-7499 |  |  | Update WP to Tempo Folio Mapping & Understand BCWS Automation Readiness | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-1637 | AES-7500 |  |  | Ensure Biz Owner Demos are being setup for second half of team | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1638 | AES-7501 |  |  | 23.1 Increment Demos Feedback: 1LMX Connections | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1639 | AES-7502 |  |  | Investigate what effort it would take to add a Planned SP to-date column to Progress Measure | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1640 | AES-7503 |  |  | Agile Hive Reoccurring Card Generator for PMO 🎫🎫🎫 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-1641 | AES-7504 |  |  | 23.2 SMBE Operations and Execution LOE | 77.5 | 77.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1642 | AES-7505 |  |  | SMBE - QBD reporting - Month End March | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-05 |  |  | 3
|  |  | SPACE-1643 | AES-7506 |  |  | EVM - Mid Month review Meeting - March | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-1644 | AES-7507 |  |  | EVM - Month End March | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1645 | AES-7508 |  |  | SMBE - QBD reporting Month End April | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1646 | AES-7509 |  |  | SMBE - QBD reporting Month End May | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-1647 | AES-7510 |  |  | EVM - Month End May | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-1648 | AES-7511 |  |  | EVM - Month End April | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1649 | AES-7512 |  |  | EVM - Mid Month review Meeting - April | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-1650 | AES-7513 |  |  | EVM - Mid Month review Meeting - May | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-1651 | AES-7514 |  |  | SMBE Roadmap and Milestone Updates 🚩 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1652 | AES-7515 |  |  | APMO ROMB Prep Sprint 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1653 | AES-7516 |  |  | APMO ROMB Prep Sprint 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-21 |  |  | 3
|  |  | SPACE-1654 | AES-7517 |  |  | APMO ROMB Prep Sprint 3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
|  |  | SPACE-1655 | AES-7518 |  |  | APMO ROMB Prep Sprint 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-1656 | AES-7519 |  |  | APMO ROMB Prep Sprint 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1657 | AES-7520 |  |  | APMO ROMB Prep Sprint 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-1658 | AES-7521 |  |  | Cost Saving Calculator updates - Ops Efficiency capabilities | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1659 | AES-7522 |  |  | Create S&ME IOR Content for SMBE | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-13 |  |  | 3
|  |  | SPACE-1660 | AES-7523 |  |  | SMBE Cost Saving Calculator - Calibration Sprint 4 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1661 | AES-7524 |  |  | SMBE Cost Saving Calculator - Calibration Sprint 3 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1662 | AES-7525 |  |  | Recreation of STR Confluence Page for ERP, ETC, & NCA | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1663 | AES-7526 |  |  | Space Transformation Review - Month End Data Call (March) | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1664 | AES-7527 |  |  | Space Transformation Review - Month End Data Call (April) | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1665 | AES-7528 |  |  | Cost Saving Calculator updates - Alignment of resources | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1666 | AES-7529 |  |  | Tempo - Mid Month Review plan action | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1667 | AES-7530 |  |  | DPP Tier 2 Definitions: TSM 2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1668 | AES-7531 |  |  | DPP Tier 2 Definitions: TSM 2.2 - Vet with Stakeholders | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1669 | AES-7532 |  |  | Support ERP F2F | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1670 | AES-7533 |  |  | DPP Tier 2 milestone CMI 2.2 - Stakeholder review | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1671 | AES-7534 |  |  | DPP Tier 2 milestone CMI 2.2 and TSM 2.2 - Release | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1672 | AES-7535 |  |  | Agile Coaching and Tools 23.2.1.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1673 | AES-7536 |  |  | Wedge - Tempo | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-1674 | AES-7537 |  |  | Agile Coaching and Tools 23.2.1.2 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1675 | AES-7538 |  |  | Agile Coaching and Tools 23.2.2.1 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-1676 | AES-7539 |  |  | Agile Coaching and Tools 23.2.2.2 📚 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1677 | AES-7540 |  |  | Agile Coaching and Tools 23.2.3.1 🛠 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1678 | AES-7541 |  |  | Agile Coaching and Tools 23.2.3.2 🛠 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1679 | AES-7542 |  |  | Agile Coaching and Tools 23.2.4.2 🛠 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1680 | AES-7543 |  |  | Agile Coaching and Tools 23.2.5.1 👨‍🔧 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-1681 | AES-7544 |  |  | Agile Coaching and Tools 23.2.5.2 👨‍🔧 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1682 | AES-7545 |  |  | Agile Coaching and Tools 23.2.6.1 🛠 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-1683 | AES-7546 |  |  | Agile Coaching and Tools 23.2.6.2 🛠 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1684 | AES-7547 |  |  | SMBE GRID updates - Transition to CAMs | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1685 | AES-7548 |  |  | SMBE LOE - 23.2 S2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-1686 | AES-7549 |  |  | SMBE LOE - 23.2 S1.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1687 | AES-7550 |  |  | SMBE LOE - 23.2 S3.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1688 | AES-7551 |  |  | SMBE LOE - 23.2 S4.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-1689 | AES-7552 |  |  | SMBE LOE - 23.2 S5.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-1690 | AES-7553 |  |  | SMBE LOE - 23.2 S6.1 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1691 | AES-7554 |  |  | APMO CCB Prep Sprint 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1692 | AES-7555 |  |  | SMBE LOE - 23.2 S1.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1693 | AES-7556 |  |  | APMO CCB Prep Sprint 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1694 | AES-7557 |  |  | APMO CCB Prep Sprint 3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1695 | AES-7558 |  |  | APMO CCB Prep Sprint 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-1696 | AES-7559 |  |  | APMO CCB Prep Sprint 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-1697 | AES-7560 |  |  | APMO CCB Prep Sprint 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1698 | AES-7561 |  |  | SMBE LOE - 23.2 S2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1699 | AES-7562 |  |  | SMBE LOE - 23.2 S3.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-13 |  |  | 3
|  |  | SPACE-1700 | AES-7563 |  |  | SMBE LOE - 23.2 S4.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1701 | AES-7564 |  |  | SMBE LOE - 23.2 S5.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1702 | AES-7565 |  |  | SMBE LOE - 23.2 S6.2 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1703 | AES-7566 |  |  | Deep Dive Metrics Meeting Prep Sprint 2 🥽 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-1704 | AES-7567 |  |  | Deep Dive Metrics Meeting Prep Sprint 3 🤿 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1705 | AES-7568 |  |  | Deep Dive Metrics Meeting Prep Sprint 4 🤿 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1706 | AES-7569 |  |  | Deep Dive Metrics Meeting Prep Sprint 5 🤿 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1707 | AES-7570 |  |  | Tempo Data Ingest Checking - ME March | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1708 | AES-7571 |  |  | Tempo Data Ingest Checking - ME April | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-17 |  |  | 3
|  |  | SPACE-1709 | AES-7572 |  |  | Tempo Data Ingest Checking - ME May | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-1710 | AES-7573 |  |  | SMBE Agile Playbook - Revisions 📜 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1711 | AES-7574 |  |  | 3Q23 Run Ahead 🏃‍♂️ | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
|  |  | SPACE-1712 | AES-7575 |  |  | SMBE Run ahead 🏃‍♂️ | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1713 | AES-7576 |  |  | SMBE Run Ahead Work 🏃‍♂️ | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-1714 | AES-7577 |  |  | Kick-off 23.3 Run ahead 🏃‍♂️ | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1715 | AES-7578 |  |  | Agile Team Expectations 🤔 | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-1716 | AES-7579 |  |  | SMBE increment demos ideas | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1717 | AES-7580 |  |  | SMBE resource loading for PI 23.2 | 1.5 | 1.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1718 | AES-7581 |  |  | Tempo - Handoff to 1LMx PMO | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1719 | AES-7582 |  |  | Tempo - Update informational repository | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-1720 | AES-7583 |  |  | Tempo - Handoff to 1LMx PMO | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1721 | AES-7584 |  |  | Tempo - Handoff to 1LMx PMO | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1722 | AES-7585 |  |  | Create 23.2 Program Performance Dashboard | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1723 | AES-7586 |  |  | Clarification on Opportunity vs. CCB item | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-1724 | AES-7587 |  |  | SMBE involvement in corporate command media | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1725 | AES-7588 |  |  | SMBE Staffing Profile Update | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1726 | AES-7589 |  |  | 23.3 PI Planning Content Development | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1727 | AES-7590 |  |  | Tempo - Handoff to 1LMx PMO | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1728 | AES-7591 |  |  | Super CAM Support (ME) 22.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1729 | AES-7592 |  |  | Super CAM Support 22.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1730 | AES-7593 |  |  | Super CAM Support (ME) 22.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1731 | AES-7594 |  |  | Super CAM Support 22.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1732 | AES-7595 |  |  | Super CAM Support (ME) 22.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1733 | AES-7596 |  |  | Super CAM Support 22.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1734 | AES-7597 |  |  | SMBE Agile Playbook - 23.2 Revisions 📘 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-1735 | AES-7598 |  |  | Risk and Opportunity Management 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1736 | AES-7599 |  |  | Risk and Opportunity Management 23.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1737 | AES-7600 |  |  | Risk and Opportunity Management 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1738 | AES-7601 |  |  | Risk and Opportunity Management 23.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1739 | AES-7602 |  |  | Risk and Opportunity Management 23.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1740 | AES-7603 |  |  | Risk and Opportunity Management 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-1741 | AES-7604 |  |  | Complete CAM 101 Training | 0 | 0 | 0 | 0% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1742 | AES-7605 |  |  | ROMB Innovation Work | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1743 | AES-7606 |  |  | Tempo - Capture & Action Mid-Month Review Learnings | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1744 | AES-7607 |  |  | RTE Review of the Documents ahead of CCB | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1745 | AES-7608 |  |  | Human-Side Video | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-1746 | AES-7609 |  |  | 23.1 Increment Demos Team Feedback Review | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1747 | AES-7610 |  |  | SMBE Roadmap and Milestone Updates 🚩 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1748 | AES-7611 |  |  | SAFe PO Training Course | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1749 | AES-7612 |  |  | Nelson Data Call | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1750 | AES-7613 |  |  | APMO Month End April | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1751 | AES-7614 |  |  | Tempo - Workpackage Checking with MBE & PO teams | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-1752 | AES-7615 |  |  | SMBE Milestone Updates 🚩 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1753 | AES-7616 |  |  | SMBE Milestone Updates 🚩 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1754 | AES-7617 |  |  | 3Q23 Run Ahead Sprint 5 🏃‍♂️ | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-1755 | AES-7618 |  |  | Update description & acceptance criteria for eQube milestones | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-05-31 |  |  | 3
|  |  | SPACE-1756 | AES-7619 |  |  | Coordinate with Anita Mangan & DTw to ensure Space needs are represented as part of the future eQube EULA negotiation | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1757 | AES-7620 |  |  | Find out if DTw has any direct program commitments impacted by lack of PROD in current eQube EULA | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1758 | AES-7621 |  |  | SMBE PI Planning and Dtwin PI Planning agenda review 🧬 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-15 |  |  | 3
|  |  | SPACE-1759 | AES-7622 |  |  | SMBE Milestone Updates 🚩 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-12 |  |  | 3
|  |  | SPACE-1760 | AES-7623 |  |  | 1LMX Financial Review | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-1761 | AES-7624 |  |  | Prepare for arrival of HS Intern | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-1762 | AES-7625 |  |  | Share Functional and Enablement Roadmaps with SMBE program team | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1763 | AES-7626 |  |  | Understand if DPP Tier 2 MBE: CMI 2.2 can be updated given the eQube EULA doesn't cover PROD yet | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-26 |  |  | 3
|  |  | SPACE-1764 | AES-7627 |  |  | APMO Month End May | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1765 | AES-7628 |  |  | 23.2 Team Engagement LOE | 5 | 5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1766 | AES-7629 |  |  | 23.2 Human side videos | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1767 | AES-7630 |  |  | 23.2 Plan an SMBE Social Hour 🥨 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-1768 | AES-7631 |  |  | SMBE Townhall | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1769 | AES-7632 |  |  | Employee Spotlights | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-05-31 |  |  | 3
|  |  | SPACE-1770 | AES-7633 |  |  | 23.2 Execution Retrospective 💡👀 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-22 |  |  | 3
|  |  | SPACE-1771 | AES-7634 |  |  | SMBE Townhall Prep - Agenda | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-1772 | AES-7635 |  |  | Townhall content creation | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-1773 | AES-7636 |  |  | Townhall content creation (Ryan) | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1774 | AES-7637 |  |  | Townhall content creation (Rachel) | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1775 |  |  |  | SLMX_MBE_PRGAD | 443.3 | 443.3 | 0 | 100% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232E.0005 | SPACE-1776 | AES-7638 | ONELMX_MBE_SSC | MBESTK23 | Spc MBE: PrgAd 23.2 Starter Kit Quarterly Release - Exp Labor/NL | 143.5 | 143.5 | 0 | 100% | 2023-04-02 | 2023-06-25 | 2023-04-03 | 2023-06-23 | 1
|  |  | SPACE-1777 | AES-7639 |  |  | MBE Training Curriculum Updates 23.2 | 18.5 | 18.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1778 | AES-7640 |  |  | SEA Tag Up 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-1779 | AES-7641 |  |  | SEA Tag Up 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-1780 | AES-7642 |  |  | SEA Tag Up 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1781 | AES-7643 |  |  | SEA Tag Up 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-1782 | AES-7644 |  |  | SEA Tag Up 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-05-30 |  |  | 3
|  |  | SPACE-1783 | AES-7645 |  |  | SEA Tag Up 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1784 | AES-7646 |  |  | Check training efforts stories with Jim & Diane 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1785 | AES-7647 |  |  | Webify scenario links into Starter Kit - TSM | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1786 | AES-7648 |  |  | 1LMX Enterprise training and SK into SMBE SK | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1787 | AES-7649 |  |  | Update Starter Kit Capability Adoption pages w/ capability training | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-1788 | AES-7650 |  |  | Capability Training Plans - TSM | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1789 | AES-7651 |  |  | Check training efforts stories with Jim & Diane 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1790 | AES-7652 |  |  | Webify scenario links into Starter Kit - SDM | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1791 | AES-7653 |  |  | Develop user training strategy 23.2.2 | 1.25 | 1.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1792 | AES-7654 |  |  | Check training efforts stories with Jim & Diane 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1793 | AES-7655 |  |  | Webify scenario links into Starter Kit - Webify & TSP | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1794 | AES-7656 |  |  | Develop user training strategy 23.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1795 | AES-7657 |  |  | Check training efforts stories with Jim & Diane 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1796 | AES-7658 |  |  | Webify scenario links into Starter Kit | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1797 | AES-7659 |  |  | Capability Training Plans - modeFrontier/Volta | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1798 | AES-7660 |  |  | Develop user training strategy 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1799 | AES-7661 |  |  | Check training efforts stories with Jim & Diane 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1800 | AES-7662 |  |  | Webify scenario links into Starter Kit | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1801 | AES-7663 |  |  | Develop user training strategy 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1802 | AES-7664 |  |  | Check training efforts stories with Jim & Diane 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1803 | AES-7665 |  |  | Webify scenario links into Starter Kit <ph> | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1804 | AES-7666 |  |  | First steps of creating TSM Atlas course with Alex | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1805 | AES-7667 |  |  | Develop user training strategy (SDM focus) 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1806 | AES-7668 |  |  | Training scoping & development LOE + SK updates 23.2.1 | 0 | 0 | 0 | 0% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-1807 | AES-7669 |  |  | Training scoping & development LOE + SK updates 23.2.1 | 0 | 0 | 0 | 0% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1808 | AES-7670 |  |  | Training scoping & development LOE + SK updates 23.2.2 | 0 | 0 | 0 | 0% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1809 | AES-7671 |  |  | Training scoping & development LOE + SK updates 23.2.3 | 0 | 0 | 0 | 0% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1810 | AES-7672 |  |  | Training scoping & development LOE + SK updates 23.2.3 | 0 | 0 | 0 | 0% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1811 | AES-7673 |  |  | Training scoping & development LOE + SK updates 23.2.4 | 0 | 0 | 0 | 0% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1812 | AES-7674 |  |  | Training scoping & development LOE + SK updates 23.2.5 | 0 | 0 | 0 | 0% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1813 | AES-7675 |  |  | Training scoping & development LOE + SK updates 23.2.5 | 0 | 0 | 0 | 0% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1814 | AES-7676 |  |  | Training scoping & development LOE + SK updates 23.2.6 | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1815 | AES-7677 |  |  | Assessment / eval of older training material | 0 | 0 | 0 | 0% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1816 | AES-7678 |  |  | 23.2 Feature Closure for Training Work | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1817 | AES-7679 |  |  | Develop user training strategy 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1818 | AES-7680 |  |  | Training scoping & development LOE + SK updates 23.2.2 | 0 | 0 | 0 | 0% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1819 | AES-7681 |  |  | Training scoping & development LOE + SK updates 23.2.4 | 0 | 0 | 0 | 0% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1820 | AES-7682 |  |  | Training scoping & development LOE + SK updates 23.2.6 | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1821 | AES-7683 |  |  | 1LMX Enterprise training and SK into SMBE SK part 2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1822 | AES-7684 |  |  | vCPE training | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1823 | AES-7685 |  |  | Engineering Process Updates 23.2 | 50.5 | 50.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1824 | AES-7686 |  |  | Update MBEP in PGT and Post to SK | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1825 | AES-7687 |  |  | Awareness Communication w/ BPT team | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1826 | AES-7688 |  |  | Update capability information on Alliance pages for 23.2 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1827 | AES-7689 |  |  | User Guide Updates for all Zuken Capabilities Part 1 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1828 | AES-7690 |  |  | User Guide updates for: SDM; TSM (includes TSP EKG view) Part 1 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1829 | AES-7691 |  |  | User Guide updates for: SDM; TSM (includes TSP EKG view) Part 2 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-1830 | AES-7692 |  |  | User Guide Updates for Webify Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1831 | AES-7693 |  |  | Enhance process organization / user experience Part 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-1832 | AES-7694 |  |  | User Guide Updates for TSP Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1833 | AES-7695 |  |  | User Guide Updates for Intelligent Assembly Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1834 | AES-7696 |  |  | User Guide Updates for Factory DTwin Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1835 | AES-7697 |  |  | User Guide Updates for DTwin vCPE Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1836 | AES-7698 |  |  | User Guide Updates for Visual Work Instructions Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1837 | AES-7699 |  |  | Determine existing/Create new processes/user guides/documentation for LMScripts & Metrics Module Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-1838 | AES-7700 |  |  | User Guide Updates for modeFroniter/Volta Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1839 | AES-7701 |  |  | Determine existing or create new processes/user guides/documentation for DCT SPC Part 1 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1840 | AES-7702 |  |  | Awareness Communication w/ Harness Team | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1841 | AES-7703 |  |  | Awareness Communication w/ ME | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-1842 | AES-7704 |  |  | Include new/updated CDAO guidance into Starter Kit | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-1843 | AES-7705 |  |  | Enhance process organization / user experience Part 2 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1844 | AES-7706 |  |  | User Guide Updates for Polyworks Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1845 | AES-7707 |  |  | Investigate 1LMX / other BA DX Processes and Playbooks | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1846 | AES-7708 |  |  | Collaborate w/ MBE Test team to understand the workflows | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1847 | AES-7709 |  |  | Awareness Communication w/ GNC | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1848 | AES-7710 |  |  | Awareness Communication w/ SE | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1849 | AES-7711 |  |  | Investigate what data / model standards may need to be developed for MBE Capabilities | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1850 | AES-7712 |  |  | Update Eng Discipline Process Lists Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1851 | AES-7713 |  |  | Work with BPT teams to update inputs for relevant BPTs | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1852 | AES-7714 |  |  | Update links to other BA resources in Starter Kit | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1853 | AES-7715 |  |  | Awareness Communication w/ OPCOE | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1854 | AES-7716 |  |  | Awareness Communication w/ RFCOE | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1855 | AES-7717 |  |  | Include new/updated Supply Chain guidance into Starter Kit | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1856 | AES-7718 |  |  | Update Eng Discipline Process Lists Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1857 | AES-7719 |  |  | User Guide Updates for Intelligent Assembly Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1858 | AES-7720 |  |  | User Guide Updates for Webify Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1859 | AES-7721 |  |  | User Guide Updates for Polyworks Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1860 | AES-7722 |  |  | Enhance process organization / user experience Part 3 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1861 | AES-7723 |  |  | Develop new 1LMX playbooks based on the investigation | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1862 | AES-7724 |  |  | Solicit MBE Plan Updates | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-1863 | AES-7725 |  |  | 23.2 Feature Closure for Process Work | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1864 | AES-7726 |  |  | Update/Review MBEP - 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1865 | AES-7727 |  |  | Collaborate w/ MBE Test team | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1866 | AES-7728 |  |  | Query program for example processes / artifacts for re-use (part 1) | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1867 | AES-7729 |  |  | Query program for example processes / artifacts for re-use (part 2) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1868 | AES-7730 |  |  | Query program for example processes / artifacts for re-use (part 3) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1869 | AES-7731 |  |  | Thin Thread Expertise (part 1) | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-25 |  |  | 3
|  |  | SPACE-1870 | AES-7732 |  |  | Thin Thread Expertise (part 2) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1871 | AES-7733 |  |  | Update/Review MBEP - 23.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1872 | AES-7734 |  |  | Update/Review MBEP - 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1873 | AES-7735 |  |  | Update/Review MBEP - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1874 | AES-7736 |  |  | Update/Review MBEP - 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-1875 | AES-7737 |  |  | Cross Function Communication - 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1876 | AES-7738 |  |  | Cross Function Communication - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1877 | AES-7739 |  |  | Cross Function Communication - 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1878 | AES-7740 |  |  | Cross Function Communication - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1879 | AES-7741 |  |  | Cross Function Communication - 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1880 | AES-7742 |  |  | Cross Function Communication - 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-1881 | AES-7743 |  |  | Update MDP Content | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1882 | AES-7744 |  |  | Update/Review MBEP - 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1883 | AES-7745 |  |  | Awareness Communication w/ SWE | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1884 | AES-7746 |  |  | Awareness Communication w/ EE | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1885 | AES-7747 |  |  | Determine existing/create new processes/user guides/documentation for LMScripts & Metrics Module Part 3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1886 | AES-7748 |  |  | User Guide Updates for Visual Work Instructions Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1887 | AES-7749 |  |  | User Guide Updates for DTwin vCPE Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1888 | AES-7750 |  |  | User Guide Updates for Factory DTwin Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1889 | AES-7751 |  |  | Peer Review of MBE Plan | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1890 | AES-7752 |  |  | Update MDP in PGT and Post to SK | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1891 | AES-7753 |  |  | User Guide Updates for: Simplis and Mastercam Start-Up Wizard Part 1 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1892 | AES-7754 |  |  | User Guide Updates for all Zuken Capabilities Part 2 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1893 | AES-7755 |  |  | User Guide Updates for: Simplis and Mastercam Start-Up Wizard Part 2 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1894 | AES-7756 |  |  | Comment Adjudication of MBE Plan | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1895 | AES-7757 |  |  | Determine existing/create new processes/user guides/documentation for DCT SPC Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1896 | AES-7758 |  |  | User Guide Updates for TSP Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1897 | AES-7759 |  |  | Determine existing/create new processes/user guides/documentation for DTECTX Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1898 | AES-7760 |  |  | Determine existing/create new processes/user guides/documentation for DTECTX Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1899 | AES-7761 |  |  | User Guide Updates for modeFroniter/Volta Part 2 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1900 | AES-7762 |  |  | (if needed) Update starter kit with command media or other work instructions | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1901 | AES-7763 |  |  | (If needed) Provide updates to command media or other work instruction | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1902 | AES-7764 |  |  | Determine existing/Create new processes/user guides/documentation for LMScripts & Metrics Module Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1903 | AES-7765 |  |  | Collaborate w/ MBE Test team to understand the workflows | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1904 | AES-7766 |  |  | Investigate what data / model standards may need to be developed for MBE Capabilities | 0.75 | 0.75 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1905 | AES-7767 |  |  | Determine existing/create new processes/user guides/documentation for DTECTX Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1906 | AES-7768 |  |  | MBE General Starter Kit & Communications 23.2 | 10.25 | 10.25 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1907 | AES-7769 |  |  | Solicit feedback on Starter Kit | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1908 | AES-7770 |  |  | Incorporate any SK feedback | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1909 | AES-7771 |  |  | Update Savant entry as needed for 23.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1910 | AES-7772 |  |  | Advertise 23.1 Accomplishments | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-1911 | AES-7773 |  |  | Create survey(s) for Program Adoption impact on programs | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1912 | AES-7774 |  |  | CapCat vs SK Duplication Assessment and Next Steps | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1913 | AES-7775 |  |  | Organize brown bag for TBD capability | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1914 | AES-7776 |  |  | Decide whether to organize another brown bag for TBD capability | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1915 | AES-7777 |  |  | Agile / Metrics Support 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-1916 | AES-7778 |  |  | Update Engagement Material | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1917 | AES-7779 |  |  | Update Comm Plan | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1918 | AES-7780 |  |  | Review full Starter Kit Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1919 | AES-7781 |  |  | Agile / Metrics Support 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1920 | AES-7782 |  |  | Agile / Metrics Support 23.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-08 |  |  | 3
|  |  | SPACE-1921 | AES-7783 |  |  | Agile / Metrics Support 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-1922 | AES-7784 |  |  | Agile / Metrics Support 23.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1923 | AES-7785 |  |  | Agile / Metrics Support 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1924 | AES-7786 |  |  | 23.2 Feature Closure for Starter Kit Work | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1925 | AES-7787 |  |  | Cyber: MBE Cyber Dashboard - Integrate Reporting MVP | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-1926 | AES-7788 |  |  | Review full Starter Kit Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1927 | AES-7789 |  |  | Capability Implementation 23.2 | 64.25 | 64.25 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-1928 | AES-7790 |  |  | Update Existing Capability Cost Estimates | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1929 | AES-7791 |  |  | Capability Cost Estimates: Harness Builder | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1930 | AES-7792 |  |  | Cost Roles & Responsibilities | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-1931 | AES-7793 |  |  | Starter Kit Application List into Cameo/Webify | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1932 | AES-7794 |  |  | CRRA / CICADA (aka CYCADA) to Starter Kit 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1933 | AES-7795 |  |  | Update SW Capability List | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1934 | AES-7796 |  |  | Capability Cost Estimates: Polyworks | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1935 | AES-7797 |  |  | Capability Cost Estimates: SIMPLIS | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-19 |  |  | 3
|  |  | SPACE-1936 | AES-7798 |  |  | Capability Cost Estimates: Intelligent Assembly App | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1937 | AES-7799 |  |  | Capability Cost Estimates: DTECTX | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-1938 | AES-7800 |  |  | Update Starter Kit Ready-Now and Ready Soon List for new 23.2 or earlier capabilities (Part 1) | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-1939 | AES-7801 |  |  | Update Starter Kit Ready-Now and Ready Soon List for new 23.2 or earlier capabilities (Part 3) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1940 | AES-7802 |  |  | New Strategy Adoption Plan SDM | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1941 | AES-7803 |  |  | New Strategy Adoption Plan TSM | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1942 | AES-7804 |  |  | New Strategy Adoption Plan Template | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-1943 | AES-7805 |  |  | Provide List of Target Programs to Externals | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1944 | AES-7806 |  |  | New Strategy Adoption Plan Webify | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-1945 | AES-7807 |  |  | New Strategy Adoption Plan modeFrontier/Volta | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1946 | AES-7808 |  |  | Update Program Adoption Template | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1947 | AES-7809 |  |  | 1LMX Ready-Now List & Starter Kit Integration | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1948 | AES-7810 |  |  | 23.2 Feature Closure Work for Capability Implementation Work | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1949 | AES-7811 |  |  | SpaceCat vs SMBE SK application lists | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-1950 | AES-7812 |  |  | Finalize Capability Implementation Plans: SDM | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-1951 | AES-7813 |  |  | Reference Architecture Updates | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1952 | AES-7814 |  |  | Capability Implementation Plans: Incorporate NGI Lessons Learned | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1953 | AES-7815 |  |  | Capability Implementation Plan: Assess Existing Material | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-1954 | AES-7816 |  |  | Finish Updating Starter Kit Ready-Now and Ready Soon List from 23.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1955 | AES-7817 |  |  | Proposal Insertion Strategies: Understanding Existing Material | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1956 | AES-7818 |  |  | Proposal Insertion Strategies: Reconcile SMBE Cost Information | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1957 | AES-7819 |  |  | Proposal Insertion Strategies: SDM | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1958 | AES-7820 |  |  | Proposal Insertion Strategies: TSM | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1959 | AES-7821 |  |  | Proposal Insertion Strategies: Other Capabilities | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1960 | AES-7822 |  |  | Update Program Engagement Plan | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1961 | AES-7823 |  |  | Proposal Insertion Strategies: Cleanup | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-1962 | AES-7824 |  |  | New Strategy Adoption Plan TSP | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1963 | AES-7825 |  |  | Update Starter Kit Ready-Now and Ready Soon List for new 23.2 or earlier capabilities (Part 2) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1964 | AES-7826 |  |  | Define Target Programs per Major Capability | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1965 | AES-7827 |  |  | CapCat Record Maturation Understanding | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-1966 | AES-7828 |  |  | CapCat Record Update for Green Rating | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1967 | AES-7829 |  |  | Verify all MBE capabilities are covered in CapCat; update existing entries as needed | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1968 | AES-7830 |  |  | Finish Cost Estimate TBDs | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1969 | AES-7831 |  |  | CRRA / CICADA (aka CYCADA) into SK 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1970 | AES-7832 |  |  | CRRA / CICADA (aka CYCADA) into SK 23.2.3 | 1.25 | 1.25 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-1971 | AES-7833 |  |  | CRRA / CICADA (aka CYCADA) and Cyber into SK 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1972 | AES-7834 |  |  | CRRA / CICADA (aka CYCADA) and Cyber into SK 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-1973 | AES-7835 |  |  | CRRA / CICADA (aka CYCADA) into SK 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1974 | AES-7836 |  |  | Finalize Capability Implementation Plans: TSM | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1975 | AES-7837 |  |  | Capability Implementation Plan: Create New Template | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-1976 | AES-7838 |  |  | Document License Info for each Capability | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1977 | AES-7839 |  |  | DPP Model Updates with SMBE Caps - 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-1978 | AES-7840 |  |  | DPP Model Updates with SMBE Caps - 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1979 | AES-7841 |  |  | DPP Model Updates with SMBE Caps - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1980 | AES-7842 |  |  | DPP Model Updates with SMBE Caps - 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-1981 | AES-7843 |  |  | DPP Model Updates with SMBE Caps - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1982 | AES-7844 |  |  | DPP Model Updates with SMBE Caps - 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1983 | AES-7845 |  |  | Cyber: Integrate ASP into Starter Kit | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-1984 | AES-7846 |  |  | Cyber: Establish Cyber Security Discipline in Starter Kit | 3 | 3 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-1985 | AES-7847 |  |  | Cyber: Investigate Integrate ASP into Starter Kit | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-12 |  |  | 3
|  |  | SPACE-1986 | AES-7848 |  |  | Finish Updating Starter Kit Ready-Now and Ready Soon List from 23.1 (Part 2) | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-1987 | AES-7849 |  |  | Confirm Cyber/Security TBDs | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-1988 | AES-7850 |  |  | Review Reference Architecture Diagram | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-1989 | AES-7851 |  |  | Reference Architecture Diagram to Webify | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1990 | AES-7852 |  |  | Program-Specific Ref Arch: NGI | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-1991 | AES-7853 |  |  | Cyber: Integrate ASP into Starter Kit | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-1992 | AES-7854 |  |  | Verify all MBE capabilities are covered in CapCat; update existing entries as needed (Part 2) | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1993 | AES-7855 |  |  | Add software lists for newer capabilities pt1 | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-1994 | AES-7856 |  |  | Sprint 23.2.3 Cleanup Work | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1995 | AES-7857 |  |  | Update 'pending' CapCat solutions | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-1996 | AES-7858 |  |  | Document License Info for each Capability pt.2 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-25 |  |  | 3
|  |  | SPACE-1997 | AES-7859 |  |  | Finalize Capability Implementation Plans: SIMPLIS | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-1998 | AES-7860 |  |  | Finalize Capability Implementation Plans: Harness Builder | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-1999 | AES-7861 |  |  | Finalize Capability Implementation Plans: Zuken DS-CR/DS-E3 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-2000 | AES-7862 |  |  | Finalize Capability Implementation Plans: VWI | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-2001 | AES-7863 |  |  | Finalize Capability Implementation Plans: Polyworks | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-2002 | AES-7864 |  |  | Finalize Capability Implementation Plans: Webify | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-2003 | AES-7865 |  |  | Finalize Capability Implementation Plans: TSP | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-2004 | AES-7866 |  |  | Finalize Capability Implementation Plans: modeFrontier/Volta | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-2005 | AES-7867 |  |  | Finalize Capability Implementation Plans: Intelligent Assembly | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2006 | AES-7868 |  |  | Proposal Insertion Strategies: Zuken Review | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-2007 | AES-7869 |  |  | Finalize Capability Implementation Plans: Mastercam | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-2008 | AES-7870 |  |  | 1-pager and Capcat updates | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-2009 | AES-7871 | ONELMX_MBE_SSC | MBE23LOE | Spc MBE: PRGAD LOE 23.2 - Exp - Lab/NL | 299.8 | 299.8 | 0 | 100% | 2023-02-12 | 2023-06-28 | 2023-04-03 | 2023-06-23 | 1
|  |  | SPACE-2010 | AES-7872 |  |  | MBEC Team 23.2 (LOE) | 84.05 | 84.05 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2011 | AES-7873 |  |  | 23.2 Enabler Closure for MBEC Work | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2012 | AES-7874 |  |  | MBE Orientation (Part 2) |  |  | 0 | 0% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2013 | AES-7875 |  |  | MBE Orientation (Part 1) - Mechanical | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2014 | AES-7876 |  |  | MBE Orientation (Part 1) - Mechanical | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2015 | AES-7877 |  |  | MBE Orientation (Part 2) - Mechanical |  |  | 0 | 0% | 2023-04-30 | 2023-05-03 |  |  | 3
|  |  | SPACE-2016 | AES-7878 |  |  | MBE Orientation (Part 1) - Anger - DT |  |  | 0 | 0% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-2017 | AES-7879 |  |  | MBE Orientation (Part 2) - Anger - DT | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-06-23 |  |  | 3
|  |  | SPACE-2018 | AES-7880 |  |  | MBE Orientation (Part 1) - Specialty Engineering |  |  | 0 | 0% | 2023-04-16 | 2023-04-28 |  |  | 3
|  |  | SPACE-2019 | AES-7881 |  |  | MBE Orientation (Part 1) |  |  | 0 | 0% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-2020 | AES-7882 |  |  | MBE Orientation (Part 1) - Systems Engineering |  |  | 0 | 0% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-2021 | AES-7883 |  |  | MBE Orientation (Part 1) - Systems Engineering |  |  | 0 | 0% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-2022 | AES-7884 |  |  | MBE Orientation (Part 2) - Systems Engineering |  |  | 0 | 0% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-2023 | AES-7885 |  |  | MBE Orientation (Part 1) |  |  | 0 | 0% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2024 | AES-7886 |  |  | MBE Orientation (Part 1) | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2025 | AES-7887 |  |  | MBE Orientation (Part 2) - Specialty Engineering | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-2026 | AES-7888 |  |  | MBE Orientation (Part 2) - Systems Engineering | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-18 |  |  | 3
|  |  | SPACE-2027 | AES-7889 |  |  | MBE Orientation (Part 2) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-2028 | AES-7890 |  |  | MBE Orientation (Part 1) |  |  | 0 | 0% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2029 | AES-7891 |  |  | MBE Orientation (Part 1) |  |  | 0 | 0% | 2023-04-30 | 2023-05-02 |  |  | 3
|  |  | SPACE-2030 | AES-7892 |  |  | MBE Orientation (Part 1) | 0.7 | 0.7 | 0 | 100% | 2023-04-30 | 2023-05-30 |  |  | 3
|  |  | SPACE-2031 | AES-7893 |  |  | MBE Orientation (Part 1) |  |  | 0 | 0% | 2023-04-30 | 2023-05-08 |  |  | 3
|  |  | SPACE-2032 | AES-7894 |  |  | MBE Orientation (Part 1) | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-18 |  |  | 3
|  |  | SPACE-2033 | AES-7895 |  |  | MBE Orientation (Part 2) - Proposal | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-17 |  |  | 3
|  |  | SPACE-2034 | AES-7896 |  |  | MBE Orientation (Part 1) | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-16 |  |  | 3
|  |  | SPACE-2035 | AES-7897 |  |  | MBE Orientation (Part 1) |  |  | 0 | 0% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-2036 | AES-7898 |  |  | MBE Orientation (Part 2) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-19 |  |  | 3
|  |  | SPACE-2037 | AES-7899 |  |  | MBE Orientation (Part 1) |  |  | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2038 | AES-7900 |  |  | MBE Orientation (Part 2) | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-2039 | AES-7901 |  |  | MBE Orientation (Part 2) |  |  | 0 | 0% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2040 | AES-7902 |  |  | MBE Orientation (Part 1) - Electrical Engineering |  |  | 0 | 0% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2041 | AES-7903 |  |  | MBE Orientation (Part 2) - Software Engineering |  |  | 0 | 0% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2042 | AES-7904 |  |  | MBE Orientation (Part 2) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2043 | AES-7905 |  |  | MBE Orientation (Part 1) - Software Engineering |  |  | 0 | 0% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-2044 | AES-7906 |  |  | MBE Orientation (Part 2) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-22 |  |  | 3
|  |  | SPACE-2045 | AES-7907 |  |  | MBE Orientation (Part 1) | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-18 |  |  | 3
|  |  | SPACE-2046 | AES-7908 |  |  | Specialty - HSI: Develop Draft Business Process Thread | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-30 |  |  | 3
|  |  | SPACE-2047 | AES-7909 |  |  | I&T - Research Tools for LM Space | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2048 | AES-7910 |  |  | MBE Orientation (Part 1) | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2049 | AES-7911 |  |  | MBE Orientation (Part 2) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-01 |  |  | 3
|  |  | SPACE-2050 | AES-7912 |  |  | I&T - Review of Starter kit with I&T focus | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-2051 | AES-7913 |  |  | MBE Orientation (Part 1 cont) | 0.3 | 0.3 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2052 | AES-7914 |  |  | TSM Familiarization - Patel | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2053 | AES-7915 |  |  | Understand current SA infrastructure | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2054 | AES-7916 |  |  | Develop HSI Plan Charts | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2055 | AES-7917 |  |  | Collaborate with the CHIL on Delmia Linkage & Develop HSI Tools List | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2056 | AES-7918 |  |  | Install infrastructure | 4 | 4 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2057 | AES-7919 |  |  | SMBE SW Upskilling Plan - Initial | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2058 | AES-7920 |  |  | Create Slides for Draft ME Plan | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-2059 | AES-7921 |  |  | EE - Review the Starter Kit EE Sections | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2060 | AES-7922 |  |  | SW - Review of SMBE SW Development Methodology | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-09 |  |  | 3
|  |  | SPACE-2061 | AES-7923 |  |  | Review Starter Kit | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-06 |  |  | 3
|  |  | SPACE-2062 | AES-7924 |  |  | EE - Outline SMBE EE UpSkilling Plan - Draft - Part 1 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2063 | AES-7925 |  |  | EE - Outline SMBE EE UpSkilling Plan - Draft | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2064 | AES-7926 |  |  | TSM Familiarization | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2065 | AES-7927 |  |  | Setup MBSE Proposal Dev Strategy Location | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2066 | AES-7928 |  |  | Gather Proposal Data and Examples | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2067 | AES-7929 |  |  | EE - Review the Starter Kit EE Sections | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2068 | AES-7930 |  |  | Draft outline of SA plan for DX | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-2069 | AES-7931 |  |  | Create Draft Specialty Cyber & E3 Vision Plan | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-2070 | AES-7932 |  |  | SW - Review of SMBE Sofware List Per Capability | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-2071 | AES-7933 |  |  | SW - Review of SMBE Software Engineering Process | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-2072 | AES-7934 |  |  | Create SA quick start guide | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2073 | AES-7935 |  |  | Update Vision Plan for Cyber | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2074 | AES-7936 |  |  | Create Cyber page | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2075 | AES-7937 |  |  | Meet with Mechanical SMEs in SMBE | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2076 | AES-7938 |  |  | Reach out to known Cyber POCs | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2077 | AES-7939 |  |  | MBE Orientation (Part 1) - SM | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2078 | AES-7940 |  |  | MBE Orientation (Part 2) - SM | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2079 | AES-7941 |  |  | EE - Outline SMBE EE UpSkilling Plan - Draft - Part 2 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2080 | AES-7942 |  |  | EE - Conduct a Brainstorming Session | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2081 | AES-7943 |  |  | EE - Meet with EE SMEs in SMBE | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2082 | AES-7944 |  |  | EE - Meet with EE Sr Manager SMEs | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2083 | AES-7945 |  |  | Investigate available IT resources | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2084 | AES-7946 |  |  | Develop Top Level Training Implementation Strategy | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2085 | AES-7947 |  |  | Develop Specialty Engineering Top Level Plan | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2086 | AES-7948 |  |  | Develop Proposal Upskilling Plan | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2087 | AES-7949 |  |  | Refine HSI Tools List | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2088 | AES-7950 |  |  | Create SA quick start guide | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2089 | AES-7951 |  |  | Gathering information/input from SMEs | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2090 | AES-7952 |  |  | Resources Familiarization - OneLM MBE Playbook project | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2091 | AES-7953 |  |  | Determine ME Best Practices in CSM | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2092 | AES-7954 |  |  | Complete PTC University Creo Trainings | 0.2 | 0.2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2093 | AES-7955 |  |  | Draft System Safety Upskilling Plan | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2094 | AES-7956 |  |  | Review existing System Safety Command Media | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2095 | AES-7957 |  |  | EE - Create a Survey to Gather EE Data | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2096 | AES-7958 |  |  | Review Gary's Upskill Plan and Provide Feedback - Patel | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2097 | AES-7959 |  |  | Draft Integration and Test Upskilling Plan | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2098 | AES-7960 |  |  | MBE Orientation (Part 1) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2099 | AES-7961 |  |  | MBE Orientation (Part 1) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2100 | AES-7962 |  |  | Scum Master Duties | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2101 | AES-7963 |  |  | Create EE survey in Airtable | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2102 | AES-7964 |  |  | PO Duties LOE | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2103 | AES-7965 |  |  | EE - Test the Survey to Gather EE Data | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2104 | AES-7966 |  |  | Begin PTC University Creo Trainings | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2105 | AES-7967 |  |  | Determine ME Best Practices in CSM | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2106 | AES-7968 |  |  | Creating plan for future work (Pre-PI-Planning) | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2107 | AES-7969 |  |  | PI Pre-Planning | 0.1 | 0.1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2108 | AES-7970 |  |  | MBE Orientation (Part 2) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-28 |  |  | 3
|  |  | SPACE-2109 | AES-7971 |  |  | NGI MBE Capability Adoption 23.2 (LOE) | 27.25 | 27.25 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2110 | AES-7972 |  |  | NGI TSM Support | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2111 | AES-7973 |  |  | NGI TSM Support | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2112 | AES-7974 |  |  | NGI TSM Support | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2113 | AES-7975 |  |  | NGI TSM Support | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2114 | AES-7976 |  |  | NGI TSM Support | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2115 | AES-7977 |  |  | NGI TSM Support | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2116 | AES-7978 |  |  | Develop storyboard for PDR demo of use of TSM | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-2117 | AES-7979 |  |  | Understand NGI roadblocks to SDM classified use | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2118 | AES-7980 |  |  | NGI Program Engagement 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2119 | AES-7981 |  |  | NGI Program Engagement 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2120 | AES-7982 |  |  | NGI Program Engagement 23.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2121 | AES-7983 |  |  | NGI Program Engagement 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2122 | AES-7984 |  |  | NGI Program Engagement 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2123 | AES-7985 |  |  | NGI Program Engagement 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2124 | AES-7986 |  |  | NGI Use Case Development | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2125 | AES-7987 |  |  | NGI Use Case Development | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2126 | AES-7988 |  |  | NGI Use Case Development | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2127 | AES-7989 |  |  | NGI Use Case Development | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2128 | AES-7990 |  |  | 23.2 Enabler Closure Work for NGI Adoption | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2129 | AES-7991 |  |  | 23.2.1 TSM on NGI Deployment Execution | 2.5 | 2.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-2130 | AES-7992 |  |  | 23.2.2 TSM on NGI Deployment Execution | 2.5 | 2.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2131 | AES-7993 |  |  | 23.2.3 TSM on NGI Deployment Execution | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2132 | AES-7994 |  |  | 23.2.4 TSM on NGI Deployment Execution | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2133 | AES-7995 |  |  | 23.2.5 TSM on NGI Deployment Execution | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2134 | AES-7996 |  |  | 23.2.6 TSM on NGI Deployment Execution | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2135 | AES-7997 |  |  | GSFA Classified MBE Adoption on COWAN 23.2 (LOE) | 16.5 | 16.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2136 | AES-7998 |  |  | Coordination with GSFA 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2137 | AES-7999 |  |  | Coordination with GSFA 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2138 | AES-8000 |  |  | Coordination with GSFA 23.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2139 | AES-8001 |  |  | Coordination with GSFA 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-2140 | AES-8002 |  |  | Coordination with GSFA 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2141 | AES-8003 |  |  | Coordination with GSFA 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-2142 | AES-8004 |  |  | GSFA Unclass Adoption Investigation for Use Case Pairing | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2143 | AES-8005 |  |  | 23.2.6 COWAN Deployment Planning | 1.25 | 1.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2144 | AES-8006 |  |  | 23.2.5 COWAN Deployment Planning | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-2145 | AES-8007 |  |  | 23.2.4 COWAN Deployment Planning | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-2146 | AES-8008 |  |  | 23.2.3 COWAN Deployment Planning | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2147 | AES-8009 |  |  | 23.2.2 COWAN Deployment Planning | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2148 | AES-8010 |  |  | 23.2.1 COWAN Deployment Planning | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-2149 | AES-8011 |  |  | 23.2.6 COWAN Deployment Execution | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2150 | AES-8012 |  |  | 23.2.5 COWAN Deployment Execution | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-2151 | AES-8013 |  |  | 23.2.4 COWAN Deployment Execution | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2152 | AES-8014 |  |  | 23.2.3 COWAN Deployment Execution | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2153 | AES-8015 |  |  | 23.2.2 COWAN Deployment Execution | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2154 | AES-8016 |  |  | 23.2.1 COWAN Deployment Execution | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-2155 | AES-8017 |  |  | 23.2 Enabler Closure Work for GSFA Adoption | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2156 | AES-8018 |  |  | GSFA architecture diagram | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2157 | AES-8019 |  |  | Program Adoption Team Admin 23.2 (LOE) | 43.75 | 43.75 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2158 | AES-8020 |  |  | SEIT support 23.2.1 <ph> | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2159 | AES-8021 |  |  | Program Adoption DTwin SME | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-2160 | AES-8022 |  |  | SEIT Support - 23.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2161 | AES-8023 |  |  | SEIT Support - 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2162 | AES-8024 |  |  | SEIT Support - 23.2.3: Evaluate Use Cases | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2163 | AES-8025 |  |  | SEIT Support - 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2164 | AES-8026 |  |  | SEIT Support - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2165 | AES-8027 |  |  | SEIT Support - 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2166 | AES-8028 |  |  | DPP Model Updates and Administration - 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2167 | AES-8029 |  |  | DPP Model Updates and Administration - 23.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-2168 | AES-8030 |  |  | DPP Model Updates and Administration - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-2169 | AES-8031 |  |  | DPP Model Updates and Administration - 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-2170 | AES-8032 |  |  | DPP Model Updates and Administration - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-05-31 |  |  | 3
|  |  | SPACE-2171 | AES-8033 |  |  | DPP Model Updates and Administration - 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-2172 | AES-8034 |  |  | Discuss DPP Handoff | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-20 |  |  | 3
|  |  | SPACE-2173 | AES-8035 |  |  | Handoff and Train New DPP Admin | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-2174 | AES-8036 |  |  | SEIT support 23.2.2 <ph> | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-2175 | AES-8037 |  |  | SEIT support 23.2.3 <ph> | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2176 | AES-8038 |  |  | SEIT support 23.2.4 <ph> | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2177 | AES-8039 |  |  | SEIT support 23.2.5 <ph> | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2178 | AES-8040 |  |  | SEIT support 23.2.6 <ph> | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2179 | AES-8041 |  |  | Scrum Master Support 23.2.2 | 0.75 | 0.75 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2180 | AES-8042 |  |  | Scrum Master Support 23.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2181 | AES-8043 |  |  | Scrum Master Support 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-2182 | AES-8044 |  |  | Scrum Master Support 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2183 | AES-8045 |  |  | Scrum Master Support 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2184 | AES-8046 |  |  | Scrum Master Support 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2185 | AES-8047 |  |  | Complete "Who We Are" page for team - Tyler | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-2186 | AES-8048 |  |  | Complete "Who We Are" page for team - Diane | 0 | 0 | 0 | 0% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-2187 | AES-8049 |  |  | Complete "Who We Are" page for team - Jim | 0 | 0 | 0 | 0% | 2023-04-02 | 2023-04-05 |  |  | 3
|  |  | SPACE-2188 | AES-8050 |  |  | ROMB PO - 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-2189 | AES-8051 |  |  | ROMB PO - 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-2190 | AES-8052 |  |  | ROMB PO - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2191 | AES-8053 |  |  | ROMB PO - 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-2192 | AES-8054 |  |  | 23.2 Enabler Closure for Admin Work | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2193 | AES-8055 |  |  | ROMB PO - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2194 | AES-8056 |  |  | ROMB PO - 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2195 | AES-8057 |  |  | ProgAd PO & CRB Support 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-2196 | AES-8058 |  |  | ProgAd PO & CRB Support 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2197 | AES-8059 |  |  | ProgAd PO & CRB Support 23.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2198 | AES-8060 |  |  | ProgAd PO & CRB Support 23.2.4 | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-2199 | AES-8061 |  |  | ProgAd PO & CRB Support 23.2.5 | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-2200 | AES-8062 |  |  | ProgAd PO & CRB Support 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2201 | AES-8063 |  |  | 1LMX DA & ITDE ED&D Support / Alignment Coordination 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-2202 | AES-8064 |  |  | 1LMX DA & ITDE ED&D Support / Alignment Coordination 23.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2203 | AES-8065 |  |  | 1LMX DA & ITDE ED&D Support / Alignment Coordination 23.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2204 | AES-8066 |  |  | 1LMX DA & ITDE ED&D Support / Alignment Coordination 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2205 | AES-8067 |  |  | 1LMX DA & ITDE ED&D Support / Alignment Coordination 23.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2206 | AES-8068 |  |  | 1LMX DA & ITDE ED&D Support / Alignment Coordination 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2207 | AES-8069 |  |  | Increment Demo Prep / Dry-Run | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2208 | AES-8070 |  |  | Increment Demo Execution | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-2209 | AES-8071 |  |  | 23.2 Run Ahead Planning (Part 1) | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2210 | AES-8072 |  |  | 23.2 Run Ahead Planning (Part 2) | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-2211 | AES-8073 |  |  | 23.2 Run Ahead Planning (Part 3) | 1.5 | 1.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2212 | AES-8074 |  |  | Cameo Collaborator Process Check | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-2213 | AES-8075 |  |  | CapCat Connections - 23.2.6 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2214 | AES-8076 |  |  | CapCat Connections - 23.2.5 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2215 | AES-8077 |  |  | Ready Now Caps Hand-Off - 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-2216 | AES-8078 |  |  | CapCat Connections - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2217 | AES-8079 |  |  | CapCat Connections - 23.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2218 | AES-8080 |  |  | CapCat Connections - 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2219 | AES-8081 |  |  | Publish DPP Model to HTML | 0.5 | 0.5 | 0 | 100% | 2023-02-12 | 2023-04-25 |  |  | 3
|  |  | SPACE-2220 | AES-8082 |  |  | Complete "Who We Are" page for team - Dan | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-05-25 |  |  | 3
|  |  | SPACE-2221 | AES-8083 |  |  | Complete "Who We Are" page for team - Isaac | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-2222 | AES-8084 |  |  | Complete "Who We Are" page for team - Olga | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-2223 | AES-8085 |  |  | Complete "Who We Are" page for team - Kris | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-2224 | AES-8086 |  |  | Complete "Who We Are" page for team - Keegan | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-2225 | AES-8087 |  |  | Complete "Who We Are" page for team - Russ | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-2226 | AES-8088 |  |  | Complete "Who We Are" page for team - Steve | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-2227 | AES-8089 |  |  | Complete "Who We Are" page for team - Katie | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-03 |  |  | 3
|  |  | SPACE-2228 | AES-8090 |  |  | Program Adoption Month End May | 0 | 0 | 0 | 0% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2229 | AES-8091 |  |  | Program Adoption Month End April | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2230 | AES-8092 |  |  | MBE Orientation - Ashley | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-2231 | AES-8093 |  |  | MBE Orientation Part 2 - Ashley | 7 | 7 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2232 | AES-8094 |  |  | Ready Now Scorecard compilation and delivery - 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2233 | AES-8095 |  |  | Use Case Demos & Program/Solution Pairings 23.2 (LOE) | 53.25 | 53.25 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2234 | AES-8096 |  |  | Use Case Development and SK Updates - 23.2.3 | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2235 | AES-8097 |  |  | Use Case Development and SK Updates - 23.2.4 | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2236 | AES-8098 |  |  | Use Case Development and SK Updates - 23.2.5 | 3 | 3 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2237 | AES-8099 |  |  | Use Case Development and SK Updates - 23.2.6 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2238 | AES-8100 |  |  | Develop TSP Templates for SK - 23.2.1 | 2.5 | 2.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2239 | AES-8101 |  |  | Develop TSP Templates for SK - 23.2.2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2240 | AES-8102 |  |  | Develop TSP Templates for SK - 23.2.3 | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2241 | AES-8103 |  |  | SP - TSP Coordination | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2242 | AES-8104 |  |  | Use Case / Tutorials / Workflows 23.2.1 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2243 | AES-8105 |  |  | DRM Pilot Integrate MBE disciplines to mF/V workflow - 23.2.1 | 2.5 | 2.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2244 | AES-8106 |  |  | Webify demo/workflow dev (part 1) | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2245 | AES-8107 |  |  | Use Case / Tutorials / Workflows 23.2.2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-2246 | AES-8108 |  |  | Webify demo/workflow dev (part 2) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2247 | AES-8109 |  |  | DRM Pilot Integrate MBE disciplines to mF/V workflow - 23.2.4 | 2.5 | 2.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2248 | AES-8110 |  |  | SDM upskilling training/familiarization - 23.2.6 | 1.25 | 1.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2249 | AES-8111 |  |  | Create/update templates (part 1) | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-2250 | AES-8112 |  |  | Create/update templates (part 2) | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-2251 | AES-8113 |  |  | Create/update templates (part 3) | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-2252 | AES-8114 |  |  | Use Case Development and SK Updates - 23.2.1 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2253 | AES-8115 |  |  | Use Case Development and SK Updates - 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2254 | AES-8116 |  |  | Brainstorm program - solution - functional pairings for future | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2255 | AES-8117 |  |  | Use Case / Tutorials / Workflows 23.2.5 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2256 | AES-8118 |  |  | Use Case / Tutorials / Workflows 23.2.6 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2257 | AES-8119 |  |  | DRM Pilot Integrate MBE disciplines to mF/V workflow - 23.2.2 | 2.5 | 2.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2258 | AES-8120 |  |  | DRM Pilot Integrate MBE disciplines to mF/V workflow - 23.2.3 | 2.25 | 2.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2259 | AES-8121 |  |  | DRM Pilot Integrate MBE disciplines to mF/V workflow - 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2260 | AES-8122 |  |  | DRM Pilot Integrate MBE disciplines to mF/V workflow - 23.2.6 | 2.5 | 2.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2261 | AES-8123 |  |  | 23.2 Enabler Closure for Use Case Work | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2262 | AES-8124 |  |  | MBE Program Adoption 23.2 (LOE) | 75 | 75 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2263 | AES-8125 |  |  | TSM Program Adoption Support | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2264 | AES-8126 |  |  | TSM Program Adoption Support | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2265 | AES-8127 |  |  | TSM Program Adoption Support | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2266 | AES-8128 |  |  | TSM Program Adoption Support | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2267 | AES-8129 |  |  | TSM Program Adoption Support | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2268 | AES-8130 |  |  | TSM Program Adoption Support | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2269 | AES-8131 |  |  | MSOL Program Coordination - 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2270 | AES-8132 |  |  | Review lessons gathered by 1LMX DA team | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2271 | AES-8133 |  |  | CPS Program Coordination - 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2272 | AES-8134 |  |  | ASP Program Coordination - 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2273 | AES-8135 |  |  | Mk21A Program Coordination - 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2274 | AES-8136 |  |  | FBM Program Coordination - 23.2.1 | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2275 | AES-8137 |  |  | ASP Program Coordination - 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2276 | AES-8138 |  |  | CPS Program Coordination - 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2277 | AES-8139 |  |  | FBM Program Coordination - 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2278 | AES-8140 |  |  | Mk21A Program Coordination - 23.2.2 | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-2279 | AES-8141 |  |  | ASP Program Coordination - 23.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2280 | AES-8142 |  |  | FBM Program Coordination - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2281 | AES-8143 |  |  | CPS Program Coordination - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2282 | AES-8144 |  |  | ASP Program Coordination - 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2283 | AES-8145 |  |  | CPS Program Coordination - 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2284 | AES-8146 |  |  | FBM Program Coordination - 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2285 | AES-8147 |  |  | ASP Program Coordination - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2286 | AES-8148 |  |  | FBM Program Coordination - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2287 | AES-8149 |  |  | CPS Program Coordination - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2288 | AES-8150 |  |  | ASP Program Coordination: New Capabilities - 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2289 | AES-8151 |  |  | CPS Program Coordination: New Capabilities - 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2290 | AES-8152 |  |  | FBM Program Coordination: New Capabilities - 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2291 | AES-8153 |  |  | Update Program Adoption Plans: ASP | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-2292 | AES-8154 |  |  | Update Program Adoption Plans: CPS/CPS JFC | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2293 | AES-8155 |  |  | Update Program Adoption Plans: FBM | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-05 |  |  | 3
|  |  | SPACE-2294 | AES-8156 |  |  | Update Program Adoption Plans: Mk21A | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-2295 | AES-8157 |  |  | Update Program Adoption Plans: GPI | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2296 | AES-8158 |  |  | MilSpace Program Coordination 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2297 | AES-8159 |  |  | MilSpace Program Coordination 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2298 | AES-8160 |  |  | MilSpace Program Coordination 23.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2299 | AES-8161 |  |  | MilSpace Program Coordination 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2300 | AES-8162 |  |  | MilSpace Program Coordination 23.2.5 | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2301 | AES-8163 |  |  | MilSpace Program Coordination 23.2.6 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2302 | AES-8164 |  |  | MSOL Program Coordination - 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2303 | AES-8165 |  |  | MSOL Program Coordination - 23.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2304 | AES-8166 |  |  | MSOL Program Coordination - 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2305 | AES-8167 |  |  | MSOL Program Coordination - 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2306 | AES-8168 |  |  | MSOL Program Coordination - 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2307 | AES-8169 |  |  | 23.2.1 DarkStar Deployment Planning | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-2308 | AES-8170 |  |  | Support DX competition - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2309 | AES-8171 |  |  | Support DX competition - 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-2310 | AES-8172 |  |  | Support DX competition - 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-05 |  |  | 3
|  |  | SPACE-2311 | AES-8173 |  |  | Support DX competition - 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2312 | AES-8174 |  |  | Misc. Program Engagement 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-2313 | AES-8175 |  |  | Misc. Program Engagement 23.2.2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2314 | AES-8176 |  |  | Misc. Program Engagement 23.2.3 | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2315 | AES-8177 |  |  | Misc. Program Engagement 23.2.4 | 1.5 | 1.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2316 | AES-8178 |  |  | Misc. Program Engagement 23.2.5 | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2317 | AES-8179 |  |  | Misc. Program Engagement 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2318 | AES-8180 |  |  | SP & MilSpace Program Engagement 23.2.1 | 0 | 0 | 0 | 0% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2319 | AES-8181 |  |  | SP & MilSpace Program Engagement 23.2.2 | 0 | 0 | 0 | 0% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2320 | AES-8182 |  |  | SP & MilSpace Program Engagement 23.2.4 | 0 | 0 | 0 | 0% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2321 | AES-8183 |  |  | SP & MilSpace Program Engagement 23.2.5 | 0 | 0 | 0 | 0% | 2023-05-28 | 2023-06-11 |  |  | 3
|  |  | SPACE-2322 | AES-8184 |  |  | SP & MilSpace Program Engagement 23.2.6 | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2323 | AES-8185 |  |  | Support DX competition 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2324 | AES-8186 |  |  | Support DX competition 23.2.4 | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-2325 | AES-8187 |  |  | Support DX competition 23.2.5 | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-05-31 |  |  | 3
|  |  | SPACE-2326 | AES-8188 |  |  | Support DX competition 23.2.6 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2327 | AES-8189 |  |  | 23.2 Enabler Closure Work for Program Adoption Work | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2328 | AES-8190 |  |  | SP Program (P819, Mustang, Zoran) Coordination 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2329 | AES-8191 |  |  | SP Program (P819, Mustang, Zoran) Coordination 23.2.6 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2330 | AES-8192 |  |  | SP Program (P819, Mustang, Zoran) Coordination 23.2.5 | 1.5 | 1.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2331 | AES-8193 |  |  | SP Program (P819, Mustang, Zoran) Coordination 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2332 | AES-8194 |  |  | SP Program (P819, Mustang, Zoran) Coordination 23.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2333 | AES-8195 |  |  | SP Program (P819, Mustang, Zoran) Coordination 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2334 | AES-8196 |  |  | CCS Program Engagement 23.2.1 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2335 | AES-8197 |  |  | CCS Program Engagement 23.2.2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2336 | AES-8198 |  |  | CCS Program Engagement 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-2337 | AES-8199 |  |  | CCS Program Engagement 23.2.5 | 2 | 2 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2338 | AES-8200 |  |  | CCS Program Engagement 23.2.6 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2339 | AES-8201 |  |  | 23.2.6 DarkStar Deployment Planning | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2340 | AES-8202 |  |  | 23.2.5 DarkStar Deployment Planning | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2341 | AES-8203 |  |  | 23.2.4 DarkStar Deployment Planning | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2342 | AES-8204 |  |  | 23.2.3 DarkStar Deployment Planning | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2343 | AES-8205 |  |  | 23.2.2 DarkStar Deployment Planning | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2344 | AES-8206 |  |  | 23.2.1 Enablers Collaboration | 0.25 | 0.25 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-2345 | AES-8207 |  |  | 23.2.2 CNET/LMSPAN Status | 0.25 | 0.25 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2346 | AES-8208 |  |  | 23.2.3 Enablers Collaboration | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-14 |  |  | 3
|  |  | SPACE-2347 | AES-8209 |  |  | 23.2.4 CNET/LMSPAN Status | 0.25 | 0.25 | 0 | 100% | 2023-05-14 | 2023-05-28 |  |  | 3
|  |  | SPACE-2348 | AES-8210 |  |  | 23.2.5 Enablers Collaboration | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2349 | AES-8211 |  |  | 23.2.6 CNET/LMSPAN Status | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2350 | AES-8212 |  |  | Update/Create COE Confluence Adoption Plans - 23.2.6 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2351 | AES-8213 |  |  | COE Stakeholder/Program Engagement & Adoption Plans- 23.2.6 | 2.5 | 2.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2352 | AES-8214 |  |  | COE Stakeholder/Program Engagement - 23.2.2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2353 | AES-8215 |  |  | Update/Create COE Confluence Adoption Plans - 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2354 | AES-8216 |  |  | COE Stakeholder/Program Engagement - 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2355 | AES-8217 |  |  | Update/Create COE Confluence Adoption Plans - 23.2.3 | 0.25 | 0.25 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2356 | AES-8218 |  |  | Update/Create COE Confluence Adoption Plans - 23.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-28 | 2023-06-07 |  |  | 3
|  |  | SPACE-2357 | AES-8219 |  |  | COE Stakeholder/Program Engagement - 23.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2358 | AES-8220 |  |  | COE Stakeholder/Program Engagement - 23.2.4 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2359 | AES-8221 |  |  | Update/Create COE Confluence Adoption Plans - 23.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2360 | AES-8222 |  |  | Update/Create COE Confluence Adoption Plans - 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2361 | AES-8223 |  |  | COE Stakeholder/Program Engagement - 23.2.1 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2362 | AES-8224 |  |  | Ops Efficiency | 1 | 1 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2363 | AES-8225 |  |  | GSFA classified TSM deployment software versions | 0.25 | 0.25 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-2364 | AES-8226 |  |  | GSFA classified TSM deployment software versions pt.2 | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2365 | AES-8227 |  |  | Ops Efficiency pt.2 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2366 | AES-8228 |  |  | VWI feedback | 0.25 | 0.25 | 0 | 100% | 2023-06-11 | 2023-06-25 |  |  | 3
|  |  | SPACE-2367 |  |  |  | SLMX_MBE_SCATS | 386 | 386 | 0 | 100% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-2368 | AES-8229 | ONELMX_MBE_SSC | MBE23LOE | Spc MBE: SCATS LOE 23.2 - Exp - Lab/NL | 386 | 386 | 0 | 100% | 2023-03-12 | 2023-06-26 | 2023-03-27 | 2023-06-23 | 1
|  |  | SPACE-2369 | AES-8230 |  |  | 23.2 UX: Requirements Management | 4.5 | 4.5 | 0 | 100% |  |  | 2023-04-04 | 2023-06-23 | 2
|  |  | SPACE-2370 | AES-8231 |  |  | UX: Applicable WCAG UX Requirements Review | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-28 |  |  | 3
|  |  | SPACE-2371 | AES-8232 |  |  | UX: Automated UX Requirements | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2372 | AES-8233 |  |  | Test: Create MILSTD-1472H Spreadsheet | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-06 |  |  | 3
|  |  | SPACE-2373 | AES-8234 |  |  | Test: Develop Use and Accessibility Requirements | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2374 | AES-8235 |  |  | Test: Develop UX and Accessibility Requirements | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-26 |  |  | 3
|  |  | SPACE-2375 | AES-8236 |  |  | Test: Agreement reached on the categorization of Use and Accessibility Requirements. | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2376 | AES-8237 |  |  | 23.2 UX Support | 4 | 4 | 0 | 100% |  |  | 2023-04-09 | 2023-06-23 | 2
|  |  | SPACE-2377 | AES-8238 |  |  | UX: 2023.2 PI Planning Support | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-03 |  |  | 3
|  |  | SPACE-2378 | AES-8239 |  |  | UX: WCAG UX Requirements Review - Continued | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2379 | AES-8240 |  |  | Test: Support UX Design Effort | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2380 | AES-8241 |  |  | Test: Support UX Design Effort | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2381 | AES-8242 |  |  | Test: Support UX development | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2382 | AES-8243 |  |  | 23.2 Architecture Support | 11 | 11 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2383 | AES-8244 |  |  | Review Space Digital Transformation Architecture Standards to adopt as our new checklist | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-12 |  |  | 3
|  |  | SPACE-2384 | AES-8245 |  |  | Support modeling standards for rapid need drawings | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2385 | AES-8246 |  |  | Arch: Support and review our new Guardrails checklist for | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2386 | AES-8247 |  |  | Work with Nelson to undersatnd the scope of Space 1LMX MBE Architecture for 2025 | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-12 |  |  | 3
|  |  | SPACE-2387 | AES-8248 |  |  | Arch: Plan the stakeholder engagement and data collection strategy to shape Space 1LMX MBE Architecture for 2025 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2388 | AES-8249 |  |  | Refine Value Stream Deliverables to reflect current Roadmap view 23.2.3 | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2389 | AES-8250 |  |  | Refine Value Stream Deliverables to reflect current Roadmap view 23.2.4 | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2390 | AES-8251 |  |  | Refine Value Stream Deliverables to reflect current Roadmap view 23.2.5 | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-09 |  |  | 3
|  |  | SPACE-2391 | AES-8252 |  |  | 23.2 Cyber Support | 96 | 96 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2392 | AES-8253 |  |  | Cyber: OpenShift, Containers and Kubernetes Courses | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-16 |  |  | 3
|  |  | SPACE-2393 | AES-8254 |  |  | Cyber: Capabilities Overview | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2394 | AES-8255 |  |  | Cyber: Application Deployment via OpenShift | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-09 |  |  | 3
|  |  | SPACE-2395 | AES-8256 |  |  | Cyber: Application Container Security Guide | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-08 |  |  | 3
|  |  | SPACE-2396 | AES-8257 |  |  | Cyber: Guidance Checkups for Harden Environments | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2397 | AES-8258 |  |  | Cyber: NIST 800-53 Security Objectives | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2398 | AES-8259 |  |  | Cyber: Attend MBE ERB/CCB and ROMB (S2) | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-25 |  |  | 3
|  |  | SPACE-2399 | AES-8260 |  |  | Cyber: Attend MBE ERB/CCB and ROMB (S3) | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2400 | AES-8261 |  |  | Cyber: Attend MBE ERB/CCB and ROMB (S4) | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-22 |  |  | 3
|  |  | SPACE-2401 | AES-8262 |  |  | Cyber: Attend MBE ERB/CCB and ROMB (S5) | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2402 | AES-8263 |  |  | Cyber: Attend MBE ERB/CCB and ROMB (S6) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2403 | AES-8264 |  |  | Cyber: Daily Stand Up (S2) | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2404 | AES-8265 |  |  | Cyber: Daily Stand Up (S3) | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2405 | AES-8266 |  |  | Cyber: Daily Stand Up (S4) | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2406 | AES-8267 |  |  | Cyber: Daily Stand Up (S5) | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2407 | AES-8268 |  |  | Cyber: PI 2 Support | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-06 |  |  | 3
|  |  | SPACE-2408 | AES-8269 |  |  | Cyber: Sprint 2 Planning | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-25 |  |  | 3
|  |  | SPACE-2409 | AES-8270 |  |  | Cyber: Sprint 3 Planning | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2410 | AES-8271 |  |  | Cyber: Workload Alignment (S4) | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2411 | AES-8272 |  |  | Cyber: Workload Alignment (S5) | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2412 | AES-8273 |  |  | Cyber: Workload Alignment (S6) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-2413 | AES-8274 |  |  | Cyber: Run Ahead Work for PI 3 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2414 | AES-8275 |  |  | Cyber: Leadership MBE PMO Tag Up (S2) | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2415 | AES-8276 |  |  | Cyber: Leadership MBE PMO Tag Up (S3) | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2416 | AES-8277 |  |  | Cyber: Leadership MBE PMO Tag Up (S4) | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2417 | AES-8278 |  |  | Cyber: Leadership MBE PMO Tag Up (S5) | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-07 |  |  | 3
|  |  | SPACE-2418 | AES-8279 |  |  | Cyber: Leadership SISO Tag Up (May) | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2419 | AES-8280 |  |  | Cyber: SISO Mini MOR - May | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2420 | AES-8281 |  |  | Cyber: Cyber PM Oversite (S1) | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2421 | AES-8282 |  |  | Cyber: Cyber PM Oversite (S2) | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2422 | AES-8283 |  |  | Cyber: Cyber PM Oversite (S3) | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2423 | AES-8284 |  |  | Cyber: Cyber PM Oversite (S4) | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2424 | AES-8285 |  |  | Cyber: Cyber PM Oversite (S5) | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2425 | AES-8286 |  |  | Cyber: Cyber PM Oversite (S6) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2426 | AES-8287 |  |  | Cyber: Innovation Brainstorming and Planning | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2427 | AES-8288 |  |  | Cyber: On-board New Employee | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2428 | AES-8289 |  |  | Cyber: Socialize Cyber Approval Process Flow w/ MBE Program | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2429 | AES-8290 |  |  | Cyber: Sprint 1 Planning | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-10 |  |  | 3
|  |  | SPACE-2430 | AES-8291 |  |  | Cyber: Daily Stand Up (S6) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2431 | AES-8292 |  |  | Cyber: Innovation Brainstorming | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2432 | AES-8293 |  |  | Cyber: SBOM reporting automation | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-12 |  |  | 3
|  |  | SPACE-2433 | AES-8294 |  |  | Cyber: Increment 1 Demo | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-18 |  |  | 3
|  |  | SPACE-2434 | AES-8295 |  |  | Cyber: Eng. Eff. Design Automation Status Review | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-09 |  |  | 3
|  |  | SPACE-2435 | AES-8296 |  |  | Cyber: Increment 1 Demo | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-19 |  |  | 3
|  |  | SPACE-2436 | AES-8297 |  |  | Cyber: Increment 1 Demo | 5 | 5 | 0 | 100% | 2023-04-17 | 2023-04-18 |  |  | 3
|  |  | SPACE-2437 | AES-8298 |  |  | Cyber: Increment 1 Demo | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-18 |  |  | 3
|  |  | SPACE-2438 | AES-8299 |  |  | Cyber: Increment 1 Demo | 3 | 3 | 0 | 100% | 2023-04-17 | 2023-04-19 |  |  | 3
|  |  | SPACE-2439 | AES-8300 |  |  | Cyber: Increment 1 Demo | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-19 |  |  | 3
|  |  | SPACE-2440 | AES-8301 |  |  | Cyber: Vulnerability Consolidation Step (Aqua) | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2441 | AES-8302 |  |  | Cyber: False Positive pipeline step creation | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-2442 | AES-8303 |  |  | Cyber: Reporting MVP | 3 | 3 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2443 | AES-8304 |  |  | Cyber: Capability Level Consolidation | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-12 |  |  | 3
|  |  | SPACE-2444 | AES-8305 |  |  | Cyber: Update Cyber Approval Process Flow | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2445 | AES-8306 |  |  | Cyber: Governance for Development LMI Environments | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-30 |  |  | 3
|  |  | SPACE-2446 | AES-8307 |  |  | Cyber: Threat Driven Methodologies for Cyber | 3 | 3 | 0 | 100% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2447 | AES-8308 |  |  | Cyber: ASP NIST 800-53 API Generator | 3 | 3 | 0 | 100% | 2023-04-03 | 2023-04-16 |  |  | 3
|  |  | SPACE-2448 | AES-8309 |  |  | Cyber: Investigate other Cloud Scanning Tools (Hoppr Cop) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-2449 | AES-8310 |  |  | Cyber: Starburst Query | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2450 | AES-8311 |  |  | Cyber: Learn Bulk Load Process for Jira Stories | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2451 | AES-8312 |  |  | Cyber: Attend MBE ERB/CCB and ROMB (S1) | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-10 |  |  | 3
|  |  | SPACE-2452 | AES-8313 |  |  | Cyber: Shane's Innovation (Cyber Dashboard) | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2453 | AES-8314 |  |  | Cyber: Vulnerability Consolidation Step (SCA, SAST, Secrets) | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2454 | AES-8315 |  |  | Cyber: Deliver ASP update to ERB ready | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2455 | AES-8316 |  |  | MBE Cyber Process Flow Review | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-2456 | AES-8317 |  |  | SMBE Cyber Capability Review | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-2457 | AES-8318 |  |  | Cyber: NIST 800-53 Security Objectives Research | 3 | 3 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2458 | AES-8319 |  |  | Cyber: Investigate Aqua, SCA False Positive pipeline step creation (Part 1) | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2459 | AES-8320 |  |  | Cyber: Cross Training | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2460 | AES-8321 |  |  | Cyber: Download, Install, and Configure Developer Desktop | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2461 | AES-8322 |  |  | Cyber: Finalize Cyber Approval Process Flow | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2462 | AES-8323 |  |  | Cyber: Support for IAT GSFA CARB Approval | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-16 |  |  | 3
|  |  | SPACE-2463 | AES-8324 |  |  | Cyber: Governance Update | 3 | 3 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2464 | AES-8325 |  |  | Cyber: Cyber Dashboard Secrets integration | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-05-31 |  |  | 3
|  |  | SPACE-2465 | AES-8326 |  |  | Cyber: SISO MOR - June | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2466 | AES-8327 |  |  | Cyber: Provide Technical Direction | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2467 | AES-8328 |  |  | Cyber: Provide Technical Direction | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2468 | AES-8329 |  |  | Cyber: SISO MOR - June Finalize | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-13 |  |  | 3
|  |  | SPACE-2469 | AES-8330 |  |  | 23.2 UX: MBE Design System | 2.5 | 2.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-2470 | AES-8331 |  |  | UX: MBE Style Guide Review | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2471 | AES-8332 |  |  | UX: MBE Style Guide Revisions | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2472 | AES-8333 |  |  | 23.2 Test Support | 32 | 32 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2473 | AES-8334 |  |  | Test: SCEE Coordination - 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2474 | AES-8335 |  |  | Test: Enablers Coordination - 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2475 | AES-8336 |  |  | Test: Enablers Coordination - 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2476 | AES-8337 |  |  | Test: Enablers Coordination - 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2477 | AES-8338 |  |  | Test: SCEE Coordination - 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2478 | AES-8339 |  |  | Test: SCEE Coordination - 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2479 | AES-8340 |  |  | Test: Enablers Coordination - 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2480 | AES-8341 |  |  | Test: Enablers Coordination - 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2481 | AES-8342 |  |  | Test: Enablers Coordination - 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2482 | AES-8343 |  |  | Test: SCEE Coordination - 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2483 | AES-8344 |  |  | Test: SCEE Coordination - 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2484 | AES-8345 |  |  | Test: SCEE Coordination - 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-26 |  |  | 3
|  |  | SPACE-2485 | AES-8346 |  |  | Test: Enablers Coordination - 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2486 | AES-8347 |  |  | Test: Enablers Coordination - 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2487 | AES-8348 |  |  | Test: Support SMBE Team Coordination | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2488 | AES-8349 |  |  | Test: SCEE Coordination - 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-03 |  |  | 3
|  |  | SPACE-2489 | AES-8350 |  |  | Test: SCEE Coordination - 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2490 | AES-8351 |  |  | Test: Refine TSM Performance Requirements | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2491 | AES-8352 |  |  | Test: SMBE Team Coordination - 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2492 | AES-8353 |  |  | Test: SMBE Team Coordination - 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2493 | AES-8354 |  |  | Test: Support SMBE Team Coordination | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2494 | AES-8355 |  |  | Test: Mature Intelligent Assembly Test Cases | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-24 |  |  | 3
|  |  | SPACE-2495 | AES-8356 |  |  | Test: Update V&V Plan | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-06-22 |  |  | 3
|  |  | SPACE-2496 | AES-8357 |  |  | Test: SMBE Team - 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2497 | AES-8358 |  |  | Test: SMBE Team Coordination - 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2498 | AES-8359 |  |  | Test: Support SMBE Team Coordination | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2499 | AES-8360 |  |  | Test: Enablers Coordination - 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2500 | AES-8361 |  |  | Test: Enablers Coordination - 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2501 | AES-8362 |  |  | Test: Support SMBE Team Coordination | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2502 | AES-8363 |  |  | Test: SCEE Coordination - 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-2503 | AES-8364 |  |  | Test: SCEE Coordination - 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-2504 | AES-8365 |  |  | Test: Tech Review the New and Updated Checklists | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-24 |  |  | 3
|  |  | SPACE-2505 | AES-8366 |  |  | Test: Update Guardrail Checklist - 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2506 | AES-8367 |  |  | Test: Obtain ERB/CCB Approval of New and Updated Checklists | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2507 | AES-8368 |  |  | Requirements Support | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-12 |  |  | 3
|  |  | SPACE-2508 | AES-8369 |  |  | Test: Explore Options for Password Maintenance | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-25 |  |  | 3
|  |  | SPACE-2509 | AES-8370 |  |  | Test: Automated Test Coordination | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2510 | AES-8371 |  |  | Test: Automated Test Coordination | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2511 | AES-8372 |  |  | Test: Playwright Familiarization | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2512 | AES-8373 |  |  | Test: Playwright Familiarization | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2513 | AES-8374 |  |  | Test: Support SEIT and Governance Board Reviews | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2514 | AES-8375 |  |  | Test: Support SEIT and Governance Board Reviews | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-19 |  |  | 3
|  |  | SPACE-2515 | AES-8376 |  |  | Test: Support SEIT and Governance Board Reviews | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-02 |  |  | 3
|  |  | SPACE-2516 | AES-8377 |  |  | Test: Support SEIT and Governance Board Reviews | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-2517 | AES-8378 |  |  | Test: Explore Automated Test Tools for Testing Intelligent Assembly | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2518 | AES-8379 |  |  | Test: Configure Postman in Windows and Linux | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-22 |  |  | 3
|  |  | SPACE-2519 | AES-8380 |  |  | Test: Exploratory Testing with Postman | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-24 |  |  | 3
|  |  | SPACE-2520 | AES-8381 |  |  | Test: Establish a Windows Configuration for Playwright/Selenium | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2521 | AES-8382 |  |  | Test: SMBE Team - 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2522 | AES-8383 |  |  | Test: Playwright Reporter Development | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2523 | AES-8384 |  |  | Test: Selenium Reporter Development | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2524 | AES-8385 |  |  | 23.2 Software Support | 36.5 | 36.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-24 | 2
|  |  | SPACE-2525 | AES-8386 |  |  | SW: SW Team Support | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2526 | AES-8387 |  |  | SM: Scrum Master (Sprint Wk1) | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2527 | AES-8388 |  |  | SM: Scrum Master (Sprint Wk2) | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2528 | AES-8389 |  |  | SW: SW Team Support (Sprint Wk1) | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2529 | AES-8390 |  |  | SW: Update SDP with Changes | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-14 |  |  | 3
|  |  | SPACE-2530 | AES-8391 |  |  | SW: SW Team Support (Sprint Wk2) | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2531 | AES-8392 |  |  | SW: Software Process Mgmt (Sprint Wk1) | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2532 | AES-8393 |  |  | SW: Software Process Mgmt (Sprint Wk2) | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2533 | AES-8394 |  |  | SM: Scrum Master | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2534 | AES-8395 |  |  | SW: SW Functional Support (Wk2 of Sprint) | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2535 | AES-8396 |  |  | SW: Software Process Mgmt | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2536 | AES-8397 |  |  | SW: SW Functional Support (Wk1 of Sprint) | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2537 | AES-8398 |  |  | SW: SDP Review and Understand Needed Updates | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2538 | AES-8399 |  |  | SW: Scrum Master (Sprint Wk1) | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-08 |  |  | 3
|  |  | SPACE-2539 | AES-8400 |  |  | SM: Scrum Master: Sprint 3, Wk2 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2540 | AES-8401 |  |  | SW: SW Team Support (Sprint Wk1) | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-08 |  |  | 3
|  |  | SPACE-2541 | AES-8402 |  |  | SW: SW Team Support (Sprint Wk2) | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2542 | AES-8403 |  |  | SW: Software Process Mgmt (Sprint Wk1) | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-08 |  |  | 3
|  |  | SPACE-2543 | AES-8404 |  |  | SW: Process Mgmt. SDP & Continuous Delivery | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2544 | AES-8405 |  |  | SW: SW Functional Support (Wk1 of Sprint) | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-08 |  |  | 3
|  |  | SPACE-2545 | AES-8406 |  |  | SW: SW Function: Staffing, Resource Planning | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2546 | AES-8407 |  |  | SW: SW Team Support (Sprint Wk1) | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-2547 | AES-8408 |  |  | SW: SW Team Support 23.2.4.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2548 | AES-8409 |  |  | SM: Scrum Master (Sprint Wk1) | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-2549 | AES-8410 |  |  | SM: Scrum Master 23.2.4.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2550 | AES-8411 |  |  | SW: SW Functional Support (Wk1 of Sprint) | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-2551 | AES-8412 |  |  | SW: SW Functional Support 23.2.4.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2552 | AES-8413 |  |  | SM: PI3 Run Ahead Work | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2553 | AES-8414 |  |  | SW: Software Process Mgmt (Sprint Wk1) | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-2554 | AES-8415 |  |  | SW: Software Process Mgmt 23.2.4.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2555 | AES-8416 |  |  | SM: Scrum Master 23.2.5.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2556 | AES-8417 |  |  | SM: Scrum Master 23.2.6.1 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2557 | AES-8418 |  |  | SW: SW Team Support 23.2.5.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2558 | AES-8419 |  |  | SW: SW Team Support 23.2.6.1 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2559 | AES-8420 |  |  | SW: SW Team Support 23.2.5.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2560 | AES-8421 |  |  | SW: SW Team Support (Sprint Wk2) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2561 | AES-8422 |  |  | SM: Scrum Master 23.2.5.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2562 | AES-8423 |  |  | SM: Scrum Master (Sprint Wk2) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2563 | AES-8424 |  |  | SW: Software Process Mgmt 23.2.5.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2564 | AES-8425 |  |  | SW: Software Process Mgmt 23.2.6.1 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2565 | AES-8426 |  |  | SW: Software Process Mgmt 23.2.5.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2566 | AES-8427 |  |  | SW: Software Process Mgmt (Sprint Wk2) | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2567 | AES-8428 |  |  | SM: PI3 Run Ahead Work | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2568 | AES-8429 |  |  | SW: SW Functional Support 23.2.5.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2569 | AES-8430 |  |  | SW: SW Functional Support 23.2.6.1 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-16 |  |  | 3
|  |  | SPACE-2570 | AES-8431 |  |  | SW: SW Functional Support 23.2.5.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2571 | AES-8432 |  |  | SW: SW Functional Support (Wk2 of Sprint) | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2572 | AES-8433 |  |  | SM: 23.3 Run Ahead Work | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2573 | AES-8434 |  |  | SW: Functional Support | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2574 | AES-8435 |  |  | CE: Lead Active Engagement with Intercax/Syndeia -- Iteration 23.2.1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-06 |  |  | 3
|  |  | SPACE-2575 | AES-8436 |  |  | CE: Lead Active Engagement with Intercax/Syndeia -- Iteration 23.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2576 | AES-8437 |  |  | CE: Lead Active Engagement with Intercax/Syndeia -- Iteration 23.2.3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2577 | AES-8438 |  |  | CE: Lead Active Engagement with Intercax/Syndeia -- Iteration 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-22 |  |  | 3
|  |  | SPACE-2578 | AES-8439 |  |  | CE: Lead Active Engagement with Intercax/Syndeia -- Iteration 23.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2579 | AES-8440 |  |  | CE: Lead Active Engagement with Intercax/Syndeia -- Iteration 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2580 | AES-8441 |  |  | SW: SDP Baseline Updates 23.2.4.2 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2581 | AES-8442 |  |  | SW: Staffing Support 23.2.4 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2582 | AES-8443 |  |  | SW: Staffing Support 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2583 | AES-8444 |  |  | SW: Staffing Support 23.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2584 | AES-8445 |  |  | SW: SDP Review & Update 23.2.5 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2585 | AES-8446 |  |  | 23.2 SEIT Support | 37.5 | 37.5 | 0 | 100% |  |  | 2023-04-04 | 2023-06-23 | 2
|  |  | SPACE-2586 | AES-8447 |  |  | SEIT: Content Reviews -S6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2587 | AES-8448 |  |  | SEIT: Dependency Management -S6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2588 | AES-8449 |  |  | SEIT: Content Reviews -S5 | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2589 | AES-8450 |  |  | SEIT: Dependency Management - S5 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2590 | AES-8451 |  |  | SEIT: ORR/ERB/CCB Support -S5 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2591 | AES-8452 |  |  | SEIT: External Dependency Coordination - S5 | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2592 | AES-8453 |  |  | SEIT: PI Run Ahead Activities - S5 | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2593 | AES-8454 |  |  | SEIT: Content Reviews -S4 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2594 | AES-8455 |  |  | SEIT: Dependency Management -S4 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2595 | AES-8456 |  |  | SEIT: ERB/CCB Support -S4 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2596 | AES-8457 |  |  | SEIT: 1:1's- S4 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2597 | AES-8458 |  |  | SEIT: Content Reviews - S3 | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2598 | AES-8459 |  |  | SEIT: Dependency Management -S3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2599 | AES-8460 |  |  | SEIT: ORR/ERB/CCB Support -S3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2600 | AES-8461 |  |  | SEIT: Content Reviews - S2 | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-2601 | AES-8462 |  |  | SEIT: Dependency Management -S2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-24 |  |  | 3
|  |  | SPACE-2602 | AES-8463 |  |  | SEIT: Update Skeleton for UAF guidance - S2 | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-24 |  |  | 3
|  |  | SPACE-2603 | AES-8464 |  |  | SEIT: ATLAS PERFORM- S2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-26 |  |  | 3
|  |  | SPACE-2604 | AES-8465 |  |  | SEIT: PI Planning Run Ahead | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2605 | AES-8466 |  |  | SEIT: ORR/ERB/CCB Support -S6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-14 |  |  | 3
|  |  | SPACE-2606 | AES-8467 |  |  | SEIT: Staffing - S1 | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-10 |  |  | 3
|  |  | SPACE-2607 | AES-8468 |  |  | SEIT: Subscription Alerting Services | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2608 | AES-8469 |  |  | SEIT: SEMP Baseline Update - S1 | 3 | 3 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2609 | AES-8470 |  |  | Test: New Team Member On-Boarding | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2610 | AES-8471 |  |  | Test: New Team Member On-Boarding | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2611 | AES-8472 |  |  | Test: New Team Member On-Boarding | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2612 | AES-8473 |  |  | SEIT: add direction for link summary diagrams to skeleton model | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-11 |  |  | 3
|  |  | SPACE-2613 | AES-8474 |  |  | Test: New Team Member On-Boarding | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2614 | AES-8475 |  |  | SEIT: Support Sprint 1 | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2615 | AES-8476 |  |  | SEIT Support Sprint 2 | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-26 |  |  | 3
|  |  | SPACE-2616 | AES-8477 |  |  | SEIT: Requirements Flattening start | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-25 |  |  | 3
|  |  | SPACE-2617 | AES-8478 |  |  | SEIT: Support Sprint 3.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-03 |  |  | 3
|  |  | SPACE-2618 | AES-8479 |  |  | SEIT: Support Sprint 4.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-22 |  |  | 3
|  |  | SPACE-2619 | AES-8480 |  |  | SEIT: Support Sprint 5.1 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2620 | AES-8481 |  |  | SEIT: Support Sprint 6.1 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2621 | AES-8482 |  |  | SEIT: ATLAS PERFORM- S3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2622 | AES-8483 |  |  | SEIT: 1:1's- S4 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-24 |  |  | 3
|  |  | SPACE-2623 | AES-8484 |  |  | SEIT: PI Run Ahead Activities - S5 | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-12 |  |  | 3
|  |  | SPACE-2624 | AES-8485 |  |  | SEIT: PI Planning Run Ahead | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2625 | AES-8486 |  |  | SEIT: PI Run Ahead Activities - S4 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2626 | AES-8487 |  |  | Test: New Team Member On-Boarding | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2627 | AES-8488 |  |  | Test: Support In-Person Demos | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-24 |  |  | 3
|  |  | SPACE-2628 | AES-8489 |  |  | SEIT: Prepare and Present SMBE Requirements at Townhall Meeting | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2629 | AES-8490 |  |  | 23.2 Cyber: CRRA Support | 88.5 | 88.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2630 | AES-8491 |  |  | CRRA: Create Initial Draft for Module 2 (Integrating CRRA into a program’s System Architecture Model (SAM)) | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2631 | AES-8492 |  |  | CRRA: Evaluate pre-req training options. (1) | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-14 |  |  | 3
|  |  | SPACE-2632 | AES-8493 |  |  | CRRA: Manage Task 1 for Sprint 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-14 |  |  | 3
|  |  | SPACE-2633 | AES-8494 |  |  | CRRA: Review Initial Draft for Module 1 (Cyber Resiliency) | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2634 | AES-8495 |  |  | CRRA: Continue OCSMP Course in Atlas (2) | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2635 | AES-8496 |  |  | CRRA: Review Initial Draft for Module 2 (Integrating CRRA into a program’s System Architecture Model (SAM)) | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2636 | AES-8497 |  |  | CRRA: Manage Task 1 for Sprint 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-28 |  |  | 3
|  |  | SPACE-2637 | AES-8498 |  |  | CRRA: Create Initial Draft for Module 1 (Cyber Resiliency) | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-28 |  |  | 3
|  |  | SPACE-2638 | AES-8499 |  |  | CRRA: Develop Specialized Structure for Missile Platform | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-06 |  |  | 3
|  |  | SPACE-2639 | AES-8500 |  |  | CRRA: Develop Shared Embedded System Reference Architecture | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-06 |  |  | 3
|  |  | SPACE-2640 | AES-8501 |  |  | CRRA: Manage Task 1 for Sprint 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2641 | AES-8502 |  |  | CRRA: Manage Task 1 for Sprint 4 | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2642 | AES-8503 |  |  | CRRA: Manage Task 1 for Sprint 5 | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2643 | AES-8504 |  |  | CRRA: Manage Task 1 for Sprint 6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2644 | AES-8505 |  |  | CRRA: Evaluate pre-req training options. (3) | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2645 | AES-8506 |  |  | CRRA: Refine Modules 1 and 2 | 3 | 3 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2646 | AES-8507 |  |  | Cyber: CRRA/Profile Modeling Investigation | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2647 | AES-8508 |  |  | CRRA: Task 2 - Fellow Support | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2648 | AES-8509 |  |  | CRRA: Task 2 - Fellow Support | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2649 | AES-8510 |  |  | CRRA: Peer review for the SIEM pattern and resiliency behavior relationships. | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-05-15 |  |  | 3
|  |  | SPACE-2650 | AES-8511 |  |  | CRRA: Peer review the Specialized Structure for Satellite Platform | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2651 | AES-8512 |  |  | CRRA: Peer review the Specialized Structure for Missile Platform | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-14 |  |  | 3
|  |  | SPACE-2652 | AES-8513 |  |  | CRRA: Task 2 - Fellow Support | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-17 |  |  | 3
|  |  | SPACE-2653 | AES-8514 |  |  | CRRA: Draft a SIEM pattern and approach coordination. | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2654 | AES-8515 |  |  | CRRA: SIEM pattern and resiliency behavior relationships | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2655 | AES-8516 |  |  | CRRA: States and Modes | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-17 |  |  | 3
|  |  | SPACE-2656 | AES-8517 |  |  | CRRA: States and Modes | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-2657 | AES-8518 |  |  | CRRA: Develop Specialized Structure for Satellite Platform | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-06 |  |  | 3
|  |  | SPACE-2658 | AES-8519 |  |  | CRRA: Task 1 - Fellow Support | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-09 |  |  | 3
|  |  | SPACE-2659 | AES-8520 |  |  | CRRA: Evaluate pre-req training options. (2) | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-28 |  |  | 3
|  |  | SPACE-2660 | AES-8521 |  |  | CRRA: Begin OCSMP Course in Atlas (1) | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-28 |  |  | 3
|  |  | SPACE-2661 | AES-8522 |  |  | CRRA: KDM Blade Risk Management Review | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-24 |  |  | 3
|  |  | SPACE-2662 | AES-8523 |  |  | CRRA: Task 1 - Understand RMS use of CRRA | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-26 |  |  | 3
|  |  | SPACE-2663 | AES-8524 |  |  | CRRA: Task 2 - Fellow Support | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-2664 | AES-8525 |  |  | CRRA: Task 1 - Fellow Support | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2665 | AES-8526 |  |  | CRRA: Task 1 - Fellow Support | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2666 | AES-8527 |  |  | CRRA: Peer review the Tactical Ground System Structure | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2667 | AES-8528 |  |  | CRRA: Task 2 - Fellow Support | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-09 |  |  | 3
|  |  | SPACE-2668 | AES-8529 |  |  | CRRA: Task 1 - Fellow Support | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2669 | AES-8530 |  |  | CRRA: Peer review for the Embedded System Reference Architecture. | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2670 | AES-8531 |  |  | CRRA: Develop high-level architecture for a Tactical Ground System | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-2671 | AES-8532 |  |  | CRRA: Peer review for the Satellite System Reference Architecture. | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2672 | AES-8533 |  |  | CRRA: Create Tom Sawyer Perspective (TSP) Use Cases | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2673 | AES-8534 |  |  | CRRA: CRRA Teams Coordination | 3 | 3 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-2674 | AES-8535 |  |  | CRRA: CRRA Teams Coordination | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2675 | AES-8536 |  |  | CRRA: CRRA Teams Coordination | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2676 | AES-8537 |  |  | CRRA: CRRA Teams Coordination | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2677 | AES-8538 |  |  | CRRA: Update the SMBE Starter Kit CRRA page with content | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2678 | AES-8539 |  |  | CRRA: Peer review for the Missile System Reference Architecture. | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2679 | AES-8540 |  |  | CRRA: Continue OCSMP Course in Atlas (3) | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-15 |  |  | 3
|  |  | SPACE-2680 | AES-8541 |  |  | CRRA: Cyber Implementation (Encryption) | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-09 |  |  | 3
|  |  | SPACE-2681 | AES-8542 |  |  | CRRA: Cyber Implementation (Encryption) Behavior Mapping | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-09 |  |  | 3
|  |  | SPACE-2682 | AES-8543 |  |  | CRRA: Review CRRA Checklists | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-2683 | AES-8544 |  |  | CRRA: Review Use Cases | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-2684 | AES-8545 |  |  | CRRA: Peer review for the SIEM pattern and resiliency behavior relationships. | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2685 | AES-8546 |  |  | CRRA: Tom Sawyer Perspective (TSP) view development | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2686 | AES-8547 |  |  | CRRA: Integrate Missile System Reference Architecture with CRRA construct. | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2687 | AES-8548 |  |  | CRRA: Integrate Satellite System Reference Architecture with CRRA construct. | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2688 | AES-8549 |  |  | CRRA: Integrate Embedded System Reference Architecture with CRRA construct. | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2689 | AES-8550 |  |  | CRRA: Follow-up on Tactical Ground System Reference Architecture | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2690 | AES-8551 |  |  | CRRA: Embedded System with Cyber Resilient Exchanges | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2691 | AES-8552 |  |  | CRRA: Embedded System Reference Architecture - Threat Model | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2692 | AES-8553 |  |  | CRRA: States and Modes | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-30 |  |  | 3
|  |  | SPACE-2693 | AES-8554 |  |  | CRRA: States and Modes | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2694 | AES-8555 |  |  | CRRA: Continue OSCMP Course | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2695 | AES-8556 |  |  | CRRA: Create Tactical Ground System Reference Architecture in Cameo | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-09 |  |  | 3
|  |  | SPACE-2696 | AES-8557 |  |  | CRRA: Mapping resiliency behaviors to model elements | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2697 | AES-8558 |  |  | CRRA: 1LMx SMBE Starter Kit webpage | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2698 | AES-8559 |  |  | CRRA: Peer review for the Tactical Ground System model. | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2699 | AES-8560 |  |  | CRRA: Continue OSCMP Course | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2700 | AES-8561 |  |  | CRRA: Peer review for the cyber implementation (encryption). | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-06-16 |  |  | 3
|  |  | SPACE-2701 | AES-8562 |  |  | CRRA: Refine Modules 1 and 2 | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2702 | AES-8563 |  |  | CRRA: States and Modes | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-09 |  |  | 3
|  |  | SPACE-2703 | AES-8564 |  |  | CRRA: Continue OSCMP Course | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-09 |  |  | 3
|  |  | SPACE-2704 | AES-8565 |  |  | CRRA: Task 1 - Fellow Support | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-07 |  |  | 3
|  |  | SPACE-2705 | AES-8566 |  |  | CRRA: Task 2 - Fellow Support | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-07 |  |  | 3
|  |  | SPACE-2706 | AES-8567 |  |  | CRRA: 1LMx SMBE Starter Kit webpage | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2707 | AES-8568 |  |  | CRRA: CRRA Teams Coordination | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2708 | AES-8569 |  |  | CRRA: Start OSCMP Course | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2709 | AES-8570 |  |  | CRRA: Package Module 1 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-23 |  |  | 3
|  |  | SPACE-2710 | AES-8571 |  |  | CRRA: Peer review feedback for SIEM cyber implementation pattern | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2711 | AES-8572 |  |  | CRRA: Peer review feedback for Encryption cyber implementation pattern | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2712 | AES-8573 |  |  | CRRA: Peer review feedback for SIEM cyber implementation pattern | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2713 | AES-8574 |  |  | 23.2 Manage SMBE Governance Processes | 46.5 | 46.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-25 | 2
|  |  | SPACE-2714 | AES-8575 |  |  | CE: SMBE Project Cross-Check -- Iteration 6 | 2 | 2 | 0 | 100% | 2023-03-12 | 2023-06-19 |  |  | 3
|  |  | SPACE-2715 | AES-8576 |  |  | CE: Detailed SMBE Project Review -- Iteration 3 | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2716 | AES-8577 |  |  | PO: Run-Ahead work for Next PI Planning (Iteration 4) | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-24 |  |  | 3
|  |  | SPACE-2717 | AES-8578 |  |  | PO: Run-Ahead work for Next PI Planning (Iteration 5) | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2718 | AES-8579 |  |  | CE: Perform Product Owner (PO) Tasking -- Iteration 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2719 | AES-8580 |  |  | CE: Perform Product Owner (PO) Tasking -- Iteration 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2720 | AES-8581 |  |  | CE: Perform Product Owner (PO) Tasking -- Iteration 23.2.3 | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2721 | AES-8582 |  |  | CE: Perform Product Owner (PO) Tasking -- Iteration 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2722 | AES-8583 |  |  | CE: Perform Product Owner (PO) Tasking -- Iteration 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2723 | AES-8584 |  |  | CE: Perform Product Owner (PO) Tasking -- Iteration 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2724 | AES-8585 |  |  | CE/CA: Prepare to Host SMBE Roadmap Overview | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2725 | AES-8586 |  |  | CE: Lead/Support Governance Boards -- Iteration 23.2.1 | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-06 |  |  | 3
|  |  | SPACE-2726 | AES-8587 |  |  | CE: Lead/Support Governance Boards -- Iteration 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2727 | AES-8588 |  |  | CE: Lead/Support Governance Boards -- Iteration 23.2.3 | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2728 | AES-8589 |  |  | CE: Lead/Support Governance Boards -- Iteration 23.2.4 | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-2729 | AES-8590 |  |  | CE: Lead/Support Governance Boards -- Iteration 23.2.5 | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2730 | AES-8591 |  |  | CE: Lead/Support Governance Boards -- Iteration 23.2.6 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-2731 | AES-8592 |  |  | PO: Run-Ahead work for Next PI Planning (Iteration 6) | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2732 | AES-8593 |  |  | CE: Lead/Support SMBE Program Increment 23.1 Demos | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-04-19 |  |  | 3
|  |  | SPACE-2733 | AES-8594 |  |  | CE: Develop Draft CRB Process Change ¦ Utilize Action Item | 3 | 3 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2734 | AES-8595 |  |  | CE: Propose New CRB Process via Jira Action Item -- Iteration 23.2.2 | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2735 | AES-8596 |  |  | 23.2.2 SEMP: Minor update - Milestones reflecting deliverable product to customer | 0 | 0 | 0 | 0% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2736 | AES-8597 |  |  | 23.2.2 SCEE Roadmap: Swap Syndeia Connector Increments for Zuken DS-CR and E3 | 0 | 0 | 0 | 0% | 2023-05-01 | 2023-05-08 |  |  | 3
|  |  | SPACE-2737 | AES-8598 |  |  | 23.2.2 SDM Adoption Scope Focus Change | 0 | 0 | 0 | 0% | 2023-04-17 | 2023-04-20 |  |  | 3
|  |  | SPACE-2738 | AES-8599 |  |  | CE: Complete and Publish New ERB Process | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2739 | AES-8600 |  |  | SECATS: Provide Feedback on Innovation Week / Priorities -- Iteration 23.2.2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2740 | AES-8601 |  |  | SMBE Change Request Template: CLONE to generate a new Change Request -- Increment 23.2 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2741 | AES-8602 |  |  | CE: Detailed Cyber ASP Review -- Iteration 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2742 | AES-8603 |  |  | Support Governance Boards 23.2.3 | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2743 | AES-8604 |  |  | CE: Direct Support for SP CNET 1LMX Digital Tools Acceleration SIA | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-03 |  |  | 3
|  |  | SPACE-2744 | AES-8605 |  |  | Change Digital Twin Platform Baseline Q3 Milestone to Focus on PROD-Readiness | 0 | 0 | 0 | 0% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2745 | AES-8606 |  |  | Change Quarter from 23Q3 to 24Q1 for BOM Integration Milestone | 0 | 0 | 0 | 0% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2746 | AES-8607 |  |  | SMBE Change Request Operations Efficiency -- Increment 23.2 | 0 | 0 | 0 | 0% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-2747 | AES-8608 |  |  | Cyber: Capability Fielding Requirements Update | 3 | 3 | 0 | 100% | 2023-05-01 | 2023-05-20 |  |  | 3
|  |  | SPACE-2748 | AES-8609 |  |  | Delete DTs for Mustang 2023Q3 Milestone | 0 | 0 | 0 | 0% | 2023-05-15 | 2023-05-30 |  |  | 3
|  |  | SPACE-2749 | AES-8610 |  |  | SMBE Change Request 23.2.4: SDP Revision Plan & Updates | 0 | 0 | 0 | 0% | 2023-05-15 | 2023-05-22 |  |  | 3
|  |  | SPACE-2750 | AES-8611 |  |  | RE: 23.1.6 Cameo/Zuken E3 Model Standardization and Integration | 0 | 0 | 0 | 0% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2751 | AES-8612 |  |  | SECATS Month End May | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-05 |  |  | 3
|  |  | SPACE-2752 | AES-8613 |  |  | SECATS Month End April | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-09 |  |  | 3
|  |  | SPACE-2753 | AES-8614 |  |  | Support Governance Boards 23.2.4 | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-2754 | AES-8615 |  |  | CE: Quarterly Review of the MBE Plan (Program Adoption) | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-17 |  |  | 3
|  |  | SPACE-2755 | AES-8616 |  |  | CE: Prepare and Present Roadmap Accomplishments at Townhall Meeting | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-07 |  |  | 3
|  |  | SPACE-2756 | AES-8617 |  |  | SDM TCRA Scope Removal | 0 | 0 | 0 | 0% | 2023-05-30 | 2023-06-01 |  |  | 3
|  |  | SPACE-2757 | AES-8618 |  |  | Support Governance Boards 23.2.5 | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-09 |  |  | 3
|  |  | SPACE-2758 | AES-8619 |  |  | Support Governance Boards 23.2.6 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2759 | AES-8620 |  |  | Space Guardrail Checklist Update | 0 | 0 | 0 | 0% | 2023-05-30 | 2023-06-14 |  |  | 3
|  |  | SPACE-2760 | AES-8621 |  |  | Reduce Scope for MPMLink Development for Q2 | 0 | 0 | 0 | 0% | 2023-05-30 | 2023-06-12 |  |  | 3
|  |  | SPACE-2761 | AES-8622 |  |  | SEIT Support of Enablers Team 2023.2 | 27 | 27 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-2762 | AES-8623 |  |  | SEIT Support 2023.2.1 | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-2763 | AES-8624 |  |  | SEIT Support 2023.2.6 | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2764 | AES-8625 |  |  | SEIT Support 2023.2.5 | 6 | 6 | 0 | 100% | 2023-05-28 | 2023-06-12 |  |  | 3
|  |  | SPACE-2765 | AES-8626 |  |  | SEIT Support 2023.2.4 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2766 | AES-8627 |  |  | SEIT Support 2023.2.3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-2767 | AES-8628 |  |  | SEIT Support 2023.2.2 | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-05-01 |  |  | 3
|  |  | SPACE-2768 | AES-8629 |  |  | UAF Actual Resource Diagram Fundamentals | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2769 | AES-8630 |  |  | Enablers System Actual Resource Diagram | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2770 | AES-8631 |  |  | UAF Actual Resources Connectivity Diagram Fundamentals | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2771 | AES-8632 |  |  | Actual Resources Connectivity Diagram for Enablers System | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2772 | AES-8633 |  |  | Make adjustments to Volta Actual Resource Diagram | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2773 |  |  |  | SLMX_MBE_SCEE | 408.5 | 408.5 | 0 | 100% |  |  |  |  | 0
1.5 | 1.3.1.5 | 4.2.05.232C.0008 | SPACE-2774 | AES-8634 | ONELMX_MBE_SSC | MBETEE23CP | Spc MBE: Impl. TSM 4.0, Thin Thread 1.0 - Cap Lab/NL | 359.5 | 359.5 | 0 | 100% | 2023-01-15 | 2023-06-26 | 2023-04-03 | 2023-06-23 | 1
| 1.3.1.5 |  | SPACE-2775 | AES-8635 |  |  | CAP: E2E DT: Thin Thread 1.0 | 41.5 | 41.5 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-2776 | AES-8636 |  |  | TT Metrics | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2777 | AES-8637 |  |  | TT Metrics | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-2778 | AES-8638 |  |  | TT Metrics | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2779 | AES-8639 |  |  | TT Metrics | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2780 | AES-8640 |  |  | TT Metrics | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-2781 | AES-8641 |  |  | TT Metrics | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2782 | AES-8642 |  |  | Engineering Domain Interview | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-2783 | AES-8643 |  |  | Metric Consolidation | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2784 | AES-8644 |  |  | Metric Consolidation | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-2785 | AES-8645 |  |  | Metric Consolidation | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2786 | AES-8646 |  |  | Metric Consolidation | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-2787 | AES-8647 |  |  | Metric Data Collection | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-2788 | AES-8648 |  |  | Metric Data Collection | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-2789 | AES-8649 |  |  | TSM Zuken DS-CR Connection Verification | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2790 | AES-8650 |  |  | TSM Zuken DS-CR SEIT Peer Review | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2791 | AES-8651 |  |  | Clean up TT Confluence | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-2792 | AES-8652 |  |  | Hook up DOORS-Next Testbed with TSM | 0.5 | 0.5 | 0 | 100% | 2023-01-15 | 2023-04-04 |  |  | 3
|  |  | SPACE-2793 | AES-8653 |  |  | Torus Capability Walkthrough | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-05 |  |  | 3
|  |  | SPACE-2794 | AES-8654 |  |  | Populate SMBE EKG | 1.5 | 1.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2795 | AES-8655 |  |  | Thin Thread Parametric Model work | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2796 | AES-8656 |  |  | IL Space Guard Rail | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2797 | AES-8657 |  |  | Thin Thread Parametric Model work | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2798 | AES-8658 |  |  | Thin Thread Parametric Model work | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2799 | AES-8659 |  |  | Thin Thread Parametric Model work | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2800 | AES-8660 |  |  | Thin Thread Parametric Model work | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2801 | AES-8661 |  |  | Create 5 min TT demo | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-14 |  |  | 3
|  |  | SPACE-2802 | AES-8662 |  |  | Cyber: TSM Zuken DS-CR Connection Review | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2803 | AES-8663 |  |  | TT Metrics Support | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-2804 | AES-8664 |  |  | TT Metrics Support | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2805 | AES-8665 |  |  | TT Metrics Support | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2806 | AES-8666 |  |  | TT Metrics Support | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2807 | AES-8667 |  |  | TT Metrics Support | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-2808 | AES-8668 |  |  | TT Metrics Support | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2809 | AES-8669 |  |  | Write Intercax SOW part 1 of 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2810 | AES-8670 |  |  | Support IT - S1 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2811 | AES-8671 |  |  | Support IT - S2 | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2812 | AES-8672 |  |  | Support IT - S3 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2813 | AES-8673 |  |  | Support IT - S4 | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2814 | AES-8674 |  |  | Support IT - S5 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2815 | AES-8675 |  |  | Support IT - S6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2816 | AES-8676 |  |  | Engineering Domain Interview | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2817 | AES-8677 |  |  | Engineering Domain Interview | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-2818 | AES-8678 |  |  | Populate SMBE EKG | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-25 |  |  | 3
|  |  | SPACE-2819 | AES-8679 |  |  | Populate SMBE EKG | 1.5 | 1.5 | 0 | 100% | 2023-04-30 | 2023-05-25 |  |  | 3
|  |  | SPACE-2820 | AES-8680 |  |  | Write Intercax SOW | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-2821 | AES-8681 |  |  | S-MBE SCEE Familiarization | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-06 |  |  | 3
|  |  | SPACE-2822 | AES-8682 |  |  | Cameo Familiarization | 3 | 3 | 0 | 100% | 2023-05-29 | 2023-06-12 |  |  | 3
|  |  | SPACE-2823 | AES-8683 |  |  | Run Ahead Planning | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
| 1.3.1.5 |  | SPACE-2824 | AES-8684 |  |  | CAP: E2E DT: eQube, MOVEit, Elysium, CP4D Development | 48 | 48 | 0 | 100% |  |  | 2023-04-02 | 2023-06-18 | 2
|  |  | SPACE-2825 | AES-8685 |  |  | eQube Connection / License - Part 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2826 | AES-8686 |  |  | [CP4D] Obtain access to their prod instance part 1 | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2827 | AES-8687 |  |  | [CP4D] Training for connectors and data virtualizations | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2828 | AES-8688 |  |  | [CP4D] Create a Plan to Ingest AF and Q-Note unstructured fields into Watson Discovery | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-2829 | AES-8689 |  |  | [Exper] eQube Training | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2830 | AES-8690 |  |  | [Exper] eQube - get access to eQube environment | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-10 |  |  | 3
|  |  | SPACE-2831 | AES-8691 |  |  | [Exper] eQube/DTw EDW Oracle relational data transfer requirements capture eQube Req #3 (Part-1) | 3 | 3 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2832 | AES-8692 |  |  | [Exper] Cameo Interoperability link to Excel part 1 | 2 | 2 | 0 | 100% | 2023-01-15 | 2023-05-22 |  |  | 3
|  |  | SPACE-2833 | AES-8693 |  |  | [Exper] Cameo Interoperability link to Excel part 2 | 3 | 3 | 0 | 100% | 2023-05-29 | 2023-06-11 |  |  | 3
|  |  | SPACE-2834 | AES-8694 |  |  | Cyber: Review/Targeted Testing of DTs connectors REST API | 3 | 3 | 0 | 100% | 2023-05-30 | 2023-06-09 |  |  | 3
|  |  | SPACE-2835 | AES-8695 |  |  | [Exper] Elysium Training - eQube experiment | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-25 |  |  | 3
|  |  | SPACE-2836 | AES-8696 |  |  | [Exper] eQube - Get EPDM & SDM EIS connector build from EIS Team Req#4 (Part 1) | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2837 | AES-8697 |  |  | eQube Connection / License - Part 2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2838 | AES-8698 |  |  | [CP4D] - Get Access to the Other DT TIBCO Connectors | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-2839 | AES-8699 |  |  | Cyber: Digital Twin CP4D data connector Review | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-24 |  |  | 3
|  |  | SPACE-2840 | AES-8700 |  |  | [Exper] Elysium -Get File conversion licenses for eQube experiment | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-2841 | AES-8701 |  |  | [Exper] Elysium Client access - eQube experiment | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2842 | AES-8702 |  |  | [CP4D] Virtualize DT data sources and replicate the TIBCO views Part 1 | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2843 | AES-8703 |  |  | [CP4D] Virtualize DT data sources and replicate the TIBCO views Part 2 | 3 | 3 | 0 | 100% | 2023-05-29 | 2023-06-11 |  |  | 3
|  |  | SPACE-2844 | AES-8704 |  |  | [CP4D] Virtualize DT data sources and replicate the TIBCO views Part 3 | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2845 | AES-8705 |  |  | [CP4D] Create DTs connectors REST API Part 1 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2846 | AES-8706 |  |  | [CP4D] Obtain access to their dev instance Part 2 | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2847 | AES-8707 |  |  | [CP4D] Obtain access to their dev instance Part 3 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2848 | AES-8708 |  |  | Cameo setup and requirement analysis | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-2849 | AES-8709 |  |  | Cameo Interoperability for DTw - system setup | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2850 | AES-8710 |  |  | eQube Connection Verification and Troubleshooting | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-05-11 |  |  | 3
|  |  | SPACE-2851 | AES-8711 |  |  | eQube Connection Support | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-05-25 |  |  | 3
|  |  | SPACE-2852 | AES-8712 |  |  | eQube Connection Support | 2 | 2 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-2853 | AES-8713 |  |  | eQube Connection Support | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-2854 | AES-8714 |  |  | CAP: E2E DT: Torus 4.0 | 180.5 | 180.5 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-2855 | AES-8715 |  |  | [Torus] Update Torus dependencies page | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2856 | AES-8716 |  |  | Error Message in New Report Dialog refers to Pipeline. | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-01 |  |  | 3
|  |  | SPACE-2857 | AES-8717 |  |  | Delete Saved Search Tool Tip is Incorrect | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2858 | AES-8718 |  |  | Reports Tool Tips Refer to Pipelines | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-01 |  |  | 3
|  |  | SPACE-2859 | AES-8719 |  |  | Project Selection Dialog Displayed Before Menu is Populated | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-22 |  |  | 3
|  |  | SPACE-2860 | AES-8720 |  |  | [Torus] Java Backend - Implement Change Notification Logic | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-2861 | AES-8721 |  |  | [Torus] Extended API - Auth Client Fix Ups | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-2862 | AES-8722 |  |  | [Torus] Extended API - Implement Versioned Container Tags | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-01 |  |  | 3
|  |  | SPACE-2863 | AES-8723 |  |  | [Torus] Extended API - Modify Login Functionality to use the Integration Layer | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2864 | AES-8724 |  |  | [Torus] Extended API - Move Current Login Functionality to API | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2865 | AES-8725 |  |  | [Torus] Extended API - Remove the Auth and Cleanup Pipeline | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2866 | AES-8726 |  |  | [Torus] Java Backend - Implement Versioned Container Tags | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-01 |  |  | 3
|  |  | SPACE-2867 | AES-8727 |  |  | [Torus] Postgres - Implement Versioned Container Tags | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-2868 | AES-8728 |  |  | [Torus] Redis - Implement Versioned Container Tags | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2869 | AES-8729 |  |  | [Torus] Implement Versioned Container on release tag in UI | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-01 |  |  | 3
|  |  | SPACE-2870 | AES-8730 |  |  | [Torus] extAPI Change CRUD endpoints for Artifact Collections | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-2871 | AES-8731 |  |  | [Torus] UI Change - select results to add to Artifact Collections | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2872 | AES-8732 |  |  | [Torus] UI Change add menu item and layout for Artifact Collections | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2873 | AES-8733 |  |  | [Torus] UI Change connect layouts to CRUD endpoints for Artifact Collections | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-25 |  |  | 3
|  |  | SPACE-2874 | AES-8734 |  |  | [IL] DB Create Cassandra Schema for Artifact Collections | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-2875 | AES-8735 |  |  | [Torus] extAPI Change - create api method to get new versions of artifacts | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-2876 | AES-8736 |  |  | [Torus] DB Implement Schema Migration Solution part 1 | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2877 | AES-8737 |  |  | [Torus] Dynamically Updating cicd pipeline | 1 | 1 | 0 | 100% | 2023-03-12 | 2023-04-11 |  |  | 3
|  |  | SPACE-2878 | AES-8738 |  |  | [Torus] Update FOSS versions for 4.0 | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2879 | AES-8739 |  |  | [Torus] node upgrade | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-2880 | AES-8740 |  |  | [Torus] Backend Change - Format Notification Emails | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2881 | AES-8741 |  |  | [Torus] Backend Change call extAPI to get new Artifact Versions | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2882 | AES-8742 |  |  | [Torus] UI collapse menu into icon tray | 2.5 | 2.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2883 | AES-8743 |  |  | [Torus] UI Core add right tray for displaying details | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2884 | AES-8744 |  |  | [Torus] Investigate date-time stamp timezones in Syndeia | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-21 |  |  | 3
|  |  | SPACE-2885 | AES-8745 |  |  | [Torus] Update Torus Walkthru video 4.0 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-2886 | AES-8746 |  |  | [Torus] Java Backend - Implement Data Access for Change Notification tables | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-2887 | AES-8747 |  |  | [Torus] UX Notifications Design Discussion | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2888 | AES-8748 |  |  | [Torus] extAPI Swagger Docs | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2889 | AES-8749 |  |  | [Torus] Update User Guides | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-21 |  |  | 3
|  |  | SPACE-2890 | AES-8750 |  |  | Support UI/UX design - Notification Lists | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2891 | AES-8751 |  |  | Support Torus Development | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2892 | AES-8752 |  |  | Support Torus Development | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2893 | AES-8753 |  |  | Support Torus Development | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2894 | AES-8754 |  |  | Support Torus Development | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2895 | AES-8755 |  |  | Support Torus Development | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-2896 | AES-8756 |  |  | Cannot Change Report Rule or Value | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-2897 | AES-8757 |  |  | Gremlin query removed from search box if it's a mal-formed query | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-06-01 |  |  | 3
|  |  | SPACE-2898 | AES-8758 |  |  | Reports Search Box Doesn't Retain Search Term When Navigating Off of Page | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-12 |  |  | 3
|  |  | SPACE-2899 | AES-8759 |  |  | [Torus] Implement Refresh/Logout Pop Up | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-15 |  |  | 3
|  |  | SPACE-2900 | AES-8760 |  |  | [Torus] backend add Torus logo to Notification emails | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2901 | AES-8761 |  |  | Support UI/UX design - Reports | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2902 | AES-8762 |  |  | [Torus] UI Results - button tray for actions | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2903 | AES-8763 |  |  | [Torus] Extract Material Icon Font | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2904 | AES-8764 |  |  | UI S&A update to match UX designs | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2905 | AES-8765 |  |  | Cyber: Torus 4.0 Extended API Threat Model Updates | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-06 |  |  | 3
|  |  | SPACE-2906 | AES-8766 |  |  | Cyber: Torus 4.0 Extended API Targeted Testing | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-09 |  |  | 3
|  |  | SPACE-2907 | AES-8767 |  |  | Torus Requirements | 3 | 3 | 0 | 100% | 2023-04-02 | 2023-04-16 |  |  | 3
|  |  | SPACE-2908 | AES-8768 |  |  | Torus 4.0 V&V Pt. 1 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2909 | AES-8769 |  |  | Torus 4.0 V&V Pt. 2 | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-2910 | AES-8770 |  |  | [Torus] DB Saved Extra field in saved queries table | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-2911 | AES-8771 |  |  | [Torus] DB Implement Schema Migration Solution part 2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-2912 | AES-8772 |  |  | Test: Support Test Automation - 1 | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2913 | AES-8773 |  |  | Cameo Smart Text Opportunity Exploration | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2914 | AES-8774 |  |  | Cameo Smart Text Opportunity Exploration Pt. 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2915 | AES-8775 |  |  | Cameo Smart Text Opportunity Exploration Pt. 3 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-2916 | AES-8776 |  |  | Torus Requirements | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2917 | AES-8777 |  |  | Torus Requirements | 2 | 2 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-2918 | AES-8778 |  |  | Torus Requirements | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2919 | AES-8779 |  |  | Torus Requirements | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-2920 | AES-8780 |  |  | Torus Cyber Checklist Pt. 2 | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-12 |  |  | 3
|  |  | SPACE-2921 | AES-8781 |  |  | Test: Support Test Automation- 1 | 0.5 | 0.5 | 0 | 100% | 2023-04-03 | 2023-04-12 |  |  | 3
|  |  | SPACE-2922 | AES-8782 |  |  | Test: Support Test Automation - 2 | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2923 | AES-8783 |  |  | Test: Support Test Automation - 2 | 0.5 | 0.5 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2924 | AES-8784 |  |  | Test: Support Test Automation- 3 | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2925 | AES-8785 |  |  | Test: Support Test Automation - 3 | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2926 | AES-8786 |  |  | SEIT Cyber Checklist- Torus | 2 | 2 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-2927 | AES-8787 |  |  | Test: Update Torus Test Cases - 4 | 3 | 3 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2928 | AES-8788 |  |  | Test: Update Torus Test Cases | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-06-08 |  |  | 3
|  |  | SPACE-2929 | AES-8789 |  |  | Test: Torus Test Planning | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2930 | AES-8790 |  |  | Test: Update Torus Test Cases - 5 | 3 | 3 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2931 | AES-8791 |  |  | Test: TSM History Test Dry-Run Testing | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2932 | AES-8792 |  |  | Test: Perform Torus Performance Testing | 5 | 5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2933 | AES-8793 |  |  | Test: Perform Torus Performance Testing | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-2934 | AES-8794 |  |  | Test: Update Torus & Integration Performance Test Scripts | 3 | 3 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2935 | AES-8795 |  |  | Test: Update Syndeia Performance Test Scripts | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2936 | AES-8796 |  |  | Cyber: Change Notifications Cyber Review - SCEE | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-05 |  |  | 3
|  |  | SPACE-2937 | AES-8797 |  |  | Cyber: Torus 4.0 - Delta Cyber Checklist | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-07 |  |  | 3
|  |  | SPACE-2938 | AES-8798 |  |  | Update TSM Performance Requirements | 1 | 1 | 0 | 100% | 2023-04-03 | 2023-04-13 |  |  | 3
|  |  | SPACE-2939 | AES-8799 |  |  | Test: Update TSM Performance Requirements | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2940 | AES-8800 |  |  | Torus Doesn't Show All Repositories | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-06-22 |  |  | 3
|  |  | SPACE-2941 | AES-8801 |  |  | Correct lint job in extended-api | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-2942 | AES-8802 |  |  | [Torus] UX Email Content Discussion | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-2943 | AES-8803 |  |  | [Torus] UX Notifications System User Experience Discussion | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-30 |  |  | 3
|  |  | SPACE-2944 | AES-8804 |  |  | MR for UI updates | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-24 |  |  | 3
|  |  | SPACE-2945 | AES-8805 |  |  | Support Requirements and design rework | 1.5 | 1.5 | 0 | 100% | 2023-04-02 | 2023-04-12 |  |  | 3
|  |  | SPACE-2946 | AES-8806 |  |  | Deployment Process Error Mitigation | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2947 | AES-8807 |  |  | ClassNotFoundError Bytebuddy in backend service | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-2948 | AES-8808 |  |  | Test: Familiarization with Torus Test Cases | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2949 | AES-8809 |  |  | Test: Familiarization with Torus Test Cases | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-2950 | AES-8810 |  |  | Liquibase usage support | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-2951 | AES-8811 |  |  | eFoss compliance coordination | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-2952 | AES-8812 |  |  | Test: Establish Playwright Connector to Zephyr Scale | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2953 | AES-8813 |  |  | Test: Develop Test Case Skeleton of Collections | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2954 | AES-8814 |  |  | Test: Torus Exploratory Testing in DEV | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2955 | AES-8815 |  |  | Test: Familiarization with Zephyr and Torus Test Cases | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-2956 | AES-8816 |  |  | Test: Familiarization with Zephyr and Torus Test Cases | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-04 |  |  | 3
|  |  | SPACE-2957 | AES-8817 |  |  | Test: Provide Familiarization with Zephyr and Torus Test Cases | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2958 | AES-8818 |  |  | Test: Continue Syndeia Tuning and Optimization | 0.5 | 0.5 | 0 | 100% | 2023-05-01 | 2023-05-13 |  |  | 3
|  |  | SPACE-2959 | AES-8819 |  |  | Test: Discovery: Exploratory Cassandra Tuning and Optimization | 2 | 2 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-2960 | AES-8820 |  |  | SEA - Docker containerization training | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2961 | AES-8821 |  |  | User with One Project Gets No Projects Error | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-06-01 |  |  | 3
|  |  | SPACE-2962 | AES-8822 |  |  | [Torus] UX Notifications - Service Design Ideation | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-2963 | AES-8823 |  |  | [Torus] UX Notifications - Email Layout Design & HTML Structure | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2964 | AES-8824 |  |  | TWC 21 Connection Testing | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-2965 | AES-8825 |  |  | TWC 21 Connection Testing | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-08 |  |  | 3
|  |  | SPACE-2966 | AES-8826 |  |  | TWC 21 Connection Testing Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-2967 | AES-8827 |  |  | [Torus] UI Change connect layouts to CRUD endpoints for Artifact Collections Part 2 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2968 | AES-8828 |  |  | Test: Add and Link Requirements in LM300 Syndeia Instance | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2969 | AES-8829 |  |  | Test: Torus Performance Script Enhancements | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2970 | AES-8830 |  |  | Test: Splunk Dashboard Enhancements | 3 | 3 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2971 | AES-8831 |  |  | Test: Obtain Permission to Use LM400 Data for Testing | 0.5 | 0.5 | 0 | 100% | 2023-05-15 | 2023-06-08 |  |  | 3
|  |  | SPACE-2972 | AES-8832 |  |  | [Torus] UI/UX Collections Look and Feel | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2973 | AES-8833 |  |  | Integration v8.0 Performance Scripts | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-22 |  |  | 3
|  |  | SPACE-2974 | AES-8834 |  |  | Test: Automate Torus System Tests | 2 | 2 | 0 | 100% | 2023-05-15 | 2023-06-08 |  |  | 3
|  |  | SPACE-2975 | AES-8835 |  |  | Test: Torus Performance Script Enhancements | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-25 |  |  | 3
|  |  | SPACE-2976 | AES-8836 |  |  | [Torus] Bug - Report a Bug link is not valid | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-2977 | AES-8837 |  |  | Test: Automate the Torus Menu Test | 3 | 3 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2978 | AES-8838 |  |  | Test: Mature Zephyr Playwright Reporter | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-06 |  |  | 3
|  |  | SPACE-2979 | AES-8839 |  |  | Test: Dry-Run Torus Menu Test | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-06 |  |  | 3
|  |  | SPACE-2980 | AES-8840 |  |  | Test: Torus Dry-Run Testing | 0.5 | 0.5 | 0 | 100% | 2023-05-30 | 2023-06-06 |  |  | 3
|  |  | SPACE-2981 | AES-8841 |  |  | Test: Torus Splunk Dashboard Enhancements | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2982 | AES-8842 |  |  | Test: Polish Torus Performance Test Scripts | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-2983 | AES-8843 |  |  | Populate EKG | 2 | 2 | 0 | 100% | 2023-05-29 | 2023-06-12 |  |  | 3
|  |  | SPACE-2984 | AES-8844 |  |  | Test: Torus Login RFR Test | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2985 | AES-8845 |  |  | Test: Torus Menu RFR Test | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-2986 | AES-8846 |  |  | Test: Torus Feedback and Bug Reporting RFR Test | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-2987 | AES-8847 |  |  | Test: Torus Search & Analysis RFR Test | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-2988 | AES-8848 |  |  | Test: Torus Saved Searches RFR Test | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2989 | AES-8849 |  |  | Test: Torus Reports RFR Test | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-2990 | AES-8850 |  |  | Test: TSM History RFR Test | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-2991 | AES-8851 |  |  | Test: Torus Artifact Collection RFR Test | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-2992 | AES-8852 |  |  | Software Factory Onboarding | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-08 |  |  | 3
|  |  | SPACE-2993 | AES-8853 |  |  | UX: Jess - Review Current UX State of TORUS app | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-12 |  |  | 3
|  |  | SPACE-2994 | AES-8854 |  |  | UX: Jess - Schedule Overview Meetings with SCEE team | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-12 |  |  | 3
|  |  | SPACE-2995 | AES-8855 |  |  | UX: Jess - Review SMBE Organization | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-08 |  |  | 3
|  |  | SPACE-2996 | AES-8856 |  |  | Cyber: Torus 4.0 - Cyber Checklist | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-13 |  |  | 3
|  |  | SPACE-2997 | AES-8857 |  |  | Test: Torus Test Support | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-2998 | AES-8858 |  |  | Test: Torus Test Support | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-2999 | AES-8859 |  |  | Test: Torus Test Support | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-3000 | AES-8860 |  |  | Test: Torus Performance Test Support | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3001 | AES-8861 |  |  | Automate Torus Test Cases | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3002 | AES-8862 |  |  | TWC 21 Connection Testing Part 2 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-3003 | AES-8863 |  |  | Cyber: TSM v4.0 Vulnerability ORR Support | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3004 | AES-8864 |  |  | [Torus] SCA 3.0.0 security findings support | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-3005 | AES-8865 |  |  | Cyber: TSM v4.0 Vulnerability Hopr-Cop ID and Triage | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-3006 | AES-8866 |  |  | Torus 4.0 Space Guardrail Checklist | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-20 |  |  | 3
|  |  | SPACE-3007 | AES-8867 |  |  | SCEE Onboarding | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-3008 | AES-8868 |  |  | Support UI/UX design - Reports | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-3009 | AES-8869 |  |  | Support UI/UX design - DM Links | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-3010 | AES-8870 |  |  | Support UI/UX design - Landing page | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-3011 | AES-8871 |  |  | A search within a S&A Results tab yields unexpected results | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3012 | AES-8872 |  |  | Incorrect list of available Artifact Types after a Repository search | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3013 | AES-8873 |  |  | Saved Searches Allows Deletion of Query Used in Report | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3014 | AES-8874 |  |  | Report a Bug option does not work on Torus Log In page | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3015 | AES-8875 |  |  | Torus Reports email still refers to "Pipelines" | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3016 | AES-8876 |  |  | Report Time Picker Hides Time | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3017 | AES-8877 |  |  | New Report Duplicate Filename Check is Case Insensitive | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3018 | AES-8878 |  |  | Torus S&A "All Versions" Query Returns Only Latest | 0 | 0 | 0 | 0% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3019 | AES-8879 |  |  | CAP: DevSecOps Improvements | 22.5 | 22.5 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-3020 | AES-8880 |  |  | [DevSecOps][CI] Diagram current CI architecture | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-3021 | AES-8881 |  |  | [DevSecOps][Deployment] Coordination with Enablers for Hoppr usage | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-3022 | AES-8882 |  |  | [DevSecOps][Deployment] Coordination with Enablers for Hoppr usage | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-3023 | AES-8883 |  |  | [DevSecOps][Deployment] Investigate Redis packaging | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-08 |  |  | 3
|  |  | SPACE-3024 | AES-8884 |  |  | [DevSecOps][Test] Create Baseline creation in Torus | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-3025 | AES-8885 |  |  | [DevSecOps][Test] Create Notification List | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-3026 | AES-8886 |  |  | [DevSecOps] [Test] Create Search & Analysis test to execute an advanced filter query | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-23 |  |  | 3
|  |  | SPACE-3027 | AES-8887 |  |  | [DevSecOps][Test] Create Saved Query/Search | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3028 | AES-8888 |  |  | [DevSecOps][Test] Define and Execute a Report | 3 | 3 | 0 | 100% | 2023-05-29 | 2023-06-08 |  |  | 3
|  |  | SPACE-3029 | AES-8889 |  |  | [DevSecOps][Test] Bug creation using feedback | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-3030 | AES-8890 |  |  | [DevSecOps] Setup Torus in Sandbox using ArgoCD Part 2 | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-3031 | AES-8891 |  |  | [DevSecOps] Setup Torus in Sandbox using ArgoCD Part 1 | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-3032 | AES-8892 |  |  | [DevSecOps][CI] Publish Helm charts | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3033 | AES-8893 |  |  | [DevSecOps] Run ahead planning | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-3034 | AES-8894 |  |  | Cyber: Track IOF SMBE components for Closure | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-21 |  |  | 3
|  |  | SPACE-3035 | AES-8895 |  |  | [DevSecOps] Run ahead planning | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-3036 | AES-8896 |  |  | [DevSecOps][Test] Save and manipulate Query/Search | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-3037 | AES-8897 |  |  | Test team environment setup | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-3038 | AES-8898 |  |  | [DevSecOps][Test] Create Saved Query/Search | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-3039 | AES-8899 |  |  | CAP: E2E DT: Integration Layer Release 8 | 67 | 67 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-3040 | AES-8900 |  |  | [IL] Finalize AMQ Broker Config | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-3041 | AES-8901 |  |  | [IL] Design Access Control for Baseline Creation | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-3042 | AES-8902 |  |  | [IL] Remove eQube Module from Release 8 | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-3043 | AES-8903 |  |  | [IL] Deploy Release 8 to DEV | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-04 |  |  | 3
|  |  | SPACE-3044 | AES-8904 |  |  | [IL] Finalize Change Report Design | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-3045 | AES-8905 |  |  | [IL] Change Report Cyber Roundtable | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-3046 | AES-8906 |  |  | [IL] Add Token Expiration Input to Integration Layer | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-3047 | AES-8907 |  |  | [IL] Update Governor for Release 8 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-02 |  |  | 3
|  |  | SPACE-3048 | AES-8908 |  |  | [IL] Change Report Cyber Roundtable 2 | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-3049 | AES-8909 |  |  | [IL] Add token expiration field to Vault | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-02 |  |  | 3
|  |  | SPACE-3050 | AES-8910 |  |  | [IL] Align Trunk-Based Development with Integration Layer | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-3051 | AES-8911 |  |  | [IL] Update the regression test procedure for Release 8 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-16 |  |  | 3
|  |  | SPACE-3052 | AES-8912 |  |  | [IL] Deploy Release 8 to QAS | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-3053 | AES-8913 |  |  | [IL] Release 8 Cyber Review | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-3054 | AES-8914 |  |  | Release 8 Regression testing - Capital | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-05-31 |  |  | 3
|  |  | SPACE-3055 | AES-8915 |  |  | [IL] External Tool Connectivity Design - Part 1 | 3 | 3 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-3056 | AES-8916 |  |  | [IL] External Tool Connectivity Design - Part 2 | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-21 |  |  | 3
|  |  | SPACE-3057 | AES-8917 |  |  | [IL] Bug Fix Placeholder | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-20 |  |  | 3
|  |  | SPACE-3058 | AES-8918 |  |  | [IL] AF Normalization Updates | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-3059 | AES-8919 |  |  | [IL] Add Elevated User Group to Project Creation | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-21 |  |  | 3
|  |  | SPACE-3060 | AES-8920 |  |  | [IL] Update Auth Module for Elevated Project Privileges | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-21 |  |  | 3
|  |  | SPACE-3061 | AES-8921 |  |  | [IL] Add AF Data Mappings | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-11 |  |  | 3
|  |  | SPACE-3062 | AES-8922 |  |  | SEIT Cyber Checklist- Integration layer 8 | 2 | 2 | 0 | 100% | 2023-05-29 | 2023-06-08 |  |  | 3
|  |  | SPACE-3063 | AES-8923 |  |  | [IL] Develop Syndeia Data Sync Framework Layout | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-21 |  |  | 3
|  |  | SPACE-3064 | AES-8924 |  |  | [IL] Develop Syndeia Data Sync cronjob service | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-3065 | AES-8925 |  |  | [IL] Document Artifact Collection CRUD Capabilities | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-16 |  |  | 3
|  |  | SPACE-3066 | AES-8926 |  |  | [IL] Artifact Collection Bug/Feature Update Support | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-22 |  |  | 3
|  |  | SPACE-3067 | AES-8927 |  |  | [IL] Update Backup Pruning Logic | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-3068 | AES-8928 |  |  | [IL] Change Report Bug Fix Placeholder | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-3069 | AES-8929 |  |  | [IL] PI1 Increment Demo Support | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-19 |  |  | 3
|  |  | SPACE-3070 | AES-8930 |  |  | [IL] Document AF Artifact Types | 2 | 2 | 0 | 100% | 2023-04-02 | 2023-04-05 |  |  | 3
|  |  | SPACE-3071 | AES-8931 |  |  | [IL] Update Deployment Documentation | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-19 |  |  | 3
|  |  | SPACE-3072 | AES-8932 |  |  | Support Integration Layer Development | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-3073 | AES-8933 |  |  | Support Integration Layer Development | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-3074 | AES-8934 |  |  | Support Integration Layer Development | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-3075 | AES-8935 |  |  | Support Integration Layer Development | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-3076 | AES-8936 |  |  | [IL] Deploy Updates to QAS | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-12 |  |  | 3
|  |  | SPACE-3077 | AES-8937 |  |  | Cyber: Integration Layer Token Authentication Review | 2 | 2 | 0 | 100% | 2023-04-03 | 2023-04-11 |  |  | 3
|  |  | SPACE-3078 | AES-8938 |  |  | Cyber: Integration Layer Token Authentication Targeted Testing | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-11 |  |  | 3
|  |  | SPACE-3079 | AES-8939 |  |  | Integration Layer Requirements Consolidation | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-3080 | AES-8940 |  |  | Integration Layer Requirements Consolidation | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-3081 | AES-8941 |  |  | Integration Layer Requirements Consolidation | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-3082 | AES-8942 |  |  | Test: Update Login Credentials in Syndeia Scripts | 2 | 2 | 0 | 100% | 2023-04-17 | 2023-05-01 |  |  | 3
|  |  | SPACE-3083 | AES-8943 |  |  | Test: Refactor Integration Layer Performance Scripts - 2 | 1 | 1 | 0 | 100% | 2023-04-17 | 2023-04-27 |  |  | 3
|  |  | SPACE-3084 | AES-8944 |  |  | Cyber: Integration Layer Release 8 Cyber Review - SCEE | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-18 |  |  | 3
|  |  | SPACE-3085 | AES-8945 |  |  | Cyber: Integration Layer Release 8 Vulnerability Review (embedded Jackson-Databind & Snakeyaml concerns) | 1 | 1 | 0 | 100% | 2023-05-15 | 2023-05-26 |  |  | 3
|  |  | SPACE-3086 | AES-8946 |  |  | Cyber: AMQ Online depreciation + AMQ Broker Installed (Space I2D2 Force) - SCEE | 1 | 1 | 0 | 100% | 2023-05-01 | 2023-05-10 |  |  | 3
|  |  | SPACE-3087 | AES-8947 |  |  | Torus Shows Repositories Not Connected to Syndeia | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-06-22 |  |  | 3
|  |  | SPACE-3088 | AES-8948 |  |  | Syndeia Web Browser Can't Expand EPDM | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-05-18 |  |  | 3
|  |  | SPACE-3089 | AES-8949 |  |  | Host Integration Layer Deep-Dive Session | 0 | 0 | 0 | 0% |  |  |  |  | 3
|  |  | SPACE-3090 | AES-8950 |  |  | [IL] Implement Java Logic for Collections | 3 | 3 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-3091 | AES-8951 |  |  | [IL] Create Artifact Collection API Endpoints | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3092 | AES-8952 |  |  | [IL] DB Create Cassandra Schema for Artifact Collections | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3093 | AES-8953 |  |  | [IL] AF Get FullDetails | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-3094 | AES-8954 |  |  | Update Service Mesh for External Services | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3095 | AES-8955 |  |  | [IL] CP4D Training | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-24 |  |  | 3
|  |  | SPACE-3096 | AES-8956 |  |  | Test: Automate the Integration Layer Regression Test | 1 | 1 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-3097 | AES-8957 |  |  | Test: Run Integration Performance Benchmarks Against QAS | 2 | 2 | 0 | 100% | 2023-05-30 | 2023-06-08 |  |  | 3
|  |  | SPACE-3098 | AES-8958 |  |  | Update Release 8 SCA Scan | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.232E.0002 | SPACE-3099 | AES-8959 | ONELMX_MBE_SSC | MBE23LOE | Spc MBE: SCEE LOE 23.2 - Exp - Lab/NL | 26 | 26 | 0 | 100% | 2023-04-02 | 2023-06-26 | 2023-03-27 | 2023-06-23 | 1
|  |  | SPACE-3100 | AES-8960 |  |  | 23.2 SCEE LOE | 26 | 26 | 0 | 100% |  |  |  |  | 2
|  |  | SPACE-3101 | AES-8961 |  |  | ROMB support | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-3102 | AES-8962 |  |  | ROMB support | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-21 |  |  | 3
|  |  | SPACE-3103 | AES-8963 |  |  | ROMB support | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-05 |  |  | 3
|  |  | SPACE-3104 | AES-8964 |  |  | ROMB support | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-3105 | AES-8965 |  |  | ROMB support | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-01 |  |  | 3
|  |  | SPACE-3106 | AES-8966 |  |  | ROMB support | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-15 |  |  | 3
|  |  | SPACE-3107 | AES-8967 |  |  | ERB/CCB Support | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-06 |  |  | 3
|  |  | SPACE-3108 | AES-8968 |  |  | ERB/CCB Support | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3109 | AES-8969 |  |  | ERB/CCB Support | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-09 |  |  | 3
|  |  | SPACE-3110 | AES-8970 |  |  | ERB/CCB Support | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-18 |  |  | 3
|  |  | SPACE-3111 | AES-8971 |  |  | ERB/CCB Support | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-01 |  |  | 3
|  |  | SPACE-3112 | AES-8972 |  |  | ERB/CCB Support | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3113 | AES-8973 |  |  | Run Ahead Prep | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-3114 | AES-8974 |  |  | Run Ahead Prep | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-3115 | AES-8975 |  |  | Run Ahead Prep | 3 | 3 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3116 | AES-8976 |  |  | SME Support | 1 | 1 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-3117 | AES-8977 |  |  | SME Support | 1 | 1 | 0 | 100% | 2023-04-16 | 2023-04-26 |  |  | 3
|  |  | SPACE-3118 | AES-8978 |  |  | SME Support | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-3119 | AES-8979 |  |  | SME Support | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-3120 | AES-8980 |  |  | SME Support | 1 | 1 | 0 | 100% | 2023-05-29 | 2023-06-08 |  |  | 3
|  |  | SPACE-3121 | AES-8981 |  |  | SME Support | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3122 | AES-8982 |  |  | Intern Onboarding | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-07 |  |  | 3
|  |  | SPACE-3123 | AES-8983 |  |  | Intern Onboarding | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3124 | AES-8984 |  |  | [Syndeia] REST API Training | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-04 |  |  | 3
|  |  | SPACE-3125 | AES-8985 |  |  | [Syndeia] Graph Query Training | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3126 | AES-8986 |  |  | Run Ahead Planning | 2 | 2 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3127 | AES-8987 |  |  | Scrum Master Tasks | 0.5 | 0.5 | 0 | 100% | 2023-04-02 | 2023-04-17 |  |  | 3
|  |  | SPACE-3128 | AES-8988 |  |  | Scrum Master Tasks | 0.5 | 0.5 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3129 | AES-8989 |  |  | Scrum Master Tasks | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-3130 | AES-8990 |  |  | Scrum Master Tasks | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-26 |  |  | 3
|  |  | SPACE-3131 | AES-8991 |  |  | Scrum Master Tasks | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-06-09 |  |  | 3
|  |  | SPACE-3132 | AES-8992 |  |  | Scrum Master Tasks | 0.5 | 0.5 | 0 | 100% | 2023-05-14 | 2023-05-25 |  |  | 3
|  |  | SPACE-3133 | AES-8993 |  |  | SCEE Month End April | 0.5 | 0.5 | 0 | 100% | 2023-04-30 | 2023-05-05 |  |  | 3
|  |  | SPACE-3134 | AES-8994 |  |  | SCEE Month End May | 0.5 | 0.5 | 0 | 100% | 2023-05-29 | 2023-05-31 |  |  | 3
|  |  | SPACE-3135 | AES-8995 |  |  | Run-Ahead Planning | 1 | 1 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
1.5 | 1.3.1.5 | 4.2.05.232E.0006 | SPACE-3136 | AES-8996 | ONELMX_MBE_SSC | MBETEE23 | Spc MBE: Req. - Release TSM 4.0, Thin Thread 1.0 - Exp Lab | 23 | 23 | 0 | 100% | 2023-03-12 | 2023-06-22 | 2023-04-03 | 2023-06-23 | 1
|  |  | SPACE-3137 | AES-8997 |  |  | Enablers - Thin Thread Support 2023.2 | 20 | 20 | 0 | 100% |  |  | 2023-03-27 | 2023-06-23 | 2
|  |  | SPACE-3138 | AES-8998 |  |  | Thin Thread Support 2023.2.1 | 4.5 | 4.5 | 0 | 100% | 2023-04-02 | 2023-04-13 |  |  | 3
|  |  | SPACE-3139 | AES-8999 |  |  | Thin Thread Support 2023.2.6 | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3140 | AES-9000 |  |  | Thin Thread Support 2023.2.5 | 2.5 | 2.5 | 0 | 100% | 2023-05-28 | 2023-06-08 |  |  | 3
|  |  | SPACE-3141 | AES-9001 |  |  | Thin Thread Support 2023.2.4 | 2 | 2 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-3142 | AES-9002 |  |  | Thin Thread Support 2023.2.3 | 5.5 | 5.5 | 0 | 100% | 2023-04-30 | 2023-05-10 |  |  | 3
|  |  | SPACE-3143 | AES-9003 |  |  | Thin Thread Support 2023.2.2 | 2 | 2 | 0 | 100% | 2023-04-16 | 2023-04-27 |  |  | 3
|  |  | SPACE-3144 | AES-9004 |  |  | Thin Thread - DSE3 | 3 | 3 | 0 | 100% | 2023-05-14 | 2023-05-26 |  |  | 3
|  |  | SPACE-3145 | AES-9005 |  |  | EXP: E2E DT: Integration Layer Release 8 | 3 | 3 | 0 | 100% |  |  | 2023-04-03 | 2023-06-23 | 2
|  |  | SPACE-3146 | AES-9006 |  |  | Release 8 PROD Deployment | 0.5 | 0.5 | 0 | 100% | 2023-06-11 | 2023-06-22 |  |  | 3
|  |  | SPACE-3147 | AES-9007 |  |  | [IL] Investigate Request Timeout - Part 1 | 1 | 1 | 0 | 100% | 2023-04-30 | 2023-05-11 |  |  | 3
|  |  | SPACE-3148 | AES-9008 |  |  | Governor Deployment to PROD | 0.5 | 0.5 | 0 | 100% | 2023-03-12 | 2023-04-13 |  |  | 3
|  |  | SPACE-3149 | AES-9009 |  |  | [IL] Investigate Request Timeout - Part 2 | 1 | 1 | 0 | 100% | 2023-05-14 | 2023-05-17 |  |  | 3
|  |  | SPACE-3150 | AES-9010 |  |  | [IL] Support Cassandra Backup Alternatives | 0 | 0 | 0 | 0% |  |  |  |  | 3